## qandasearchletting_results
Date: | 2022-01-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20220111 | 20220111002 | 2 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/4725r2x71i492jxi7x1fxwugnj2lckc3 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-12-09 09:10 | 2021-12-15 12:45
20220111 | 20220111002 | 2 | HMA Mix Designs | Bid items indicate (2) HMA mix designs. Typical sections & PWL table indicate (4) HMA mix designs. Please provide clarification. | An addendum will be issued to correct this and add the correct bid items. | Mike Coleman | 2 | 2021-12-16 15:12 | 2021-12-20 14:16
20220111 | 20220111002 | 2 | Missing Bid Items: Removing Pavement Butt Joints & Removing Asphaltic Surface Butt Joints | It appears the bid items for removing pavement butt joints and removing asphaltic surface butt joints have be left out of this project; however, they are both detailed out on sheet 10. Can these items and quantities be added to the project? | The bid items will be added via addendum. | Mike Coleman | 3 | 2021-12-22 16:30 | 2021-12-29 09:34
20220111 | 20220111002 | 2 | Lane Closure language - Please Clarify | SP Article 3 states to "Complete all work under continuous outside/inside lane closures as detailed in the plans". Plan sheets for Traffic Control show a single, continuous lane closure from 1630.49 to 2051.24, approximately 8 miles in length. SP Article 5 states "The maximum work zone length will be 5 miles" and "All lane closures shall be removed when work is not in progress". This article also shows the Peak Hours, US-18 table that restricts lane closures during various times of the day/week including a restriction to Segment 3 on WB US-18 from 4:00 to 5:00 PM Monday through Friday. A reasonable person could read Section 3 and the Plans and assume that the lane closures will be long term (up to 48 days), the entire length of the project (8 miles), with traffic shifted onto the shoulders while work in the opposite lane is completed. The same reasonable person could read Section 5 and assume the closures are set/opened daily with a 5 mile limit. Which is correct? | Article 3 (Prosecution and Progress) of the special provisions provides the sequence of operations and indicates that all work is to be completed under continuous outside/inside lane closures as detailed in the plan and refers to Article 5 (Traffic) for details about permitted lane closure times. Article 3 does not mention anything about long term (up to 48 days) lane closures being acceptable for the entire project as the contractor indicated. Article 5 of the special provisions provides the additional requirements for traffic operations during all stages and indicates that the maximum work zone length is 5-miles, that all lane closures shall be removed when not in progress, that this project does have peak hour lane closure restrictions, and mentions other traffic operation requirements for the project. Article 5 is the controlling criteria for traffic operations and is what the contractor should follow when preparing their bids and during construction. | Mike Coleman | 4 | 2021-12-28 11:53 | 2021-12-30 08:17
20220111 | 20220111002 | 2 | Temporary Pavement Marking | Related to the previous question regarding lane closure times/limits - if the closures are to be opened daily when work is not actively occurring, why is the temporary pavement marking to be placed off-alignment on the shoulders (as shown on the Stage Construction Typical Section pages)? This will create a major safety hazard when both lanes are open to traffic as one of the lanes will be much wider than it should be. Also, if the closures are opened daily what is the intent of the Temporary Removable Tape at the start of each lane closure and at ramp locations? Will the contractor need to install this Tape for a maximum 23 hour lane closure? Similar projects have not required temp markings on the shoulder, at the start of lane closures, or at ramps for short term lane closures. | Article 5 (Traffic) of the special provisions indicates that one lane of traffic if each direction must be maintained at all times except during holiday, special event times, or peak hour lane restriction times. When not during those specified time, single lane multi-day closures shall be utilized to perform the work, following the 5-mile maximum work zone length and 3-mile minimum gap between work zones. The closures will only be opened daily during the specified times. Following SDD Traffic Control Lane Closure, Speed Reduction, pavement markings are only removed if lane closure is to be in place 4 or more continuous days and nights. The intent of the temporary pavement marking placed off-alignment and removal of the existing pavement marking lines is only when the lane closure is in place for 4 or more continuous days and nights. For short term lane closures the temporary pavement marking on the shoulder would not be required. | Mike Coleman | 5 | 2021-12-30 09:32 | 2022-01-03 14:46
20220111 | 20220111002 | 2 | Marking Removal Line Water Blasting | Related to the previous question regarding lane closure times/limits - if the closures are to be opened daily when work is not actively occurring, what is the intent of the Water Blasting item? Does the edgeline need to be removed for a short term lane closure that does not stay in place? Also, the miscellaneous quantities table for Temporary Pavement Marking shows the Water Blasting to be done in Stages 1-3. Why is Water Blasting required for pavement that does not remain at the completion of the project? All the lines to be removed in these stages will be covered by multiple layers of asphalt. | Article 5 (Traffic) of the special provisions indicates that one lane of traffic if each direction must be maintained at all times except during holiday, special event times, or peak hour lane restriction times. When not during those specified time, single lane multi-day closures shall be utilized to perform the work, following the 5-mile maximum work zone length and 3-mile minimum gap between work zones. The closures will only be opened daily during the specified times. Following SDD Traffic Control Lane Closure, Speed Reduction, pavement markings are only removed if lane closure is to be in place 4 or more continuous days and nights. The intent of the temporary pavement marking and water blasting is only when the lane closure is in place for 4 or more continuous days and nights. For short term lane closures the temporary pavement marking and water blasting would not be required. Water blasting is included for Stages 1-3 because single lane multi-day closures (exceeding 4 or more continuous days and nights) are anticipated during those stages, so the existing pavement marking and temporary pavement marking will have to be removed prior to being covered up by asphalt in Stages 4-7. | Mike Coleman | 6 | 2021-12-30 09:37 | 2022-01-03 14:47
20220111 | 20220111002 | 2 | Lane Closure Concern | Article 5, Section C, "Single Lane Closures on USH 18 are not permitted during Peak Hours as Shown in the Peak Hour table." As Base Patching Concrete has a multiday cure time, are we correct to assume that for the sections called out in the Peak Hour table, the Base Patching SHES item will be used? | The intent was to limit the amount of Base Patching Concrete SHES because of concerns of the long-term durability of the product due to subjecting it to early traffic loading and for the contractor to stage work accordingly to primarily use standard Base Patching Concrete. Based on Article 5, Section C and the Peak Hour restrictions the majority of the base patching for Westbound USH 18 would need to be completed during night/weekend hours in order to limit the amount of Base Patching Concrete SHES unless granted approval from the engineer and regional traffic engineer. | Fred Schunke | 7 | 2022-01-03 12:41 | 2022-01-04 16:16
20220111 | 20220111002 | 2 | BASE PATCHING CONCRETE AND BASE PATCHING CONCRETE SHES QUANTITY | With the answer to question 7 stating that the roadway will need to follow the article 5 section c table you will need to change all the base patching to SHES concrete. Without the use of calcium chloride and 9 bag concrete the pavement strengths will not meet the strength criteria to open the work area to traffic daily during the peak hours. | The following changes are in an upcoming addenda. The quantities for bid items 390.0303 Base Patching Concrete and 390.0403 Base Patching Concrete SHES were revised. The quantities for bid item 390.0303 in Segments 1, 2, and 3, as specified in Article 5 Section C of the special provisions, were shifted to bid item 390.0403 to allow for the concrete pavement to meet the strength criteria required to open the work area to traffic during peak hour lane closure restrictions and not force the base patching work in those segments to be completed during weekend hours. | Fred Schunke | 8 | 2022-01-04 19:42 | 2022-01-06 09:44
20220111 | 20220111002 | 2 | FLY ASH IN SHES CONCRETE | ASP-6 requires the use of fly ash in all concrete pavements. Using fly ash in an SHES concrete during the short work windows on this project will not work. The fly ash will slow the curing time and will not allow the pavement to gain the specified strength required to open to traffic during the short closure schedule. Please allow the use of SHES concrete without fly ash on this project. | ASP-6 is required in all state and federally funded contracts. Use of SHES concrete without fly ash would require approval from the department. | Fred Schunke | 9 | 2022-01-04 19:47 | 2022-01-06 09:47
20220111 | 20220111002 | 2 | Will the Department allow the use of SHES concrete without Fly ash on this project? | Fly Ash is a retardant. It slows the curing process down. Using it in the SHES concrete will slow the strength process down and the concrete will not gain the specified required strength to open to traffic in the closure windows on this project. This project will not be buildable with Fly ash in the SHES concrete as the special provisions require. | Follow the language in the specification. Supplementary cementitious materials will be required for all concrete mixes, including HES and SHES mixes. | Fred Schunke | 10 | 2022-01-06 11:03 | 2022-01-07 11:28
20220111 | 20220111002 | 2 | CTH ID Interim Completion | CTH ID has an interim completion of 28 calendar days. Under the description is states NB ID is to be closed for 28 days but can not be re-opened until NB & SB work are completed. Is the SB work to take place prior to the 28 days? B-13-303 staging plans appear to show NB as stage 1 and SB after in stage 2. 28 days is unrealistic to complete all the work on the 303 structure in both stages. Please clarify. |  |  | 11 | 2022-01-07 10:14
20220111 | 20220111002 | 2 | Withholding of Waiver For Flyash Use in SHES Mixes. | WisDOT in question 10 has made it clear there will be no waiver for not using an SCM in SHES mixes just now being required under revised specifications required for SHES Base Patching. Flyash is the only SCM that realistically will be available. Rapid setting mixes include a number of rapid setting chemicals to excellerate set time. Some of these chemicals are not compatible with flyash such as the set control admixture that is not compatible with the free lime in flyash. Further, flyash in Southeastern Wisconsin is variable and its reactive properties can be problematic and not set one day and flashset another. Only straight cement mixes should be used and technically straight cement is a much higher controlled product needed to meet the extremely short set times required on the project and work compatibly with available admixtures. |  |  | 12 | 2022-01-08 11:54
20220111 | 20220111004 | 4 | Paving Restrictions after Milling and Excavation | Would there be any consideration of extending the time of paving after milling and excavation to more than 48 hours? Adding time to this or even removing the restriction would help cut down on costs tremendously. | The paving time restriction will be modified to 72 hours via addendum. | Mike Coleman | 1 | 2021-12-30 12:11 | 2022-01-03 14:19
20220111 | 20220111007 | 7 | Asphaltic Surface | Due to scope of work, distressed milling and shoulder widening will have to be done prior to a test strip. In addition, wedging on the north end of the job will also need to be done prior to a test strip. Can an item be added to change this HMA to Asphaltic Surface due to PWL specification? | An addenda will be issued to change the bid item for the shoulder widening binder and asphalt wedging to asphaltic surface. | Fred Schunke | 1 | 2022-01-05 13:57 | 2022-01-06 16:26
20220111 | 20220111010 | 10 | Spec Provision - Other Contracts | It is my understanding the contract 5160-07-70 on STH 35 Mill and Overlay has been pushed back one year. So does this scheduling restriction still apply? If this work can be completed prior to the detour for 5160-07-71 STH 35 Cold-in-place project would that be allowed? Thanks | The paragraph in the prosecution and progress stating to not begin work until the detours have been removed will be removed in an addendum. The Other Contracts article will also be revised. | Fred Schunke | 1 | 2021-12-22 11:14 | 2021-12-23 10:18
20220111 | 20220111012 | 12 | B-25-193 Preboring Quantity | The plans call out preboring to an elevation of 893.50 at the south abutment and 891.50 at the north abutment for a minimum tip elevation. For the south abutment this is +/-20' from the bottom of abutment. For the north abutment this is +/- 21.5' from the bottom of abutment. Based on this, should the plan quantity at the north abutment be 160 LF, and 172 LF at the south abutment? | This will be updated via addendum. | Mike Coleman | 1 | 2021-12-16 09:30 | 2021-12-20 14:12
20220111 | 20220111012 | 12 | QMP HMA Pavement Density Special Provision | The special provisions include QMP HMA Pavement Density, but the HMA table on plan page 64 does not show any pavement with QMP as the density acceptance. Is one of these an error? | After reviewing the question there is a discrepancy between the plan sheet and the specials. There will be an addenda to clarify. | Fred Schunke | 2 | 2022-01-03 08:09 | 2022-01-04 15:46
20220111 | 20220111012 | 12 | DBE Goal | This project includes an 8 percent DBE goal, many of the mill and overlay projects in this area have had 2 - 5 percent goals. Can this goal be lowered to be more in line with other similar projects? |  |  | 3 | 2022-01-03 08:12
20220111 | 20220111013 | 13 | Traffic Queue | The specials state that WB STH 136 traffic is not to queue within "500 feet of the roundabout at the EB USH 12 ramp terminal" - can the Department explain why it has to be this long? This leaves very little room for a queue. | The Stopping Sight Distance for 45 mph is a minimum of 360 feet. For traffic moving through the interchange, distance is needed to have enough time to react to stopped traffic in front of them. We would like to maintain 500 feet from the roundabout to allow traffic time and room to stop. | Mike Coleman | 1 | 2021-12-27 15:10 | 2021-12-29 09:30
20220111 | 20220111013 | 13 | Start Date | Is there a reason this project is to be completed by September 30th? Would the Department consider a later start date than August 22? | HMA paving and pavement supporting operations need to be completed by September 30th to avoid cold weather paving. No, starting by August 22nd allows time to complete all HMA paving and pavement supporting operations by September 30th. | Mike Coleman | 2 | 2021-12-27 15:20 | 2021-12-29 09:31
20220111 | 20220111013 | 13 | Side Roads | Can traffic run on milled side roads? Due to the limited paving and milling quantities, this would not be much longer than 1 day. Otherwise this will add significant expense | No, the intersections are not exempt from the same day mill and pave. | Mike Coleman | 3 | 2021-12-27 15:29 | 2021-12-29 09:32
20220111 | 20220111015 | 15 | 48-Hour Binder Placement | Within the prosecution and progress section with the special provisions it states that the lower lift of HMA pavement needs to be placed within 48 hours. This requirement does not allow enough time to completely mill, place a Binder Test Strip and cover the remaining lower lift in 48 hours. Would the Department consider a 72 hour cover specification? | An addendum will be issued to change to a 72 hour cover specification. | Mike Coleman | 1 | 2021-12-28 14:20 | 2021-12-30 08:06
20220111 | 20220111016 | 16 | File Request | Can a design schedule be provided? Can electronic files or CAD files be provided? Are any soil borings reports available? | The design schedule and soils report can be found at the following location: https://wisdot.box.com/s/9ewn9eca0vlr59o4fpgzeilmzkkxjvv5 or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. This is a local program project and does not have a contractor data packet. | Mike Coleman | 1 | 2021-12-28 09:15 | 2022-01-03 06:50
20220111 | 20220111017 | 17 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/p5sujsxum3ww035sjsufiksefrgpc0mf or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-12-09 09:13 | 2021-12-15 12:27
20220111 | 20220111017 | 17 | SHES Base Patching Quantity. | The SHES Base Patching Quantity of over 30,000syds seems high relative to the amount of Sawing and Dowel Bars? Is this quantity correct or are the Sawing and Dowel Bar quantities understated? Can the location and size of each SHES Base Patch be provided? | Base Patching Concrete SHES quantity is correct. This includes both concrete base areas and concrete base areas that have been cracked & seated. The sawing and dowel bars are only for the areas that are not cracked & seated. The Sawing Concrete quantity is incorrect and an addendum will be prepared to address this. | Fred Schunke | 2 | 2021-12-18 08:18 | 2021-12-23 10:14
20220111 | 20220111017 | 17 | Echelon Paving | In reference to sheet 46 of the plan set for construction details. Is it the departments intent to place two different mix designs for the length of the project on the mainline and shoulder in echelon? | Yes, that is the departments intent. | Fred Schunke | 3 | 2021-12-20 15:26 | 2021-12-23 10:15
20220111 | 20220111017 | 17 | HMA Longitudinal Joint Repair | In reference to the plan set detail on sheet 48 and description in specials on page 96 for item HMA Longitudinal Joint Repair. Is this item only to be done prior to milling and paving of the permanent pavement placement? There are conflicting mix design designations listed for this item. Please confirm correct mix design. | The department anticipates the HMA Longitudinal Joint Repair be completed prior to placement of the surface layer of HMA. The HMA type listed in the special provisions for the HMA longitudinal Joint Repair item is incorrect and an addendum will be prepared to address this. | Fred Schunke | 4 | 2021-12-20 15:36 | 2021-12-23 10:16
20220111 | 20220111017 | 17 | Bridge Approach | I feel the bridge approach quanity is to high.I found 791 sy. | The quantities for items 415.0410 Concrete Pavement Approach Slab and 415.1410 Concrete Pavement Approach Slab HES are listed in the Miscellaneous Quantities table for Concrete Pavement Items. | Mike Coleman | 5 | 2021-12-23 09:07 | 2021-12-29 09:36
20220111 | 20220111017 | 17 | Schedule of Operations - single lane closures | Please define closures and work to be completed under stage 1A and 1B in reference to sheet 11 and 12 of the specials stating long term weekend single lane closures. Stage 1A permits 3 and Stage 1B permits 2. | The work to be completed under stage 1A and 1B is defined in the Prosecution and Progress article. The long term weekend lane closures will be allowed for the replacement of the approach slabs at Moorland Rd. An addendum is being prepared to identify the work restriction hours for the long term weekend lane closure. | Fred Schunke | 6 | 2022-01-03 11:51 | 2022-01-04 15:23
20220111 | 20220111017 | 17 | SHES AND HES CONCRETE | ASP-6 requires the use of fly ash in all concrete mixes. With the short work window on this project the SHES and HES concrete will not meet the required strengths to open to traffic using Fly Ash. Will the Department allow SHES and HES on this project without fly ash? | The response to the question is to follow the language in the specification. Yes, supplementary cementitious material will be required to be used for all concrete mixes, including HES and SHES mixes. | Fred Schunke | 7 | 2022-01-04 19:21 | 2022-01-06 16:15
20220111 | 20220111017 | 17 | Channel Excavation and Medium Riprap placement | During which stage of construction, and under what traffic configuration, is the Channel Excavation (3,303 cy) and Medium Riprap placement (3,093 cy) (I43 SB 59+50 to 74+50) expected to take place? This work is not mentioned on any of the Traffic control sheets nor is it shown on the designers schedule. | The special provisions state that the replacement of the concrete channel with riprap be completed during Stage 1B under the Schedule of Operations section within the Prosecution and Progress article. It is anticipated that this work be completed under a shoulder closure. | Fred Schunke | 8 | 2022-01-06 11:33 | 2022-01-06 16:16
20220111 | 20220111017 | 17 | Will the Department allow SHES and HES concrete on this project without Fly ash | Fly Ash is a retardant. It slows the curing process down. Using it in the SHES concrete will slow the strength process down and the concrete will not gain the specified required strength to open to traffic in the closure windows on this project. This project will not be buildable with Fly ash in the SHES concrete as the special provisions require. I have spoke to all the Redi mix suppliers in Southeast Wisconsin and they have all told me that using Fly ash in the SHES and HES mix will not work. The concrete will not get the required strength to open to traffic within the short time frame this project requires. | Follow the specification language. Supplementary cementitious material will be required for all concrete mixes, including HES and SHES mixes. | Fred Schunke | 9 | 2022-01-06 16:47 | 2022-01-07 11:29
20220111 | 20220111017 | 17 | Slope Restoration adjacent to Channel Work | Significant areas of Topsoil and Restoration will be required after the Channel Excavation and Riprap placement takes place. Very little restoration is shown, on page 87, adjacent to the channel work. Will the topsoil/restoration areas be added to the project or will this topsoil/restoration work be considered incidental to the channel/riprap work? |  |  | 10 | 2022-01-07 11:31
20220111 | 20220111017 | 17 | Remove shoulder rumble strips prior to work | In Waukesha county for the bridge approach work. What pay item covers the remove shoulder rumble strips? |  |  | 11 | 2022-01-07 13:34
20220111 | 20220111017 | 17 | Base Patching Mix | Is the contractor allowed to develop and utilizes mixes per 501.3.2.3 that meets opening requirements per 320.3? |  |  | 12 | 2022-01-07 15:21
20220111 | 20220111017 | 17 | Requirement to use SCMs in SHES Mix. | Can the Department please explain why it is withholding a waiver for the use of SCMs in the SHES Mix and respectfully reconsider it determination? 501.3.2.2.2(3) provides for a waiver of the new SCM requirement. realistically, flyash is the only SCM that will be commercially available. In addition to being a nature retardant with highly variable properties, Flyash is not compatible with some of the chemical admixtures used to rapidly excellerate set times. For example, the set control used in rapid set mixes does not react with the free lime in flyash. Historically only straight cement mixes have been used for rapid setting mixes due to compatibility with excellerating admixtures and the much higher controlled nature of the Portland cement product when early opening is required. |  |  | 13 | 2022-01-08 12:33
20220111 | 20220111017 | 17 | Tie Bar placement | Will it be required to place tie bars in plastic concrete at centerline of base patches with-in the crack and seated areas if patch is going to extend across both lanes? |  |  | 14 | 2022-01-09 09:58
20220111 | 20220111017 | 17 | Sawing and addendum 1 | After reviewing addendum 1, it appears the new sawing quantity has become more confusing. The original amount prior to the addendum appeared to represent the quantity of sawing needed for patches in the non-crack and seated pavement areas accurate to sawing all 4 sides of patches. The addendum listed a revised quantity, but appears to have added the old and revised quantities together providing a new proposal quantity. Was this intended or a typo? The typical existing sections call out the crack and seated pavement area as reinforced. Is this reinforcement mesh? To remove a patch properly all 4 sides need to be sawed, which makes the addendums proposal quantity very low. Sawing all sides lessens risk of the excavation binding and loosening adjacent pavement types. If the department does not intend to pay for sawing at centerline or shoulder edge adjacent to base patch limit, how will department handle and pay for areas that loosen or pull up with patch? Will base patching quantity pay limits extend into these area to fill limits of excavation prior to opening? Is the department going to pay for all sawing with the contract item, or are only some of the crack and seated areas going to be paid with the contract item and other areas incidental? |  |  | 15 | 2022-01-09 10:24
20220111 | 20220111018 | 18 | Pit Run Sources | Article 10 Pit Run, Item 313.0110, requires at least a portion of the pit run to come from a department-approved source and eliminates the use of 3-inch dense-graded base, breaker run, or select crushed material as possible substitute materials. Are there available pit run sources in Door County? Can any of the existing materials excavated for the wall be used as a portion of the pit run backfill? | Yes, there are available pit run sources in Door County. See the Approved Products List. To provide an additional option for the pit run backfill material, an addendum will be issued that will allow native material from the wall excavation to fill in the remaining voids between larger riprap pieces if the contractor chooses to use riprap from the existing emergency breakwater wall as pit run, provided the overall combined mixture meets the requirements of standard spec 313.2(1). | Fred Schunke | 1 | 2022-01-04 15:31 | 2022-01-04 15:33
20220111 | 20220111018 | 18 | Weighing Pit Run | Pit Run item 313.0110 provided in the plan is measured by the ton. The note under the Aggregate quantities table on page 9 of the plan states that riprap from the existing emergency breakwater wall used as pit run will be paid as pit run. How can the existing riprap used for pit run be reasonably measured (weighed) in the field? | An addendum will be issued to replace Pit Run Item 313.0110 (by the ton) with Pit Run Item 313.0115 (by the CY) to help facilitate measurement in the field. | Fred Schunke | 2 | 2022-01-04 15:32 | 2022-01-04 15:33
20220111 | 20220111018 | 18 | instream disturbance | Under Prosecution and Progress - it states minimal instream disturbance from March 1 to June 15th. Does that mean the wall and riprap work will have to be completed by March 1 or is the work being performed in the plan considered "minimal"? | No. The wall and riprap work does not need to be completed prior to March 1, 2022. Work may occur after that date. The work noted in the plan is considered minimal disturbance of Ephraim Creek and the shoreline of Lake Michigan at the current water levels, provided the contractor takes care to minimize disturbance below the existing water line. The agreement with DNR is that the work will be completed above the waterline to the greatest extent practicable. | Fred Schunke | 3 | 2022-01-05 13:54 | 2022-01-06 09:53
20220111 | 20220111023 | 23 | Crack & Damage and Seismograph | Can The department list the specific buildings associated with Kaukauna Utilities that will require surveys & seismographs? | The designated Kaukauna Utility facilities will require crack and damage survey and seismograph. See satellite image: https://wisdot.box.com/s/72w84rn0zdz5i9dut9hnaaoiufeepbsc | Fred Schunke | 1 | 2022-01-04 14:56 | 2022-01-06 16:24
20220111 | 20220111024 | 24 | HMA upper course | In each stage where applicable, the special provisions state â€œcomplete HMAâ€. Could the staging be changed to complete HMA lower course (per stage), and in Stage 4 during the full closure , â€œcomplete project HMA upper course â€ as this will minimize joints and allow the paving contractor to properly pave through the intersection at CTH C. | With Stage 2A, Stage 2B, and Stage 3 without an interim completion date, these stages are only required to be completed by the overall project completion date of October 1st. Therefore, the upper layer of HMA pavement can be applied during Stage 4 if this is desired. The only stage that requires both layers of HMA Pavement to be completed by the end of that stage is Stage 4A. | Mike Coleman | 1 | 2021-12-21 09:10 | 2021-12-28 08:47
20220111 | 20220111024 | 24 | Posting Geotech Report | Please post the geotech report for this project. | The geotech report can be found at the following location: https://wisdot.box.com/s/z0v4cmtediqhg59jnk7kdwemlqp4nkn5 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Fred Schunke | 2 | 2022-01-04 12:41 | 2022-01-04 15:57
20220111 | 20220111024 | 24 | SPV 0060.02 Inlets 5 FT Diameter and SPV 0060.03 Inlets 6 FT Diameter | Other than the special provisons requiring a PE Approval/ Design is there a detail that should have been included in the plan set? | SPV0060.02 and SPV0060.03 special provisions require a stamped manhole design that needs to be approved. Materials need to follow Standard Specification section 611.2 and construction also needs to follow Standard Specification section 611.3. The general layout for inlets can follow standard detail drawing INLETS 3-FT AND 4-FT DIAMETER SDD 8C6-2 but adjusted for the 5â€™ or 6â€™ diameter inlet. No addendum will be issued. Contractor should bid it as is. | Fred Schunke | 3 | 2022-01-06 14:09 | 2022-01-07 14:09
20220111 | 20220111026 | 26 | PWL Density | The 4HT lower layer, of the mill and overlay portion on the mainline is calling out PWL Density, how do test for PWL density and or establish correction factors on a variable thickness layer of 1.75''-2.25''? | An addendum will be issued to adjust the table (on page 32) and the appropriate bid items to address this issue. | Jill Fehrman | 1 | 2022-01-04 14:33 | 2022-01-05 16:33
20220111 | 20220111026 | 26 | PWL mixture use table | Mill and Overlay lower layer on the PWL Mixture use Table includes the 4' RT shoulder, it also calls out PWL density, on sheet 5 it shows the layer thickness on the edge of pavement being 1.5" which is thinner than the minimum lift thickness in the 460 spec for a 12.5mm mix | An addendum will be issued to adjust the table (on page 32) and the appropriate bid items to address this issue. | Jill Fehrman | 2 | 2022-01-04 14:50 | 2022-01-05 16:35
20220111 | 20220111026 | 26 | Ramp work | Is there any planned work between the Gore and the ramp taper. For example sheet 5 shows the ramp mill and overlay limits for the "DC" starting at sta. 108+00 and ending at sta 118+08, it appears that sta 108+00 is at the gore, and the area from the Gore to the South is roughly 1200' to where the ramp taper starts, is this area not getting milled or paved? | The entire taper south of Sta. 108, including the shoulder adjacent to the taper, is intended to be paved using the ramp mix, 4 HT 58-28 H. | Jill Fehrman | 3 | 2022-01-04 14:55 | 2022-01-05 16:47
20220111 | 20220111026 | 26 | traffic control | Typically when crossovers get milled and overlaid both NB/SB inside lanes get closed for safety, it does not show any traffic control for NB closures, do the limits of crossover work extend to edge of NB shoulder? | The region is proposing to address this issue through a contract addendum submittal. | Fred Schunke | 4 | 2022-01-05 10:52 | 2022-01-06 16:11
20220111 | 20220111026 | 26 | SMA surface coat | Would the Department entertain paving the surface SMA layer after both Driving and Passing lanes are bindered, this will create a higher quality centerline joint. And by doing this we would also ask to eliminate the temp paint on the surface coat, removal of temp paint on a SMA surface would create a scar in the wheel path. | WisDOT will consider this proposal. Approval will be based on evaluation of the contractors proposed schedule of operations. | Fred Schunke | 5 | 2022-01-05 12:22 | 2022-01-06 16:12
20220111 | 20220111027 | 27 | Culver Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? |  |  | 1 | 2022-01-04 11:39
20220111 | 20220111028 | 28 | 72 hours for traffic on milled surface, change requested. RE: Special Provisions Articles 3 & 4 | Due to scope of work, i.e. PWL paving, lower layer shoulder widening in various areas, etc. can the 72 hours allowed for traffic on a milled surface be changed to 96 hours, and eliminate the language â€œby the end of the work weekâ€? This will allow the contractor to be more efficient. | An addendum will be submitted eliminating the â€œby the end of the work weekâ€ language and revising the 72 hours allowed for traffic on a milled surface to 96 hours. | Fred Schunke | 1 | 2022-01-05 11:30 | 2022-01-06 16:13
20220111 | 20220111029 | 29 | Covering Bottom of Box with Salvaged Streambed Material | Sheet 47 of the plans includes a note that the bottom of the box culvert is to be covered with 12" of salvaged streambed material. Where should this cost be included in the bid? Is it incidental to any specific item? | Covering the bottom of the box culvert with 12 inches of salvaged stream bed material is incidental to the bid item 206.2000 Excavation for Structures Culverts (structure) 01. B-58-0119. An addendum will be issued to add a note to the plans for clarification. | Fred Schunke | 1 | 2022-01-05 13:16 | 2022-01-06 16:18
20220111 | 20220111031 | 31 | Schedule | Hi, Can a design schedule please be provided? We have concerns that given (two) underwater pier removals and removing a multi-span slab structure, 10 more working days would be very helpful to perform a neat, clean removal of the existing structure. Additionally, the turbidity barrier detail covers the toe of the riprap, but no erosion control detail is provided for around the existing pier. given the water velocity, turbidity barrier will likely be ineffective in providing waterway protection during existing pier removal. We believe a cofferdam item should be added to make sure the Department's environmental concerns be properly addressed. | The design schedule can be found at the following location: https://wisdot.box.com/s/szm9sd6v6w2saejdsyx424cpqy6wwick or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-12-15 09:33 | 2021-12-16 06:16
20220111 | 20220111031 | 31 | HMA Pavement | The project has 156 total tons of HMA has pay items for 3MT, 4MT, and Incentive Density. Would the Department consider combining and changing this to Asphaltic Surface? | Please bid according to the plan. | Mike Coleman | 2 | 2021-12-17 10:18 | 2021-12-21 10:49
20220111 | 20220111033 | 33 | Weekend and Special Event Restrictions | The proposal calls for through traffic lanes to be paved by the end of the work week and also prohibits a milled surface during Special Events, which includes weekend ball tournaments throughout June and July. Will the department consider allowing a milled surface over the weekend to accommodate continuous construction activities, and therefore, eliminate additional mobilizations/phases to complete the work? | The milled surface restriction will be modified by addendum. The change will restrict the milled surface exposure to 72-hours, excluding weather delays, and will include prohibiting a milled surface during holiday and special event periods. Other than holidays and special events, a milled surface will be allowed on weekends. | Jill Fehrman | 1 | 2021-12-30 10:08 | 2022-01-05 16:58
20220111 | 20220111033 | 33 | HMA Pavement 3 MT 58-28S Pay Item | Will the department consider changing the HMA Pavement 3 MT 58-28S item to Asphaltic Surface with a note requiring that this material is a 3 MT 58-28S? Total quantity is 175 tons and consists of RR Xing approach patching, curb and gutter patching, and utility patching, all of which will be completed over multiple days. | An addendum will be issued changing the HMA 3 MT 58-28 S designated for patching manhole and inlet removal and salvage areas, curb and gutter repair and called out in the typical sections for the lower layer of the full depth pavement replacement at the railroad crossing approaches to Asphaltic Surface items utilizing a MT mix. | Fred Schunke | 2 | 2022-01-03 14:37 | 2022-01-04 16:13
20220111 | 20220111033 | 33 | Railroad Crossing Replacement | The proposal states that the contractor shall coordinate with the railroad and schedule contract work in conjunction with the schedule for the railroad crossing replacement. Does CN Railroad have a proposed timeframe as to when this crossing replacement will be scheduled and how long will this work take to complete? | To allow flexibility and a mutually beneficial construction schedule, the department and Wisconsin Central Ltd (CN) did not negotiate a specific timeframe for replacement of the crossing surfaces. It is the departmentâ€™s intent the contractor will begin coordination with CN, Domtar and the department as early as is reasonable after contract execution to develop a construction schedule acceptable to all parties and meeting the provisions of the contract. All railroad crossing surface replacement and contractor placed concrete pavement adjacent to the new crossing surfaces is anticipated to be completed in three to four weeks within the 45 Working Days allowed. | Jill Fehrman | 3 | 2022-01-03 17:03 | 2022-01-05 16:49
20220111 | 20220111034 | 34 | Why is Article 14 included in the Special Provisions? | Article 14 of the Special Provisions indicates that asphaltic mixture furnished under the Asphaltic Surface bid item must meet the requirement for 4MT58-28S, or greater, though the Asphaltic Surface bid item is not used in this proposal. Asphaltic mixture will be supplied under items 460.6224, 465.0120, and 465.0125, for HMA Pavement 4MT 58-28 S, Asphaltic Surface Driveways and Field Entrances, and Asphaltic Surface Temporary, respectively. Can the department explain Article 14 is included in the Special Provisions, and if the intent is to require asphaltic mixture meeting the requirements of a type 4MT58-28S for the driveways and field entrances or temporary surfaces? Those items should allow the contractor to choose the mix for use. | With the small quantity required on the project it makes more sense to bid this work as bid item 465.0105 â€“ Asphaltic Surface with article 14 included in the special provision. I will prepare an addendum to switch bid item 460.6224 â€“ HMA Pavement 4 MT 58-28 S to bid item 465.0105 â€“ Asphaltic Surface. | Fred Schunke | 1 | 2022-01-03 11:30 | 2022-01-04 15:20
20220111 | 20220111035 | 35 | Asphalt Flume ? | On sheet 28, there is a note referring to â€˜constructing an asphalt flumeâ€™, there is no bid item for this. Will a item be added for these? | Sheet 28 the note should have stated Construct Concrete Surface Drain *See SDD â€˜Concrete Surface Drains, Flume Type at Structureâ€™ For More Detail. | Fred Schunke | 1 | 2021-12-21 10:48 | 2021-12-22 13:47
20220111 | 20220111035 | 35 | Boat Traffic | Spec says to maintain boat traffic at all times (Special Provision #4) except for setting falsework and pouring the bridge deck. Once the falsework is set there will be approximately 2'-3' of clearance from the water to the bottom of the falsework. Is this an acceptable amount for clearance, or does WisDOT intend for contractors to specialty form this structure in a way that increases clearance for boat traffic? | It is anticipated that the falsework required to place the new bridge deck will reduce the vertical clearance during construction and will be acceptable. | Jill Fehrman | 2 | 2022-01-04 10:34 | 2022-01-05 16:29
20220111 | 20220111035 | 35 | Airport Operating Restriction | Concerning special provision item 12, it lists the maximum height for the temporary crane at 50 feet AGL of 813 feet AMSL. This seems rather restrictive for the work to be preformed such as driving piling. Is this in error and meant to be 150 feet AGL or will the contractor need to become innovative? If we need to use innovation, what will the department accept? |  |  | 3 | 2022-01-06 11:45
20220111 | 20220111039 | 39 | Joint replacement rebar detail | The bars detailed for the joint replacements on B-3-15/17/19/25/31/38, mainly the S502 and S510 bars are shown to be full length for each stage of the joint. The full length bars make them impossible to install as you need to feed these in underneath the joint that has already been installed. Typically these are detailed to be a max length of approximately 8' and then lapped to allow for installation. | Our structural engineer believes these are possible to install. The contractor will be allowed to install bars at the shorter length and overlap them as an alternative. | Fred Schunke | 1 | 2021-12-27 08:48 | 2022-01-05 09:27
20220111 | 20220111039 | 39 | Railing Tubular Type H | Concerning the new Type H rail to be installed on B-3-21 and B-3-23, it appears that this rail on both structures has already been removed and the anchors cut off flush. Is this correct and in that case will all new adhesive anchors be required to install the rail, hopefully offset from the locations of the existing bolt clusters? | Railing not be required to be installed â€“ and will be removed from the plans through an addendum. | Fred Schunke | 2 | 2021-12-27 08:55 | 2022-01-06 09:40
20220111 | 20220111039 | 39 | Line Item 0158- Railing Tubular Type H | The bid item of 872 feet of Aluminum Type H Railing has issues with material availability. Currently, we are experiencing a schedule of 15 weeks for tooling and 35 weeks for manufacturing. Thus a 50 Week lead time. We suggest a galvanized steel alternate that had been designed by Wisc. D.O.T. on previous projects. | Railing was removed from the project with Addendum #1. | Mike Coleman | 4 | 2021-12-28 08:56 | 2022-01-10 09:04
20220111 | 20220111039 | 39 | Barrier System Grading Shaping Finishing | Please verify that the common excavation and borrow excavation are paid separately from the Barrier System Grading Shaping Finishing item. If that is the case, please explain what is being cut under the common excavation item as the cross sections do not show it very clearly. | Bid item to remain in contract and be bid as it is. Quantity is in place at barrier/inlet locations to facilitate any differences in field conditions outside of the standard grading, shaping , finishing at sites. | Jill Fehrman | 5 | 2021-12-29 10:25 | 2022-01-05 17:02
20220111 | 20220111039 | 39 | Prosecution and Progress | Under Prosecution and Progress it states: Regarding paving, temporary pavement marking and same day pavement marking operations: The center joint of each layer of pavement must match the existing centerline of the highway. Temporary centerline pavement marking must be withing 6â€ of the exiting centerline of the highway. In constructing the surface layer of pavement work on each side of the centerline must be match up at the end of each day, so they permanent same day centerline pavement marking can be applied. It does not appear this paragraph should apply to this project since this is a 4 lane divided highway? We will be working in one lane at a time while traffic is in the other lane? Was there a specific intent or could we get clarification on what this is for? | This was addressed and removed in Addendum # 1. | Mike Coleman | 6 | 2021-12-29 14:21 | 2022-01-10 09:01
20220111 | 20220111039 | 39 | Lane Closure Length Restriction | Under the Traffic Section it states: One lane of US 53 may be closed for construction for up to 5 miles at one time to facilitate construction. The total net length of the project is 16.764 miles. Ideally for scheduling and reducing costs we want close the entire length of the project, however we understand that may not be desirable. 1 â€“ Could we close half of the project at a time? 8.5 miles +/- 2 â€“ Could we close a third of the project at a time? 5.6 miles +/- If we stick to the 5 mile limit that results in a 4th closure required to cover 1.764 miles. 3 â€“ If we are limited to closing no more than a third or 5 miles can we have a closure, then an open gap and then another closure? 5.6 miles one lane, 5.6 miles open, 5.6 miles one lane again 4 â€“ There are 8 bridges requiring work on the project. Could a traffic control plan be developed that allows us to work on all 8 bridges at the same time? Cure time alone adds up if we must wait until we can move to the next structure. | 1 - No, full length or half length closure is not a preferred option. 2 - Yes, project can be closed, and worked in thirds. 3 - Yes, but maintain a 2-mile minimum separation between work zones. 4 - Yes, the project can be split into 3 work zones, allowing the structures to all be worked on at the same time, while maintaining the minimum 2 mile separation between. | Jill Fehrman | 7 | 2021-12-29 15:49 | 2022-01-05 16:24
20220111 | 20220111039 | 39 | Test Strips | There are HMA Test Strip items for volumetrics and density for the SMA pavement, but it appears we are missing the HMA Percent Within Limits (PWL) Test Strip Volumetrics and Density items for the 5MT? | An addendum will be issued to add the items. | Mike Coleman | 8 | 2021-12-29 16:08 | 2022-01-04 06:59
20220111 | 20220111039 | 39 | Single Lane Closures During Holiday Restrictions | Per the Special Provisions it states no Single Lane Closures allowed during Holiday Restrictions. With The three holidays, there is not enough time to do both stages of bridge work on the structures as the time between is 1 month and two months. Looking at the Barrier Block Delivered and installed it does not appear that the intent is to remove the block and reinstall the block. Does single lane closure restriction pertain to the structure work or is the barrier block allowed to remain up during the holiday restrictions? | Single Lane closures are allowed during Holiday Work restrictions. This can be removed in the Addendum. | Fred Schunke | 9 | 2022-01-03 15:54 | 2022-01-05 09:37
20220111 | 20220111039 | 39 | Barrier Block Location on Overlay Bridges | Per the plan sheets it shows the barrier block tight to the centerline construction joint on the overlays. Can this be moved over 1' to give 15' in Stage 2 for traffic to face of block? The 1' past centerline is required to run the bidwell machine on for the deck pour. Without it this section could not be done with the machine and would leave an inferior product. | The barrier can be moved to accommodate the bidwell machine during the day that the overlay pour is going to occur. This would be incidental to the barrier item. Coordination with construction staff will need to occur in order to provide sufficient warning for Freight and OSOW permit unit to send out notifications to wind turbine hauling/OSOW. | Fred Schunke | 10 | 2022-01-04 15:57 | 2022-01-06 16:07
20220111 | 20220111039 | 39 | Removing Old Structure | There is a removing old structure item for B-3-15 for the wingtops but there is not similar item for bridges B-3-21,23,25,31, and 38. The plan does not say that the removals are incidental to any item. Will there be removing old structure items added for these structures for these removals? | This was addressed in Addendum # 1. Removing Structures item was added for B-3-21,23,25,31, and 38. | Mike Coleman | 11 | 2022-01-05 08:30 | 2022-01-10 09:02
20220111 | 20220111039 | 39 | Removing Asphaltic Longitudinal Notched Wedge Joint Milling | The staging requires that the median lane gets surface lift of HMA prior to the outside lane. All available mills are configured to flush cut on the right with the flow of traffic (this means that the drum of the machine is offset to the right is not centered in the frame of the mill). There are three options to complete the removal of the temporary longitudinal notched wedge joint: 1. Allow a staging change to surface the outside lane first. This will allow the milling machine to remove the temporary centerline wedge joint with the flow of traffic during a median lane closure without overhanging centerline and impeding traffic flow in the open lane. 2. Run the milling machine against traffic with an outside lane closure. 3. Run the mill with the flow of traffic with an outside lane closure. This will require that the milling machine hangs approximately 3â€™ over the centerline. Which of these methods will be acceptable? |  |  | 12 | 2022-01-07 13:28
20220111 | 20220111039 | 39 | Structure B-3-19 Structure Loading Temporary Deck Support | What are the unfactored dead and live load demands for the temporary support on the deck overhang for stage 1? |  |  | 13 | 2022-01-07 15:46
20220111 | 20220111039 | 39 | Structure B-3-19 Structure Loading Temporary Deck Support | Please provide the unfactored and factored dead, live, and impact load demands on the contractor designed temporary support for the existing deck during stage 1. Also, please identify the location the loads are assumed to act. |  |  | 14 | 2022-01-07 15:56
20220111 | 20220111039 | 39 | B-3-19 Deck Support Detail | Given there is no reduced loading in the plans or specifications, the length of these plate girder spans, and the resultant load on any support of the 180 kip max vehicle rating listed on HSI, the only method to adequately support this staged overhang to the requirements of WisDOT Bridge Manual is to move deck joint to the centerline of girder 3. Is there any reason this was not done, and is there any other preliminary concept which would be acceptable to WisDOT? |  |  | 15 | 2022-01-10 07:35
20220111 | 20220111040 | 40 | Schedule and Timing | With the special provision as written this project may take additional days beyond 40 due to several factors. With having the 72 Hours of milled surface and full lane width provision the project cannot be done as a mill and fill. Having to have it covered by the weekend means the mill has to leave every Thursday and Friday to catch up the paving operation. If the paving operation is caught up by the weekend there is no paving ready for Monday. There will be several additional mobilizations for the paving group and the mill because of this. Can you add an additional 7 days to complete the project? Is there any changes to the special provision that could make the production of the project flow better? | The weekend work restriction will be revised via addendum. | Fred Schunke | 1 | 2021-12-22 15:04 | 2022-01-05 09:40
20220111 | 20220111040 | 40 | Temporary Pavement Markings | Good morning, on plan sheet 7, the notes to the right of the temporary paint and temporary epoxy items appear to be reversed as temporary paint is typically applied to the milled surface and temporary epoxy would typically be applied to the upper layer prior to rumbles. In addition, with the milled surface allowed for 72 hours, it appears there should be additional temporary paint quantities to cover the lower layer. Will there be an addendum to address these matters? Thank you. | The â€œremarks sectionâ€ and temp paint quantity on Sheet 27 will be updated via addendum. | Fred Schunke | 2 | 2021-12-29 07:05 | 2022-01-05 09:41
20220111 | 20220111041 | 41 | CIR | 1. On past projects the Northwest Region has not Cold In Placed Recycled turn lanes. The typical finished section on sheet 11 of the plans indicates that 10 turn lanes are to be recycled with the stationing defined. Sheet No. 15 in the plans indicates at the same turn lanes are to be milled and not cold in place recycled. Please advise which turn lanes are to be CIR and which are to be milled and overlaid. | This will be addressed in addendum with along with all questions. | Fred Schunke | 3 | 2021-12-15 15:21 | 2021-12-22 13:52
20220111 | 20220111041 | 41 | CIR | 2. On past projects the Northwest region has continued to cold in place through all intersections at the same width as the mainline (in this case 17â€™). On sheets 14 and 15 of the plan the CIR is reduced from 17â€™ in width per side to 12â€™. Could the WIDOT consider allowing all intersections to be Cold In Place Recycled at 17â€™ from centerline? Keeping the width of the paving (17â€™) constant throughout the project will improve ride quality and reduce balancing problems with the CIR? | This will be addressed in addendum with along with all questions. | Fred Schunke | 4 | 2021-12-15 15:24 | 2021-12-22 13:54
20220111 | 20220111041 | 41 | CIR | 3. Sheet 15 and 16 of the plans indicate that there is no milling to be performed on the mainline of USH12 at the intersections. Plans indicate from the outside edge of the CIR a transition is milled from 0â€ to 2.75â€ and then milling is completed at 2.75â€ to the termini of the side road. Is there any concern about the cross slope getting to steep going through and back into the intersection? Perhaps at least some the existing asphalt (1â€ to 2â€) could be milled off USH12 into and out of the intersections. Another option could include paving into the gutter at the intersections. Both options would reduce the severity of the elevation/slope change in the intersection. | An addendum has been submitted that will answer the questions. | Fred Schunke | 5 | 2021-12-15 15:35 | 2021-12-23 10:12
20220111 | 20220111041 | 41 | Test Strip Density 460.0110.S | The quantities only call for 3 density test strips should there be 4 with the different thickness of HMA over the millings and CIR per lift? |  |  | 7 | 2022-01-05 15:44
20220111 | 20220111041 | 41 | box culvert cleaning | Is it required on box culvert cleanings to be de-watered prior to cleaning, or can it be completed hydraulically? |  |  | 8 | 2022-01-07 14:48
20220111 | 20220111045 | 45 | Milling/Paving Restrictions | The milling depth on this project is 1.5 inches, the lower layer pavement lift is 1.25 inches and the upper layer pavement lift is 1.5 inches. Can we extend or remove the 72 hour requirment to cover the milled surface due to the minimal milling depth? Why is there a restriction on how long traffic can run on the lower HMA layer? Should we expect issues with the existing road structure? | Question 1 The requirement to cover milled surfaces has been reviewed and will remain as part of the contract. The Pavement Condition Indices (PCI) for the existing pavement structure is low, the pavement is showing signs of significant deterioration and there is only 8-in of base under the existing 4-in to 4.5-in pavement. Milling 1.5-inches of asphalt will leave a 2.5-in. to 3-in. of the existing pavement weaking the pavement structure further. It is anticipated that the pavement structure would not be able to accommodate the through traffic and construction traffic for longer durations of time without deterioration. Question 2 We will remove the requirement to pave surface within 15 days of the lower layer being paved. (Addenda to follow.) | Mike Coleman | 1 | 2021-12-29 14:03 | 2022-01-03 14:22
20220111 | 20220111045 | 45 | Centerline Match | Under Prosecution and Progress it states that the Centerline elevations of both lanes shall match at the end of each day for the base aggregate, milling and paving operations. For milling/paving if the lane is milled and paved same day can the 1/4" difference be left with proper signage? With a 1.25" lower layer why does the lane need to match at the end of every day? Can we leave a 1.25" difference with proper signage? With a 1.5" upper layer why does the lane need to match at the end of every day? Can we leave a 1.5" difference with proper signage? | We will remove the requirement to match at the end of each day. Standard specifications will govern regarding lane drop offs. (Addenda to follow) | Mike Coleman | 2 | 2021-12-29 14:13 | 2022-01-03 14:23
20220111 | 20220111046 | 46 | Concrete Anchors | The plan does not call out any concrete anchors for the joint replacement areas. Will these be added? |  |  | 1 | 2022-01-06 08:24
20220111 | 20220111048 | 48 | Geotechnical Report | Can the geotechnical report for the project please be provided? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/nvh3f5bs2v76tq97xmgxpqchnq3n8a3p or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-01-04 11:48 | 2022-01-05 11:14
20220111 | 20220111048 | 48 | 404 Permit | Can the 404 permit please be provided. | The 404 Permit is at the following link along with the Memorandum of Agreement (MOA) for the project. The MOA is being provided because it is referenced in the 404 permit and it was attached to the issuance of the 404 permit. https://wisdot.box.com/s/nvh3f5bs2v76tq97xmgxpqchnq3n8a3p | Fred Schunke | 2 | 2022-01-07 08:36 | 2022-01-07 11:23
20220111 | 20220111049 | 49 | Pay Item #0178 - Water Main Fittings | What chart is being used for the fitting weights - C110 or C153? | For calculating the fitting weights, we used the C110 chart. | Fred Schunke | 1 | 2022-01-04 14:52 | 2022-01-06 16:17
20220111 | 20220111049 | 49 | Addendum posted on January 3rd | On the DOT Website there was an addendum for DOT49 posted. Will this file be posted for download on bid express? | No, the schedule of items was not updated. Therefore Bid Express is not updated, and the addendum will only be available on the HCCI Webpage. | Fred Schunke | 2 | 2022-01-06 15:21 | 2022-01-06 15:56