## qandasearchletting_results
Date: | 2022-02-07
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20220208 | 20220208002 | 2 | S-29-0011 & S-29-0012 Structure Plans | The plans for structures S-29-0011 & S-29-0012 appear to be missing. Can these be provided? | An addendum will be issued to add the missing sheets. | Mike Coleman | 1 | 2022-01-13 16:00 | 2022-01-19 14:31
20220208 | 20220208002 | 2 | Approach Slabs | Are the approach slabs 26'-0" wide at structure B-29-155 West Bound side sheet 43. Sheet 45 Structure B-29-153 West bound side.Are the approach slabs 26'-0" sheet 45.I beileve the shoulders are asphaltic but the arrows points to them as Approach slab on the drawing.Please clarify. | The approach slab is 52â€™ wide on the north side of the B-29-155 structure. The approach slab is 56â€™ wide on the north side of B-29-153. The asphalt shoulder would begin after the surface drains. | Mike Coleman | 2 | 2022-01-14 13:55 | 2022-01-24 06:54
20220208 | 20220208002 | 2 | 12.5 Inch HES | Could you give more clarification on locations of where the HES 12.5 inch is located on project? | The 12.5 inch HES concrete was meant to be used in the pavement gaps for the ramps or the WB transitions, depending on the timing of the work. If the standard 12.5 concrete item works in the schedule then no high early strength concrete is needed. | Mike Coleman | 3 | 2022-01-20 09:26 | 2022-01-24 12:04
20220208 | 20220208002 | 2 | Bid Item #164 4 SMA & Bid Item #166 Material Transfer Device | Bid Item #164 4 SMA 58-28 V and Bid Item #166 Material Transfer device has a such small tonnage and only 400â€™ feet of paving that mix type. The price on Bid Item #164 4 SMA 58-28 V will be extremely high because of we have to make test batches to ensure a quality product before it comes onto the project. Also, to establish a rolling pattern to achieve density for SMA we would need a longer area to pave. We suggest using a 4HT 58-28H for both lifts instead of having two different mix types in that 400â€™ section. If Bid Item #1644 4 SMA is eliminated the Material Transfer Vehicle would be eliminated as well. | Articles 34 and 35 will be removed. The 4 SMA 58-28 V will be changed to 4 HT 58-28 H in an addendum. | Mike Coleman | 4 | 2022-01-21 13:59 | 2022-01-25 07:48
20220208 | 20220208002 | 2 | Bid Item #146 HMA Pavement Test and Bid Item #148 HMA Test Strip Density | Bid Item #146 HMA Pavement Test Strips Volumetrics and Bid Item #148 HMA Test Strip Density should be eliminated because there isnâ€™t enough footage on the project to establish a rolling pattern or enough mix for a representative test section. | Articles 34 and 35 will be removed. The 4 SMA 58-28 V will be changed to 4 HT 58-28 H in an addendum. | Mike Coleman | 5 | 2022-01-21 14:00 | 2022-01-25 07:48
20220208 | 20220208002 | 2 | Bid Item #172 Asphaltic Curb | â€“ Bid Item #172 Asphaltic Curb, when looking at the plan it has 66 LF of Asphaltic Curb that runs from the new concrete curb and gutter to the flume. Wouldnâ€™t it be a beneficial to run the concrete curb and gutter further, then tie the flume into the end of the curb and gutter instead of the asphaltic curb? This would eliminate maintenance to the asphaltic curb and gutter after snow removal if it is damaged. | Per the asphaltic flume detail in the SDDâ€™s asphaltic curb is required. The locations are shown in the curb and gutter mqâ€™s. | Mike Coleman | 6 | 2022-01-21 14:01 | 2022-01-24 12:09
20220208 | 20220208002 | 2 | Bid Item #760 Incentive IRI Ride | Bid Item #760 Incentive IRI Ride â€“ is this just the concrete roadway or is some that going to be tied to the asphalt on STH 82? If some is tied to the STH 82 asphalt pavement it should be eliminated because with how the stages are to be paved there wonâ€™t be enough consistency. | This item only includes the concrete pavement on STH 82. | Mike Coleman | 7 | 2022-01-21 14:02 | 2022-01-24 12:05
20220208 | 20220208002 | 2 | Night Shift paving | Night Shift paving - Looking through the special provisions and the plan set is the temporary paving in stage 2A-2D the only paving that must be done at night for the whole project? Looking through the special provisions and the plan Stage 3A-3C & Stage 4 paving are all intended to be paved during the day. Is that correct? | It would depend on the contractorâ€™s operations. There could be some connections needed in stages 3 & 4 that would require night work. Any work that requires a lane closure on the Interstate will need to be completed at night. Refer to article 6 Traffic. | Jill Fehrman | 8 | 2022-01-21 14:02 | 2022-01-26 06:35
20220208 | 20220208002 | 2 | Bid Item #154 HMA Pavement 3MT 58-28 S & Bid Item #156 HMA Pavement 4MT 58-28 S | Bid Item #154 HMA Pavement 3MT 58-28 S & Bid Item #156 HMA Pavement 4MT 58-28 S shouldnâ€™t these items fall underneath asphaltic surface special because both items are such a small quantity? Mix testing and density testing shouldnâ€™t apply. | An addendum will be issued to change the mix type to 4 LT 58-28 S. | Fred Schunke | 9 | 2022-01-21 14:03 | 2022-01-26 16:05
20220208 | 20220208002 | 2 | Temporary Bridge construction | Can the department provide a better description of the temp bridge(s) {especially the lemonweir river structure}. Or provide a link to the approved shop drawings? | The temporary structure plans can be found at the following location: https://wisdot.box.com/s/fsr4rqnusg7bjv7emwyzmfg0zs4tn5is or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 10 | 2022-01-24 10:03 | 2022-01-24 16:21
20220208 | 20220208002 | 2 | Soil Borings | Can the soil borings be provided? | The soil borings can be found at the following location: https://wisdot.box.com/s/fsr4rqnusg7bjv7emwyzmfg0zs4tn5is or access form the February bid Letting page. | Jill Fehrman | 11 | 2022-01-24 12:40 | 2022-01-26 06:54
20220208 | 20220208002 | 2 | HTCB Standard Detail Drawings | The standard drawings for the HTCB have been updated this year and seem to be moving away from manufacturers recommendation. Do the details for the line post footings require a minimum 8 rebar rings with 8 vertical bars tied inside a 4' depth footing? With a 12" diameter footing, the outside diameter of the ring will need to be 8" to maintain 2" clearance. The inside diameter of the ring will be close to 7" diameter which doesn't provide a lot of room to tie 8 vertical bars inside the rings. | The new SDD represents the minimum steel reinforcement required in the line post footing. The manufacturer needs to review their design and determine if the minimum reinforcement is adequate for the line post and the soils present. If the minimum reinforcement design is not adequate then the manufacturer will need to add more reinforcement. If the manufacturer needs more room to place steel, they may need to increase the diameter of their footing. | Fred Schunke | 12 | 2022-01-25 09:14 | 2022-01-26 15:43
20220208 | 20220208002 | 2 | Moving Structural Steel Sign Supports | Should there be quantity for pouring new footings and providing new steel stubs at the new locations? Will the existing posts be the correct length for the new locations or will they need to be modified? | Yes, an item will be added for the footings. The existing post lengths do not need to be modified, use the lengths as-is. | Fred Schunke | 13 | 2022-01-25 13:54 | 2022-01-26 16:05
20220208 | 20220208002 | 2 | Select Borrow vs Borrow | Why is Select Borrow used on this project vs the normal borrow item? Most of the fills on this project are located outside the road core (outside the 1:1 slopes). The common excavation is going to be used in the fills first (more than likely under the roadway) which will not meet select borrow but will make a good embankment. The project area is located in an area that has good silty sands that make great embankments which doesn't meet the select borrow spec. The Select Borrow item seems like a waste of money considering the quality of the native soils on the project and where the select borrow is specified (on fills outside the road core). Please consider using the normal standard Borrow Item. | The borrow was reviewed and an addendum will be issued. | Fred Schunke | 14 | 2022-01-26 14:45 | 2022-01-28 14:18
20220208 | 20220208002 | 2 | Earthwork Summary - Its states in the comment section "Utilize Waste Material from Previous Stages" | Sheets 445 - 447 - the Earthwork Summary - Its states in the comment section "Utilize Waste Material from Previous Stages". The schedule on this project is extremely aggressive, so leaving common excavation in a previous stage is not doable per the schedule. So then this material has to be stockpiled somewhere and then haul again. How will this get paid? Traditionally if common excavation is used in another balance/stage, it is paid for as common excavation in the first stage and then paid for in the follow stage as borrow excavation. Why is the project not doing that? | The staging was reviewed with the common and borrow quantities. After review, the borrow quantities will be updated in an addendum. | Fred Schunke | 15 | 2022-01-26 15:22 | 2022-01-28 14:17
20220208 | 20220208002 | 2 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/ugo5wgruk2l8kp184wwox5h32v8g2jiw or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 16 | 2022-01-26 15:25 | 2022-02-02 18:09
20220208 | 20220208002 | 2 | Schedule | Why are there bid items for both RBC and CPM schedules? | Use the CPM schedule item. The RBC item will be removed by addendum | Mike Coleman | 17 | 2022-01-31 09:59 | 2022-02-02 17:48
20220208 | 20220208002 | 2 | Cross Drain Detail - Plan Sheet 27 | What pipes are to follow this Cross Drain Detail? Only Culvert Pipes? Or/and storm sewer also? On IH 90 only? The Ramps also? STH 82? Please clarify which runs of pipe this detail is for. | : The detail will be removed via addendum. | Mike Coleman | 18 | 2022-02-01 14:11 | 2022-02-03 05:27
20220208 | 20220208002 | 2 | Design Conversion Factors used (Tons/CY) | What are the design conversion factors used (tons/cy) for these item of work: Base Aggregate Dense 3/4" and Base Aggregate Dense 1-1/4"? | Per the FDM requirements, Base Aggregate Dense ï¿½-Inch is 2.1 Tons/CY and Base Aggregate Dense 1 ï¿½-Inch is 2.0 Tons/CY. | Fred Schunke | 19 | 2022-02-01 14:14 | 2022-02-03 15:20
20220208 | 20220208002 | 2 | Closures at sth 82 and cth G | Traffic under stage 2 and 3A states STH 82 may be closed 3 nights for demo and 2 nights for beam setting. Please confirm if this is per stage. So 5 nights full closure allowed for stage 2, stage 3A, and 3 nights for stage 4 temp bridge demo. There is no mention of full closures for demo or beam set on CTH G. Are full closures going to be allowed here similar to STH 82 as long as they are not both closed at the same time? | An addendum will be issued to make the requirements more clear. Under stage 2 and 3A, STH 82 will be closed 3 nights and 2 nights for installation of the girders for each bridge. Stage 4 will have 3 nights for removal of the STH 82 temporary bridge and 3 nights for removal of the CTH G temporary bridge. CTH G will have closures to remove the existing WB structure over CTH G. The addendum will have this information. | Fred Schunke | 20 | 2022-02-01 14:20 | 2022-02-04 10:18
20220208 | 20220208002 | 2 | STH 82 Roadway Reconstruction Staging Conflict with B-29-155 WB | Staging Plans show STH 82 roadway work being completed during stage 2 work in conjunction with B-29-154 but do not take into account the work and conflicts that will occur when work on WB/Structure 155 will take place. Is it possible to move the STH 82 reconstruction in the vicinity and under the two bridges from stage 2/3A to another stage in the 2023 construction season after the I94 EB and WB bridges over STH 82 are completed to avoid this conflict? There is also no traffic control plan available for stage 3 work on STH 82 when the pier and adjacent slope paving on the 155 bridge will be constructed? | STH 82 work must be completed in 2022. No work on STH 82 in 2023 will be allowed. When the WB structure is being constructed in the fall of 2022 use the traffic control devices already on STH 82 because STH 82 is still being constructed until Nov. 2022. Use appropriate items and follow the special provisions. | Fred Schunke | 21 | 2022-02-02 13:56 | 2022-02-04 10:17
20220208 | 20220208002 | 2 | Article 12 - 404 Permit | With the late start due to instream disturbance dates resulting in a tight time frame of construction on the Lemonweir River Bridges, multiple crews at multiple substructure units are necessary. In the absence of a 404 permit, the contractor is forced to build this structure in a more linear schedule. Would the department be able to provide a criteria from the USACE in which a temporary access road would be permitted? | The contractor will need to work with DNR and the USACOE to amend the current permit if alternate methods are used. WisDOT will help with coordination efforts but approvals and processes will need to be followed. | Fred Schunke | 22 | 2022-02-02 14:10 | 2022-02-04 10:18
20220208 | 20220208002 | 2 | Article 12 no 404 permit | Article 12 states that there is no 404 permit for this job. Please confirm that the existing piers can be removed and cofferdams and new piers can be constructed at the Lemonweir River structures without a 404 permit. |  |  | 23 | 2022-02-03 15:13
20220208 | 20220208002 | 2 | Cofferdam / Seal below Temp Bridge at Lemonweir | The inside portion of the cofferdams at the Lemonweir bridge structures can not be constructed as shown on the plans due to the existing temporary bridge that will be in conflict (north side at B-29-152 and south side at B-29-153). Please advise if the cofferdam and concrete seal size can be shortened where along the temp bridge to allow for these to be constructed. | It is anticipated that adjustments to cofferdam and seal may be required due to field conditions. | Fred Schunke | 24 | 2022-02-03 15:21 | 2022-02-04 14:16
20220208 | 20220208002 | 2 | Select Borrow - Addendum #2 | It appears Select Borrow was not expanded in Addendum #2 like it was in the original plan. So how is select borrow measured after addendum #2, original position or final position? It appears borrow excavation in measured in its original position because it was expanded, correct? Borrow & Select Borrow should be measured the same way on a project, preferably in its original position. | Select borrow is not part of the mass ordinate and will be measured in final position so no shrinkage factor was applied (per spec & DTSD Plan QA Memo). Borrow is part of the mass ordinate so that was paid in its original position with the expansion factor. | Fred Schunke | 25 | 2022-02-06 19:56 | 2022-02-07 12:24
20220208 | 20220208004 | 4 | 2021 City of Columbus Technical Standards for Sewer and Water Construction | The project special provisions reference the 2021 City of Columbus Technical Standards for Sewer and Water Construction. The technical standards are not on the City of Columbus Wisconsin Website nor in the contractor data package. Can you provide a copy of the 2021 City of Columbus Technical Standards for Sewer and Water Construction? | The 2021 Technical Specifications supplied by the City of Columbus can be found at: https://wisdot.box.com/s/44z0r1h7kv13menf2mvcluiupmver2ms or accessed from the February Bid Letting page. | Jill Fehrman | 1 | 2022-01-21 13:24 | 2022-01-26 08:48
20220208 | 20220208004 | 4 | Geotechnical Data | Please provide any available geotechnical data for the project area. | The geotechnical report can be found at the following location: https://wisdot.box.com/s/44z0r1h7kv13menf2mvcluiupmver2ms or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-01-21 13:24 | 2022-01-24 10:28
20220208 | 20220208005 | 5 | Pavement Markings | Good afternoon, in looking at the pavement marking items, will the agency be adding a regular 4" & 8" epoxy item in case the cold weather marking item is not needed on October? On similar projects, there would be a regular item and a cold weather item in case it is needed. Will an addendum be issued to address this or are we to simply plan on placing cold weather epoxy on this project regardless of the weather? Thank you. | Items 646.1020 Marking Line Epoxy 4-Inch and 646.3020 Marking Line Epoxy 8-Inch will be added into the contract. An addendum will issued. | Mike Coleman | 1 | 2022-01-12 16:07 | 2022-01-24 07:01
20220208 | 20220208005 | 5 | Soil Borings | Can you provide the soil borings for the project? | The geotechnical report can be found at the following location: https://wisdot.box.com/s/hld4sbc1weg6fs60xm6k3psu5rzcdxcq or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-01-17 08:07 | 2022-01-24 07:08
20220208 | 20220208005 | 5 | DESIGN FILES | CAN THE DEPARTMENT PROVIDE THE META DATA AND GEOTECHNICAL REPORT FOR THE PROJECT? |  |  | 3 | 2022-01-18 09:39
20220208 | 20220208005 | 5 | pond liner | looking at sheet 45 in the plan. what covers the liner on the slopes as the diagram only shows 3/4 base on the floor. also do not see a quantity listed in misc sheets for the 3/4 base for the pond. | The pond is a â€œwet pondâ€ meaning that within the limits of the sedimentation basin the slopes will be under water. The detail is correct as shown and as designed. No change required. The quantity of Base Aggregate Dense ï¿½-Inch (ie. 42 Tons) is included in the mainline quantity. No change required. | Mike Coleman | 4 | 2022-01-21 09:59 | 2022-01-24 11:43
20220208 | 20220208005 | 5 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) Min/max cover heights are less than 15 feet for Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPCS? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 5 | 2022-01-21 11:44 | 2022-01-24 15:54
20220208 | 20220208005 | 5 | pond liner | on sheet 45 how far does the base go on the liner? the section only shows the bottom. if so what covers the liner up the sides? also no qty on the misc sheet for 3/4 base. | The base aggregate dense layer is 8â€ thick. The distance up the slope is 0.67â€™ * (2:1) = 1.34â€™. No change required. The pond is a â€œwet pondâ€ meaning that within the limits of the sedimentation basin the slopes will be under water. The detail is correct as shown and as designed. No change required. The quantity of Base Aggregate Dense ï¿½-Inch (ie. 42 Tons) is included in the mainline quantity. No change required. | Mike Coleman | 6 | 2022-01-21 13:21 | 2022-01-24 12:12
20220208 | 20220208005 | 5 | asp-5 | shouldn't this project have asp-5 as all excavation total it is over 100,000 cy? | An addendum will be issued to add ASP-5 | Mike Coleman | 7 | 2022-01-21 13:38 | 2022-01-24 11:36
20220208 | 20220208006 | 6 | Rock Excavation | What is your intention for the final walls on this project? Pre split? | General rock excavation methods are anticipated, no presplitting. | Mike Coleman | 2 | 2022-01-20 12:16 | 2022-01-24 15:46
20220208 | 20220208006 | 6 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 3 | 2022-01-21 11:46 | 2022-01-24 16:03
20220208 | 20220208007 | 7 | Piling Discrepancy | Plan details for the 14" CIP call for 0.375-inch thickness. The bid item for line item 42 shows 0.25-inch thickness. Please clarify what wall thickness is desired for the 14" CIP. | The plan details are correct, the 14" CIP should have a thickness of 0.375-inch. Bid item 550.2146 Piling CIP Concrete 14 x 0.375-Inch shown on plan sheet 27 "Cross Section, General Notes & Quantities" is the correct. On the Estimate For Quatnities (page 6 of plans) for line item 42 the quantity is corrcect, however the wrong bid item was used. An addendum will be issued to change the bid item to the 0.375-Inch thick 14" CIP. | Mike Coleman | 1 | 2022-01-20 13:04 | 2022-01-24 12:13
20220208 | 20220208008 | 8 | DESIGN FILES | CAN THE DEPARTMENT PROVIDE THE META DATA AND GEOTECHNICAL REPORT FOR THE PROJECT? | This is a local program project. There is no requirement for digital delivery. However, the designer is providing the alignment files. The Geotech reports can be found at the following location: https://wisdot.box.com/s/2tno6x8k23xfi88ih4zn51yrviqqj527 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-01-18 09:41 | 2022-01-24 12:00
20220208 | 20220208010 | 10 | Design Schedule | Can the design schedule for this project be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/pcusl4hnj6bqwxnle9frovnp6g3s8vji or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-01-12 16:44 | 2022-01-24 11:16
20220208 | 20220208010 | 10 | TPO and MMA Locations | Is it possible to get some additional clarification on the locations of these applications? For example: 1. Sheet 38 appears to show TPO on structs. B-40-285-23A and 23B but there are no structure drawings indicating exact quantities for these areas 2. Sheet 38 appears to show TPO on Struct B-40-285-25D but the structure drawings shows the quantity as MMA 3. Sheet 38 appears to show MMA on Struct B-40-285-25A and 25B but there are no structure drawings indicating quantities, dimensions, etc. Thanks you | The display on sheet 38 is wrong and will be fixed with addenda #2. Scopes for those structures are as follows. B40-285-23A No work B40-285-23B No work B40-285-25A No work B40-285-25B No work B40-285-25C TPO B40-285-25D MMA | Fred Schunke | 2 | 2022-01-27 09:35 | 2022-02-02 11:50
20220208 | 20220208010 | 10 | Night Hours - Vary between 3 lane and 4 lane sections? | â€˜Night Time Hoursâ€™ between 3 lane segments and 4 lane segments differ. 3 lane segments have 1.5 hours less night time hour duration. Plan sheets 101-104 show traffic down to one through lane regardless of whether the segment is 3 or 4 lanes. Can the night time hours for 3 lane segments be adjusted to match those of the 4 lane segments? | I can see how the language in the spec could be confusing. The intent of the closure hours is: - Up to 7pm: No lane closures allowed - 700-930p: Minimum 3 lanes open - 930-1100p: Minimum 2 lanes open - 1100p-530a: Minimum 1 lane open An addendum will be issued to correct this. | Mike Coleman | 3 | 2022-02-02 10:30 | 2022-02-03 06:05
20220208 | 20220208010 | 10 | Variance between existing and proposed sections | Existing typical section areas shown on sheet 6 illustrate existing HMA depths to vary between 4.75â€-7.5â€. Proposed typical sections on sheet 8 illustrate that new 4.25â€ HMA sits directly on the underlying concrete base. Is the intent to mill out existing HMA all they way down to the concrete base and rebuild with 4.75â€-7.5â€of HMA/SMA or is the intent to carry mill/pave 4â€/4.25â€ through these sections and leave an in between wedge of asphalt? | Mill 4â€ pave 4.25â€ and leave the wedge of asphalt | Mike Coleman | 4 | 2022-02-02 10:34 | 2022-02-02 17:57
20220208 | 20220208010 | 10 | Concrete Surface Repair Quantities | Can you confirm that the concrete surface repair quantities in the bid item match the quantities listed in the bridge plans? | I checked the EOQ value in the plans of 2,322 SF against the values on all the structure plans and confirmed that they total correctly and match. The EOQ value of 2,322 SF also matches the Proposal Schedule of Items. | Mike Coleman | 5 | 2022-02-02 12:44 | 2022-02-03 09:47
20220208 | 20220208010 | 10 | SHES Base Patching. | Can SHES Base Patches be performed in lane one during weekend closures in Stage 1 prior to May 15? | No. This would require placing traffic control in an active lane. | Fred Schunke | 6 | 2022-02-05 12:34 | 2022-02-07 12:22
20220208 | 20220208010 | 10 | Traffic Control Closures | Are the various closures shown in the plans in the Traffic Control Sheets to occur only at night, only for less than 24 hours, or can they remain closed for some other period of time? | With the exception of the â€œweekend single lane closuresâ€ mentioned in the specials. There are no lane closures allowed on the freeway during peak hours. Refer to specials for all lane restrictions, ramp closures and overpass closures. | Fred Schunke | 7 | 2022-02-07 10:29 | 2022-02-07 12:23
20220208 | 20220208012 | 12 | 643.5000 Traffic Control | Hello, the item "643.5000 Traffic Control" has been left off this project; can this be added on? Thanks | The item will be added via addendum. | Mike Coleman | 1 | 2022-01-17 10:22 | 2022-01-19 14:28
20220208 | 20220208012 | 12 | storm sewer temporary cover plates | the special provisions indicate the temporary cover plates for the manhole adjustments will be paid for separately. I do not see and item for the Temp plates | A bid item will be added to the plans, in response to this question. Adding Bid Item 611.9710 via addendum will address the question. | Fred Schunke | 2 | 2022-02-02 10:18 | 2022-02-03 15:03
20220208 | 20220208014 | 14 | Install City-Furnished Signs | Under this bid item, the city is supplying the poles or posts for the contractor to install. What type of pole or post is being provided for installation? | Below is the material we use for our pipe standards and 3' RSP's, please note that the city fabricates the 3' RSP's. Also, included is material for 6" sockets that we use for concrete walk installations. The 3' RSP drawing is at the following location: https://wisdot.box.com/s/15o87zhaso2g7yrohxed6u5k2i8qlcp8 Material Aluminum pipe standard various lengths 7', 9'-6", 11' & 12'-10", noted these are predrilled for different signing configurations - 2.375" OD {A} x 2.067" ID {B} x .154" Wall {C} 2" Sch 40 Pipe 6061-T6 Aluminum, Extruded (https://www.speedymetals.com/pc-4440-8370-2-sch-40-pipe-6061-t6-aluminum-extruded.aspx) 3' RSP (see attachment) - Socket: 2.5" Schedule 40 Black Steel Pipe 6" long Rib: Steel Rib 36", 4 LBS per foot Socket 6" (used in concrete walks) - 2.5" Schedule 40 Black Steel Pipe 6" long | Fred Schunke | 1 | 2022-01-20 10:32 | 2022-02-01 11:36
20220208 | 20220208014 | 14 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 2 | 2022-01-21 11:47 | 2022-01-24 15:56
20220208 | 20220208014 | 14 | Design Files | Can the Department provide all of the meta data files and geotechnical report(s) for this project? | This is a local program project. There is no requirement for digital delivery. FDM 19-10-43 is applicable to projects on the state trunk highway system. The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/15o87zhaso2g7yrohxed6u5k2i8qlcp8 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 3 | 2022-01-21 16:59 | 2022-01-24 12:19
20220208 | 20220208014 | 14 | Can the design schedule be provided? |  | The design schedule is at the following location: https://wisdot.box.com/s/15o87zhaso2g7yrohxed6u5k2i8qlcp8 | Fred Schunke | 4 | 2022-01-30 10:36 | 2022-02-01 09:45
20220208 | 20220208014 | 14 | Can the soil report be provided? |  |  |  | 5 | 2022-01-30 10:36
20220208 | 20220208015 | 15 | Videos of Sewer to be lined | Are there pre-con videos of the sewers to be cipp lined and can we get a copy for review? | The sewer videos can be found at the following location: https://wisdot.box.com/s/d0t6dctvsouyxmjt3k0mj4r8s4l6zhn4 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-01-19 07:32 | 2022-01-24 11:09
20220208 | 20220208015 | 15 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 2 | 2022-01-21 11:48 | 2022-01-24 15:56
20220208 | 20220208015 | 15 | Concrete Driveway Quantity, Water Quantity, Salvaged Unusable Pavement Quantity | In the Bid the Quantities for the Concrete Driveway 7" & 8" the bid estimate is 6060 Square Yards. Is this correct? As take offs are coming out much lower. The Estimated Quantity for Water on the project is 8000 MGAL. This quantity seem excessive for the size of the project. Is there an explanation why so much Water is required, or a bust in the estimated quantity? The salvaged unusable quantity under common excavation is listed at 897 CY. There is currently 16,000 + Square yard of Pavement to be removed on the project. If you figure 8" +/- of pavement removal on the project this roughly equates to 3,000 + Cy of Salvaged / Unusable material. Can an explanation please be provided on how the 897 CY was calculated. | An addendum has been sent to fix the quantities for driveway, water and salvaged/usable material. | Fred Schunke | 6 | 2022-01-31 14:54 | 2022-02-01 11:47
20220208 | 20220208015 | 15 | Granular Backfill - Grade 2 | Granular Backfill Grade 2 is a pay item for backfilling when removing storm sewer pipe. Will this item also be paid for backfill that is required to remove sanitary sewer? | Per the City of Waukesha Standard Specifications payment for sanitary sewer installation includes, full compensation for furnishing and installing sanitary sewer; for excavating; for furnishing and installing bedding, cover, and backfill; for diverting existing flow around the work area; and for testing. Granular backfill shall meet the requirements of Table 39 of Chapter 8.43.7 of the Wisconsin Sewer and Water Specifications. No excavated material will be allowed for reuse as trench backfill, unless otherwise stated in the Special Provisions. | Mike Coleman | 7 | 2022-02-02 11:33 | 2022-02-02 18:59
20220208 | 20220208016 | 16 | Earthwork Table Clarification | Note 8 of the earthwork table states that "cut material may be used as determined by the engineer in the field". Is this statement refering to material used under the roadway foundation as described in section 101.3 of the standard specifications or is inteded for the entire fill section? | If the material is determined suitable by the engineer in the field the cut material can be used under the roadway foundation or in the fill section. | Mike Coleman | 1 | 2022-02-02 09:33 | 2022-02-02 18:00
20220208 | 20220208017 | 17 | Cross Sections don't show excavation below the existing pavement generally. | Can WisDOT please confirm there will no be excavation below the existing pavement most pavement removal locations? | There is a table on Page 6 that indicates the expected area where excavation below the subgrade is anticipated. These areas were identified through recommendations in the soils report and are only shown in this table and the typical section, they are not shown on the actual cross sections. Special Provision #15 also addresses this question and if unsuitable soils are observed during construction, the depth of excavation may be adjusted based on field conditions. EBS either before or after rough grading operations are complete will be paid for at the contract unit price for Excavation Common. | Fred Schunke | 1 | 2022-01-27 18:41 | 2022-02-01 12:09
20220208 | 20220208017 | 17 | Can the Design Schedule be provided? |  | The construction schedule prepared for the project is in the following Box Folder: https://wisdot.box.com/s/4lxqy1ypc06pwoic7a0v294netrp1er2 | Fred Schunke | 2 | 2022-01-30 10:32 | 2022-02-01 12:11
20220208 | 20220208017 | 17 | Can the soils report be provided? |  | There were two soils reports prepared for the project, one for the pavement and a second for the retaining walls, both are in the following Box Folder: https://wisdot.box.com/s/4lxqy1ypc06pwoic7a0v294netrp1er2 | Fred Schunke | 3 | 2022-01-30 10:33 | 2022-02-01 12:08
20220208 | 20220208017 | 17 | R-67-155 Qty's | Please review the Wall Data (plan sheets 4 and 5) for Structural Steel HS qty and foundation drilling qty. There appears to be an error in the table. Based on Top of post, bottom of post and top of footing datum, we are coming up with 67,304 lbs of structural steel and 830 ft of foundation drilling. It appears that the elevations given for bottom of post may be incorrect? | An addendum will be issued to address this. | Mike Coleman | 4 | 2022-02-02 18:11 | 2022-02-03 10:50
20220208 | 20220208017 | 17 | sanitary manhole replacement | is there information on the depth and size of the existing sanitary sewer line for the manhole replacement item? | Below is the information for the sanitary manhole to be replaced at STA 72+98, 1.0â€™ LT. Sanitary Manhole Station 72+98, 1.0â€™ LT Rim Elevation: 863.24 Depth from Rim: 11.15â€™ Invert Elevation of pipes: 8â€ North: 852.09 8â€ South: 852.12 | Fred Schunke | 5 | 2022-02-03 08:59 | 2022-02-03 14:19
20220208 | 20220208017 | 17 | Storm Sewer Pipe 36 inch Class III-A | The storm sewer table shows 8 lf of 36" C3A pipe being required between Strs. 34 & 8299. The storm sewer plan shows neither of these storm structures, or the pipe, being removed/replaced. What work is expected to occur for this pipe run? | The quantity of 8 LF shown between structures 34 and 8299 is incorrect and there will be no proposed work for this pipe run. This is an existing pipe as shown in the rest of the storm sewer plans. Because this will not affect the design and is a small quantity change, an emergency addendum will not be issued before the upcoming LET on Tuesday. This will be covered at the precon meeting to ensure that the contractor is aware that there is no work for this pipe run. | Fred Schunke | 6 | 2022-02-03 10:58 | 2022-02-04 14:19
20220208 | 20220208017 | 17 | Traffic Signals | Lead time on traffic signal items have been 25-35+ weeks. How is this going to be addressed as the completion date doesn't allow that much time? |  |  | 7 | 2022-02-07 13:16
20220208 | 20220208018 | 18 | MGS Guardrail Items | There is only quantity for MGS Thrie Beam Transition on 3 corners, but 4 corners are shown. Please clarify. There is no short radius shown or the short radius terminal. Please clarify. What radius of short radius is anticipated? Assuming the short radius is on the NW corner, the SDD requires 25 feet of MGS 3 for height adjustments. Is this included in the quantity, and is there space for it? The concrete mow strip quantity is 120 sy. Is the intent to place this item on the full length of all MGS guardrail sections? | â€¢ There is only quantity for MGS Thrie Beam Transition on 3 corners, but 4 corners are shown. The Thrie Beam Transition will be on all 4 corners â€¢ There is no short radius shown or the short radius terminal. The short radius is on the NW corner â€¢ What radius of short radius is anticipated? minimum radius of 8' per SDD 14B53-a â€¢ The concrete mow strip quantity is 120 sy. Is the intent to place this item on the full length of all MGS guardrail sections? yes | Fred Schunke | 1 | 2022-01-24 10:22 | 2022-01-31 13:56
20220208 | 20220208018 | 18 | MGS Guardrail Items Follow-Up | In a previous answer, there was supposed to be an addendum concerning this work. How should bidders proceed? | It was decided an Emergency Addendum would not be issued, that the resulting general quantity changes could be addressed in the field. â€¢ There is only quantity for MGS Thrie Beam Transition on 3 corners, but 4 corners are shown. The Thrie Beam Transition will be on all 4 corners. â€¢ There is no short radius shown or the short radius terminal. The short radius is on the NW corner â€¢ What radius of short radius is anticipated? minimum radius of 8' per SDD 14B53-a â€¢ The concrete mow strip quantity is 120 sy. Is the intent to place this item on the full length of all MGS guardrail sections? yes | Fred Schunke | 2 | 2022-02-07 07:50 | 2022-02-07 11:32
20220208 | 20220208019 | 19 | Pavement Markings | In looking at the requirement that the center line pavement markings be installed within 3 days of the completion of each layer, will the center line rumble strips be in-place prior to the permanent markings being installed within the 3 day period of completion of the surface layer? If not, should the quantity of center line markings be doubled as they will need to be placed once again after the rumbles are installed? In addition, what is the plan for the layout of the rumble strips? On similar projects, there would be a temporary epoxy item that provides for layout of the rumbles as well as guidance of traffic between the time that the surface layer is complete and the installation of the rumble strips as well as between the time the rumbles are placed and the permanent markings are installed. | Temporary Paint Would need to be applied to the final surface until such time as the rumble strips can be ground in. Same day epoxy centerline must be applied immediately after rumble strips are ground in. | Fred Schunke | 1 | 2022-01-25 07:21 | 2022-01-31 16:20
20220208 | 20220208019 | 19 | Base patching thickness | The typical existing sections do not have a thickness on the asphalt overlay on the concrete areas. Nor do they have any stationing or locations of approximate locations. Without a detail or typical existing detail asphalt thickness it is not possible to price the base patching by the square yard. Please provide the thickness of the asphalt overlay or a detail of how thick the base patch should be. | All concrete Items will be removed from plans. Asphalt repairs will only occur above the existing, underlying concrete. Repairs above existing concrete will consist of full or partial depth asphalt. Correction to be made in Addendum #1. | Mike Coleman | 2 | 2022-01-31 18:29 | 2022-02-03 10:09
20220208 | 20220208019 | 19 | Additional Question | Thank you for your response to the previous question. 3 additional questions to ask after reviewing the response. 1. There is no temporary paint or temporary epoxy item included in this project. Will the department add a temporary item to handle the payout of the rumbles? 2. Epoxy is not to be placed over temporary paint unless the department would like to take on the warranty for the pavement markings that are placed on top of paint, will a temporary epoxy item be added or, if a temporary paint item is added, will the department require the temporary paint to be removed? 3. The response to my previous question states that same day epoxy centerline must be applied immediately after rumble strips are ground in. Will the department be adding a same day epoxy item to accommodate this desire? Thank you. | Temporary paint, temporary epoxy and same day epoxy centerline quantities will be provided in Addendum #1. | Mike Coleman | 3 | 2022-02-01 06:19 | 2022-02-03 10:11
20220208 | 20220208019 | 19 | 72 Hour Requirement | Per the â€œProsecution and Progressâ€ section of the special provisions, all asphaltic base patching will be completed after milling operations. Additionally the section states to not leave milled pavement surface exposed for more than 72 hours. With base patching following milling at unknow locations/quantities, the potential of undercutting below the patches, and having proper length of pavement ready for PWL test strip, the 72 hours requirement does not allow enough time to complete all work. Can the 72 hour requirement to cover milled pavement be removed from the project specifications? | As concrete items will be removed, and an asphaltic repair SPV added, the contractor will have sufficient time to perform these repairs. A new asphaltic repair detail will be provided in Addendum #1. The asphaltic repair will be performed by milling the existing asphalt partial or full depth. | Mike Coleman | 4 | 2022-02-02 14:22 | 2022-02-03 10:12
20220208 | 20220208022 | 22 | 72 hour restriction | Would the WIDOT consider removing the 72 hour restriction between milling and paving from the project special provision found in the â€œ Milling and Paving Operationsâ€ on page 5. This project would be difficult to build as a mill and fill for the following reasons: 1. Once milling is complete, the milled surface is inspected for yielding areas and if any yielding areas are discover the â€œBase Repair for CIR Layerâ€ must be completed prior to CIR. Time must be allotted to complete this base repair. 2. In order to avoid centerline elevations drop-offs the milling must matchup daily. Cold in place recycling on the other hand does not need to matchup daily because the CIR closely matches the elevation of the milled adjacent lane or previously Cold In placed lane. The conflict with the 72 hours restriction therefore comes due the fact the CIR has a longer daily work zone than does the milling since the CIR is working on one side of centerline only each day and the milling is working on both side of centerline each day in order to match up. The milling must therefore be far enough ahead of the CIR to maintain a minimum of one mile of separation (is that correct ?) between traffic control setups. This will result in the CIR not being complete within 72 hours of the milling. 3. If the CIR operation is required by the 72 hour restriction to match up daily it will add significantly to the costs to the operations due to production inefficiencies. Not only will the project take longer to build but the number of construction joints would multiply many times over and the number of dead walks with heavy equipment to get to the next dayâ€™s starting location will multiply many times over. | 1. 72-hour restriction will be revised to 7 days via addendum. This should provide enough time to complete Base Repair for CIR Layer. 2. Milling must match daily. CIR must start within 7 days of the milling, but does not need to match daily if there is an even cross sectional surface with the adjacent lane. 3. CIR limits do not need to match up daily, however, per the standard spec a 2â€ or greater drop-off is not acceptable and would need to be dealt with in the field by the contractor. | Fred Schunke | 1 | 2022-01-21 10:21 | 2022-01-26 16:04
20220208 | 20220208022 | 22 | Pilot car use | The pilot car is required for the CIR, but is it also required for the milling and the HMA Paving? | SDD 15C12-07, note #2 details the requirements for pilot car use for any flagging operations, regardless of work operation. An addendum will be issued to clarify sentence #2 of paragraph #2 under Article #4 of the special provisions that the pilot car is required for the CIR operation at all times, unless other operations utilizing a flagging operation meet the requirements listed in SDD 15C12-07. | Fred Schunke | 2 | 2022-01-21 10:22 | 2022-01-26 16:01
20220208 | 20220208022 | 22 | Traffic | During the detoured time frames can the road be closed for the culvert pipe work at the locations or will the road need to be left one lane open and flagged. The schedule of operations only says to flag during milling, CIR, and paving operations. Please clarify. | We will be submitting an addendum to clarify if the roadway can be closed for culvert work while the highway is detoured. Draft Modification: Maintain two-way counter directional traffic along STH 96 except as noted in the Detour section below. While STH 96 is open to through traffic, one lane may be closed with flagging operations during daylight hours. While STH 96 is detoured to through traffic, both lanes may be closed to local traffic during daylight hours for culvert pipe replacements, while maintaining a minimum 10â€™ access for emergency vehicles on a base aggregate surface, and restore STH 96 to normal two-way traffic operations at the end of each workday on a minimum of a base aggregate surface. While STH 96 is detoured to through traffic, and if closed to local traffic, maintain access to all commercial, private, and field entrances at all times for local residents, and businesses from one direction or the other. | Fred Schunke | 3 | 2022-01-25 09:02 | 2022-01-26 16:00
20220208 | 20220208022 | 22 | Prepare Foundation for Asphaltic Shoulders Quantity | The prepare foundation for asphaltic shoulders quantity appears to only figure one side of the road. Based on the typical both sides in the given station ranges need to be widened. Will quantity be added to reflect this? | The quantity for Prepare Foundation for Asphaltic Shoulders, Item 211.0400, does appear to be approximately ï¿½ of what it should be. The quantity will be re-calculated to include quantity for both sides of the roadway, where applicable, and an addendum will be issued to correct the quantity error. | Fred Schunke | 4 | 2022-01-30 15:33 | 2022-02-02 11:17
20220208 | 20220208022 | 22 | Base Repair for CIR | The special provision describes the base repair for CIR item to include 5" of HMA millings or 5" if asphaltic surface. If asphaltic surface is required will the HMA be paid separately under the asphaltic surface unit price? | As described in Article #23 of the Special Provisions - Base Repair for CIR Layer, Item 211.0800.S, the contractor is given the option of placing 5â€ of either milled and re-laid pavement material or asphaltic surface. Payment for the contractorâ€™s chosen material is included in the item cost, as described in section E â€“ Payment of the special provision. No additional payment will be made for either the milled and re-laid pavement material or asphaltic pavement. | Fred Schunke | 5 | 2022-01-30 15:38 | 2022-02-02 13:56
20220208 | 20220208022 | 22 | Design Construction Schedule | Can the department provide the anticipated construction schedule used during design? | The design schedule is at the following location: https://wisdot.box.com/s/2ttkk29kdp4363x7as207as3hc1a4i23 | Fred Schunke | 6 | 2022-01-30 15:38 | 2022-02-01 09:42
20220208 | 20220208022 | 22 | 1.25" Base | The quantity in the MQ's doesn't seem to reflect filling in the patches with gravel and only accounts for 14" of Base. These areas will have to be filled in and the quantity to do so have been in other similar jobs. Please clarify. | An addendum will be issued to add additional 1.25â€ BAD quantity to accommodate filling the culvert pipe patches. | Mike Coleman | 8 | 2022-02-02 12:15 | 2022-02-03 05:42
20220208 | 20220208022 | 22 | Foundation backfill | Some culverts have frost heave work associated with them and some do not. How is the pipe foundation backfill going to be kept track of for the culvert pipes with frost heave work? There is a note saying its incidental to the pipe but in reality how is the incidental foundation backfill going to be seperated from the paid foundation backfill? Some pipe will include incidental foundation backfill and some will not? Seems confusing. | Per the culvert pipe details found on page 16 of the plan, there are 2 different construction methods for installing culvert pipes, and the culvert pipe installation methods and trench/transition requirements are called out on those details per pipe. â€¢ For the pipe installation method requiring transition cuts/fills, the foundation backfill will be paid separately for said transitions. However, in those pipe installations that require transition cuts/fills, the actual pipe trench excavation and subsequent backfill is paid for under the culvert pipe bid item, to the lines and widths shown on page 16 of the plan and within section 520 of the standard specifications. â€¢ For the pipe installation method not requiring transition cuts/fills, the foundation and backfill will be paid in accordance with section 520 of the standard specifications. | Mike Coleman | 9 | 2022-02-02 14:08 | 2022-02-03 05:53
20220208 | 20220208024 | 24 | Design Schedule | Please provide access to the DOT design schedule if one existed during the design phase of the project. | Addendum No. 1 changed the proposal to a completion date contract. The Contract Time for Completion chart can be found at: https://wisdot.box.com/s/0nnfmlkf7b4g38sbj9lfjnwevli9hzg1 Or can be accessed from the February Bid Letting page. | Jill Fehrman | 1 | 2022-01-25 07:31 | 2022-01-26 08:00
20220208 | 20220208024 | 24 | Bird Deterrent System Working Days | Will the Department charge working days for installing the bird deterrent system on this project? Previously let projects have a note in the SPVs stating that no working days will be charged for installing the bird deterrent system. | Addendum 1 for this proposal changed the proposal from working day contract to a completion date contract. Addendum #2 will modify language in the Special Provisions Traffic article to allow flagging operations to take place prior to June 1, 2022 for the installation of a bird deterrent system. | Jill Fehrman | 2 | 2022-01-25 07:36 | 2022-01-26 08:06
20220208 | 20220208024 | 24 | Underwater Concrete | The general notes of the structure plans state that pier concrete poured under water will be allowed if water depth to bottom of pier is less that 5 feet. Please advise what happens when the water is greater than 5 feet in depth at the piers as the contract does not contain any provisions or bid items for a concrete foundation seal. | The general note regarding concrete poured underwater at the pier will be revised in Addendum #2 as follows: â€œAt piers, cofferdam required. Concrete poured underwater will be allowed and shall be done in accordance with standard spec. 502.3.5.3. Concrete poured underwater shall not exceed 10.0 feet in depth, unless approved otherwise.â€ If water depth exceeds 10 ft it should be expected that dewatering will be required. | Fred Schunke | 3 | 2022-01-25 07:47 | 2022-01-26 15:29
20220208 | 20220208024 | 24 | 404 Permit and Construction Access | The Department has not received a 404 Permit for the project to impact wetlands, so how does the Department intended for the contractor to access the existing piers for removal and new piers for construction? Will the contractor be able to impact the river as long as it is within the slope intercepts of the bridge? | Construction under normal water depth is anticipated to take place from a barge. The contractor has the option of requesting/applying to build some form of causeway or docking wall but any additional impacts to wetlands or the waterway will need to be reviewed and approved by WisDOT, WisDNR, Manitowoc County Zoning (floodplain), and potentially the US Army Corps of Engineers (USACE) prior to install. The waterway marking plan/permit may also need to be modified based on waterway impacts. Itâ€™s crucial that this coordination takes place as early as possible to allow other agencyâ€™s time to review and approve impacts/plans. 404 Permit â€“ Project impacts are currently permitted under the Transportation Regional General Permit, Category 2, No Pre-construction notice with USACE. If proposed impacts exceed the permit parameters, additional coordination with USACE is required (likely a pre-construction notice). Once additional waterway impacts are known, WisDOT can aid in reviewing and modifying the permit as needed. A link to the permit is located here: https://www.mvp.usace.army.mil/Portals/57/docs/regulatory/RGP/Transportation_RGP.pdf?ver=2018-02-22-093530-183 Again, if additional temporary wetland or waterway impacts are anticipated, coordinate as soon as possible after letting with the WisDOT to determine course of action. | Mike Coleman | 4 | 2022-01-31 12:33 | 2022-02-03 09:55
20220208 | 20220208024 | 24 | Construction Staking Structure Missing Item | It appears that the contract is missing the item for Construction Staking Structure (650.6500) as this will be necessary in order to construct the new bridge. | Bid item 650.6500 Construction Staking Structure Layout will be added to the contract through an addendum. | Fred Schunke | 5 | 2022-02-01 07:29 | 2022-02-01 11:58
20220208 | 20220208024 | 24 | Pavement marking | Why was a Cold Weather Marking Epoxy 4" item added. Is temporary marking needed at a certain phase? Is this type of marking to be put down between the upper & lower level asphalt and before the Base ? | Item 646.6464 Cold Weather Marking Epoxy 4-inch was added to the project in addendum #1 when the contract was modified from a working day to completion date contract. With the contract completion date moved to November, the designer had concerns that pavement marking might occur in cold weather conditions discussed in 646 of the standard spec. If temperatures require, cold weather marking is anticipated to be applied to the finished upper layer of asphalt then, when temperatures increase, cold weather marking will be removed and 646.1020 Epoxy applied. If temperatures are warm enough or the engineer allows, the item of cold weather marking will not be used and 646.1020 Epoxy will be applied to the upper layer of asphalt prior to opening the roadway. Contract time may need to be modified if cold weather marking is used. The use of temporary marking is not anticipated since the roadway will be closed to traffic for construction. | Mike Coleman | 6 | 2022-02-01 09:35 | 2022-02-03 09:56
20220208 | 20220208025 | 25 | preliminary schedule | The contractor is requesting a copy of the DOT's preliminary schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/136dlc6goao63ugl9isjd4zzeiwj2yge or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-01-19 09:58 | 2022-01-24 11:32
20220208 | 20220208025 | 25 | Closures | In the traffic section under segment C there is a note stating " Do not close multiple auxiliary lanes simultaneously". Is this per direction, as the majority of the work is being constructed in a dived highway section and a NB closure will have little to no effect on a SB closure? | Yes. The intent is to not close auxiliary lanes of adjacent/consecutive intersections in the same direction of travel simultaneously. An addendum will soon be posted to revise this and other language in Article 5 Traffic. | Mike Coleman | 2 | 2022-01-19 10:04 | 2022-01-24 15:39
20220208 | 20220208025 | 25 | Commuter Peak Hours | Are Commuter Peak hours only valid after May 26th? | No. Commuter peak hours are valid for the entire year. | Jill Fehrman | 3 | 2022-01-25 16:56 | 2022-01-26 08:54
20220208 | 20220208025 | 25 | undoweled base patching | If a Vermeer saw is used will the patches still need to be saw cut 2" deep? | No. If a Vermeer saw is used, the 2-inch deep saw cut is not necessary. | Fred Schunke | 4 | 2022-01-26 10:23 | 2022-02-02 10:55
20220208 | 20220208025 | 25 | Construction between CTH U and the Bayview Bridge | There is a plan note stating " Daytime flagging shall occur" for the above area, and that "flagging shall not occur during commuter peak hours". The special provisions also state "provide an even cross-sectional profile on adjacent paved lanes". As this area cannot be paved in a single 6 hour closure what will the region allow? | An addendum will issued to revise the â€œeven cross-sectional profile on adjacent paved lanes and shoulders open to trafficâ€ language to be applicable to weekends only from noon Friday to 9:00 PM Sunday. Due to the two-lane counter-directional traffic in this section, flagging operations will still be necessary to construct this segment. However, flagging will not be allowed during Mainline Peak Hours nor Commuter Peak Hours. | Mike Coleman | 5 | 2022-02-01 15:39 | 2022-02-02 18:01
20220208 | 20220208025 | 25 | 4MT lower layer | There are several areas of 4MT lower layers that will have to be constructed prior to a volumetric test strip. How are those tons to be tested as there are no QMP tons indicated in the miscellaneous quantities for those areas? | The quantity for those 4MT lower layers will be moved from the PWL Incentive Air Voids HMA Pavement item to the QMP Incentive Density HMA Pavement item. This change will be made as part of an upcoming addendum. | Mike Coleman | 6 | 2022-02-01 15:49 | 2022-02-02 18:11
20220208 | 20220208025 | 25 | Schedule | With contract execution being approximately 6 weeks from bid time, which would be March 22nd, how is the contractor supposed to meet the interim completion date of June 30th for section C, when the DOT preliminary schedule shows starting in early March and not finishing until early July? | The Departmentâ€™s Contract Time for Completion Analysis is a draft not for bidding purposes. Under Article 3 Prosecution and Progress of the special provisions, there is language that states, â€œThe interim completion date for segment C is based on an expedited work schedule and may require extraordinary forces and equipment.â€ | Fred Schunke | 7 | 2022-02-03 08:19 | 2022-02-03 14:49
20220208 | 20220208026 | 26 | Pavement Marking Quantities | Good morning, Will you please check the proposal quantities versus the miscellaneous quantities? It appears that many of them are different and that some quantities of one item might be included in another, etc. Will a clarification or addendum be issued to correct this? Thank you. | An addendum will be issued. The quantities in the plans are correct. Some quantities in the proposal are not. | Mike Coleman | 1 | 2022-01-13 09:36 | 2022-01-19 14:25
20220208 | 20220208026 | 26 | Pavement Marking Quantities | Good morning, Will you please check the proposal quantities versus the miscellaneous quantities? It appears that some items are classified under the wrong item in the plans versus the proposal. Will a clarification or addendum be issued to correct this? Thank you. | The quantities in the plans are correct. Some quantities in the proposal are not. An addendum will be issued to correct. Plan sheet 56 (4670-10-71) (Estimate of Quantity) should be updated with proposal quantity changes below: Proposal Quantity Changes: Item 646.1005 item should be deleted. Item 646.1020 should have revised proposal quantity of 22214 LF. Item 646.1040 should have revised proposal quantity of 42457 LF. I also found an additional error that may or may not need to be addressed by addendum: Item # for temporary marking line paint is incorrect in 4580-10-71. Says 649.0150, should be 649.0105. Plan sheets 99, 100 (4580-10-71) and 100 (4670-10-71) should have item # for Temporary making line paint 4-Inch changed from 649.0150 to 649.0105. | Mike Coleman | 2 | 2022-01-13 09:51 | 2022-01-19 14:26
20220208 | 20220208026 | 26 | MIssing Plan & Profile Sheets | In going through the plan set for Proposal 26 it appears there are plan sheets missing for STA 209+00 to STA 232+00 and STA 328+00 to STA 349+00. Have those areas been intentionally left out? | Plan and profile sheets are not provided for the areas stated in the question and have intentionally been left out. However, plan only sheets are provided after the plan & profile sheets, starting on sheet 135, to cover the remaining areas that a design profile is not provided for or needed. | Mike Coleman | 3 | 2022-01-17 09:17 | 2022-01-24 07:24
20220208 | 20220208026 | 26 | Milling Quantities- Sherwood | In the town of Sherwood there is a note on Sheet 57 that the Parking milling pay limit is 6'. In the typical sections this is shown as 8'. Is the note on Sheet 57 incorrect? Also in the same table from 397+37 to 419+00 have a note that excludes the shoulder milling. The typical sections shows that the shoulder is to be milled to the curb line or the edge of the asphalt shoulder. Which is correct? | This was addressed in Addendum #01. | Mike Coleman | 4 | 2022-01-26 10:16 | 2022-02-03 09:43
20220208 | 20220208026 | 26 | Start By Date | Would the Department consider allowing moving the Start By Date by 2 weeks to June 27th? | WisDOT will not be change the language in the prosecution and progress section of the Special Provisions. | Mike Coleman | 5 | 2022-02-02 09:34 | 2022-02-03 09:49
20220208 | 20220208026 | 26 | Stage 1B | With all of the Concrete Curb and Gutter work, Frost Heave Repairs, and Paving work South of CTH M in Stage 1 would the department consider adding an additional 5 working days to Stage 1B to allow this work to be completed under a closure with a Detour? | The benefit to the contractor by adding working days to stage 1b does not outweigh the roadway user costs for motorist will experience when STH 114/55 is closed. The detour in stage 1b covers the work the department feels cannot be done under traffic. Activates that must be completed under stage 1b: 1. CTH M intersection island and curb ramps as well as CTH M east and northeast curb ramps including asphaltic patching 2. subgrade repair from station 427+60 to station 428+00 including asphalt patching; 3. Pedestrian bump-outs and curb ramps at station 428+65 LT and RT 4. frost heave repairs at stations 458+99 and 467+33 including asphalt patching All other actives on STH 114/55 from Stumpf Ave to the South Junction of STH 114/55 can be done outside of stage 1b under traffic. | Mike Coleman | 6 | 2022-02-02 09:37 | 2022-02-03 09:51
20220208 | 20220208026 | 26 | Coloring concrete Red | There is a bid item for Concrete Truck Apron 12-Inch(416.0512) Should there be a bid item for Coloring concrete WISDOT Red? CY (405.0100) | It was determined that the concrete truck apron being placed with the project does not need to be red so bid item 405.0100 Coloring Concrete Red was not included. | Mike Coleman | 7 | 2022-02-02 14:01 | 2022-02-03 09:50
20220208 | 20220208027 | 27 | Soil Borings | Are any soil boring reports available? | The geotechnical report can be found at the following location: https://wisdot.box.com/s/w8xa1h9wqhk7lnj5qqu314h8t36ebt6t or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-01-14 10:35 | 2022-01-24 08:25
20220208 | 20220208027 | 27 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 2 | 2022-01-21 11:51 | 2022-01-24 15:57
20220208 | 20220208027 | 27 | Storm Sewer | Storm Sewer Plans and Misc Quantity table for the storm pipe runs don't jive. There are runs and structures in a table that are not shown in the plans. Could that be checked out. Thank you | We have created Addendum 1 to revise the impacted plan sheets. | Fred Schunke | 3 | 2022-01-24 10:07 | 2022-01-26 15:37
20220208 | 20220208027 | 27 | Contractor Data Package | Can Data Packet for the project be provided? We are looking for the tables for misc quantities and Original and Proposed Surface files | This is a local program project and the contractorâ€™s package is not required for design therefore it was not compiled during design. | Fred Schunke | 4 | 2022-01-25 12:08 | 2022-01-26 15:48
20220208 | 20220208027 | 27 | Traffic Control | Traffic Control Article states :"Close the project to through traffic. Prior to closing Emons Road, implement the traffic control as shown on the plans or as directed by the engineer. Emons Road may be reduced to one lane using flagging operations during working hours as allowed by the engineer." How do we interpret this two sentences? Does it mean that all construction operations have to be flagged? | The intent of the two statements is that the road is intended to be closed to through traffic, but remain open to local only traffic. The flagging is only to be used if the contractor needs to shut off a lane to install say storm sewer across the road. This is meant to indicate when this type of incident happens that the contractor provide flagging operations to keep at least one local only traffic lane open. | Fred Schunke | 5 | 2022-01-27 16:05 | 2022-02-01 09:46
20220208 | 20220208027 | 27 | QMP Nuclear Density | It appears there is no special provision for QMP nuclear density. Will QMP nuclear density not be the responsibility of the contractor? | This is not being required since we are under the 10,000 ton suggested start point. The region also never indicated the need to include this item. | Fred Schunke | 6 | 2022-02-07 08:02 | 2022-02-07 11:35
20220208 | 20220208029 | 29 | RR insurance & coordination | Can you explain why there is an SPV for RR insurance and coordination when the RR tracks are outside of the project limits? According to the utility and plan and profile sheets; the RR x-ing is beyond the project limits. Typically this would only be required when working on or within the RR r/w. | Due to the traffic control through the railroad and approach signing and pavement marking the STSP is needed. | Mike Coleman | 1 | 2022-01-19 14:09 | 2022-01-24 07:32
20220208 | 20220208029 | 29 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 2 | 2022-01-21 11:52 | 2022-01-24 15:57
20220208 | 20220208029 | 29 | Fertilizer | Please adjust the fertilizer totals. It appears that the unit of measure was not followed in the MQ table. | The fertilizer total will be adjusted in an addendum. The storm sewer will be bid as shown in the plans, no Class III A or B allowed. | Fred Schunke | 3 | 2022-01-25 14:39 | 2022-01-26 15:51
20220208 | 20220208029 | 29 | Clearing and Grubbing | For the Clearing and Grubbing Items, was the correct unit of measure used ?? Why wouldn't you bid these both as ID, and not SY ?? | This was reviewed and the item will be changed to ID. An addendum will be issued. | Fred Schunke | 4 | 2022-01-26 10:23 | 2022-02-01 11:54
20220208 | 20220208031 | 31 | Butt Joints | Per sheet 7, the plans shows a detail for butt joints on the milled surface. Will an item be added ? | An Addendum will be issued to add the missing bid item. | Jill Fehrman | 1 | 2022-01-24 10:32 | 2022-01-26 08:49
20220208 | 20220208031 | 31 | Private Asphalt Driveway | Per sheet 30, the plans show a PE asphalt driveway. Will an item be added? | An Addendum will be issued to add the item to the proposal. | Jill Fehrman | 2 | 2022-01-24 10:34 | 2022-01-26 08:52
20220208 | 20220208031 | 31 | Start Date | Would the Department consider removing the stipulation that work must start no later than July 5, 2022? |  |  | 3 | 2022-02-02 14:38
20220208 | 20220208032 | 32 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | The culvert pipes at Stations 272+97, 342+13, 933+14, and 954+68 were chosen to have class III reinforced concrete pipe so that a smooth barrel would be installed for better hydraulic performance. If the class III A or B non-metal pipe item is used, then corrugated items may be installed and negatively affect the hydraulic performance. The designer and I discussed an alternative to upsize the pipe and use the class III A or B non-metal culvert pipe that allows a non-metallic corrugated material. However, this decision would lead to negative headwater impacts with a corrugated pipe, and/or negative impacts on the approach ditching design when upsizing a pipe that requires lowering a pipe invert to achieve a 2.0â€™ fill height. | Fred Schunke | 1 | 2022-01-21 11:54 | 2022-02-04 08:24
20220208 | 20220208032 | 32 | Prepare Foundation for Asphalt Shoulders/ Excess Shoulder Material | Under preparing foundation for asphalt shoulders, 2' of of the existing shoulder gravel will have to be graded out up to 4 inches thick after milling. Will the shaping of this material after asphalt paving be incidental to this item? Will an item be added if this material needs to be moved or removed? | The prepare foundation for asphaltic shoulders item includes the excavation and shaping of the existing shoulder gravel to be placed on the remaining aggregate shoulder after paving. Not currently anticipated and if necessary, during construction an item will be added to remove or move the excess aggregate shoulder material that canâ€™t be bladed along the roadway and used along the shoulder. | Fred Schunke | 2 | 2022-01-30 15:23 | 2022-02-01 12:29
20220208 | 20220208032 | 32 | Design Construction Schedule | Can the department provide the anticipated construction schedule used during design? | The design schedule is included in the following Box Folder: https://wisdot.box.com/s/v77647cshlz1qrytbrrn3ubu1brf6twc The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Fred Schunke | 3 | 2022-01-30 15:24 | 2022-02-01 12:28
20220208 | 20220208032 | 32 | Parking Lanes Suring | With having to mill the mainline 4" and the parking lanes 1-3/4" will the parking lanes be allowed to remain closed until paving is able to provide an even cross section similar to what is allowed with the passing lane? | After milling, the parking lanes will need to be open after paving the mainline lower layer to eliminate the vertical drop off 2 inches or greater within 72 hours or before a weekend or holiday whichever comes first per Standard Specifications 104.6.1.2.3(2). | Fred Schunke | 4 | 2022-01-30 15:27 | 2022-02-01 12:29
20220208 | 20220208032 | 32 | Even Cross Section Profile Paving Operations 72 hrs. | The second paragraph under Surface for Milling, Paving, and Trenches states â€œFor paved surface open to through traffic, provide an even cross-sectional profile of the roadway within 72 hours of paving adjacent lane.â€ If the contractor utilizes a notched wedge to eliminate the vertical longitudinal joint as required by the standard specification, could this special be removed? | No, a notched wedge will not eliminate the special provision to provide an even cross-sectional profile of the roadway within 72 hours of paving the adjacent lane for a paved surface open to through traffic. | Fred Schunke | 5 | 2022-02-02 09:49 | 2022-02-03 14:40
20220208 | 20220208032 | 32 | Utilities | Page 8 & p of the specials states that CenturyLink has 16 locations that will need to be monitored and adjusted during construction. The language also says "Provide advance notice prior to beginning culvert work, and the site will be available to the utility owner at the locations above for onsite monitoring. Cable adjusting will take approx. ï¿½ day at each location" We have tried to reach CenturyLink to get clarification, but they are not responding to phone calls or emails. Our question is: Will CenturyLink be able to monitor and adjust their cables in advance of our crew being at each specific location or do we need to allow standby of our crew while CenturyLink makes the adjustment? | Notify CenturyLink prior to beginning the culvert work and follow the Trans 220 process as stated in the special provisions if cable adjusting is necessary. Monitoring is required at all locations, but conflicts at each location are not anticipated. A secondary contact for Century Link is Scott Heinzelman, Phone: (920)361-8409, Cell: (920)757-4802, Email: Scott.Heinzelman@lumen.com | Fred Schunke | 6 | 2022-02-03 08:56 | 2022-02-03 16:06
20220208 | 20220208032 | 32 | SPV 0195.01 1-1/4 inch ( for temporary Widening ) | There is a special provision writen but there is no cooresponding bid item | The special provision SPV.0195.01 1 ï¿½ inch (for temporary widening) was included in error. All bid items are accurate in the plan and no addendum will be added. | Fred Schunke | 7 | 2022-02-03 13:36 | 2022-02-04 08:08
20220208 | 20220208033 | 33 | Adjusting manhole covers | Special Provision #26 (Adjusting Manhole Covers) has a 6' straightedge requirement. Special Provision #41 (Adjusting Sanitary Manhole Covers) does not have a straightedge requirement. Is this correct? | Special Provision #41 (Adjusting Sanitary Manhole Covers) references all of standard spec 611.3 which incorporates the 6â€™ straightedge requirement. There is no need for an addenda to be issued. | Fred Schunke | 1 | 2022-02-02 10:44 | 2022-02-03 15:18
20220208 | 20220208033 | 33 | Project Schedule | Will the department please provide the preliminary schedule used in the project design and development for review? | The design schedule can be found at the following location: https://wisdot.box.com/s/wjbiokklpicm2qhwfotj1wlutpmlzmjs or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2022-02-02 10:49 | 2022-02-03 09:29
20220208 | 20220208034 | 34 | Schedule | Could you please provide the design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/71unnwayw85lsp5ehdv7wv1y9yg4kbgn or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-01-18 10:02 | 2022-01-24 07:17
20220208 | 20220208034 | 34 | DBE Goal | This project has a DBE participation goal of 8%. This project primarily consists of concrete repair, concrete milling, HMA pavement, pavement marking, and traffic control. There are limited items for DBE contractor participation, other than trucking. Would the DOT be willing to review the DBE goal for this project? Thank you. | WisDOT has reviewed the proposed work, and DBE contractors that have worked on projects in the region. The established DBE Goal of 8% is appropriate for this project. | Mike Coleman | 2 | 2022-01-24 13:43 | 2022-02-02 12:14
20220208 | 20220208034 | 34 | Milled Surface | The Prosecution and Progress Special Provision states "Do not reopen any portion of the roadway, including intersections east of 190+00, to traffic after partial depth concrete removal until after installation of the HMA interlayer". The Traffic Special Provision also state in Stage 2, "Do not maintain ramp traffic across the milled surface prior to paving the HMA interlayer" and "Do not maintain intersection traffic across the milled surface prior to paving the HMA interlayer". The Base Patching Asphaltic for HMA Interlayer and Pavement Interlayer Special Provision discusses removal of deteriorated concrete areas and patching of these areas after milling. This provision also states "The surface shall be dry for at least 24 hours, and clean, prior to placement of the mixture (interlayer)". Will the department consider allowing traffic on the milled surface east of station 190+00 to allow completion of the milling and patching prior to beginning the interlayer paving? | The design team and Region have reviewed the question and are against permitting traffic to run on the milled surfaces. There is concern with the remaining pavement structure being adversely affected should traffic be permitted on it. â€¢ The primary reason is due to the remaining pavement structure (variable depth in milling of the concrete pavement in some areas) the concrete pavement will be 5.5â€ to 6.5â€ thick and the asphalt shoulders will be less than 3â€ thick. â€¢ The other reason is at the ramps there will be a significant lip (3â€-4â€). | Mike Coleman | 4 | 2022-01-28 08:04 | 2022-02-02 18:21
20220208 | 20220208034 | 34 | Interlayer Paving - Dry conditions for at leat 24 hours | The Prosecution and Progress SP states "Do not reopen any portion of the roadway, including intersections east of 190+00, to traffic after partial depth concrete removal until after installation of the HMA interlayer". The Traffic SP Stage 2 states, "Do not maintain ramp traffic across the milled surface prior to paving the HMA interlayer" and "Do not maintain intersection traffic across the milled surface prior to paving the HMA interlayer". The Base Patching Asphaltic for HMA Interlayer and Pavement Interlayer SP discusses removal of deteriorated concrete areas and patching of these areas after milling and also states "The surface shall be dry for at least 24 hours, and clean, prior to placement of the mixture (interlayer)". Due to the use of water during the Removing Concrete Partial Depth, will the department allow paving of the interlayer east of 190+00 on the same day that the surface is milled to allow the road and intersections to be reopened at the end of the work day? | Yes, a notched wedge will eliminate the special provision to provide an even cross-sectional profile of the roadway within 72 hours of paving the adjacent lane for a paved surface open to through traffic. | Fred Schunke | 5 | 2022-02-03 12:54 | 2022-02-04 08:07
20220208 | 20220208035 | 35 | milling | Can a detail or typical section be provided to define the milling bid item on this project? Thanks | The milling operation refers to the milling of the existing asphalt overlay removal on the existing bridge B-1-18. Details and notes are provided in the bridge plan for B-1-18 for milling the asphalt from the existing bridge for complete removal. | Mike Coleman | 1 | 2022-01-18 07:13 | 2022-01-24 08:33
20220208 | 20220208035 | 35 | Boring Logs | Are any soil borings available? | https://wisdot.box.com/s/h9wx27u3wozd7hp1dxvob1coksiyw9r5 | Mike Coleman | 2 | 2022-01-20 12:24 | 2022-01-24 11:53
20220208 | 20220208035 | 35 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) Min/max cover heights are less than 15 feet for Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPCS? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 3 | 2022-01-21 11:56 | 2022-01-24 15:58
20220208 | 20220208035 | 35 | Traffic Control | The quantities of 5-Type III Barricades and 10-Type A lights does not seem correct, would you please review. Thank you. | The quantities were reviewed and no changes were found based on 5 Type III Barricades and 10 Type A lights. | Fred Schunke | 4 | 2022-01-27 15:07 | 2022-01-31 15:50
20220208 | 20220208037 | 37 | Flagging of STH 70 | Article 4 of the Special Provisions states, â€œMaintain a minimum of one lane of STH 70 traffic in each direction throughout the duration of the projectâ€. However, the notes in the plans (i.e. Traffic Control â€“ Stage 2, Sheet 27) says that, â€œAll Milling and Paving Operations on STH 17 and in the taper areas on STH 70 should be completed under flagging operations. Will the department allow STH 70 to be reduced to a single lane while flaggers are present for this work? | No, two lanes of traffic are to be maintained along STH 70 at all times. Flagging operations occur at the STH 17 intersection area which include STH 70 tapers as indicated Page 28. | Fred Schunke | 1 | 2022-01-27 12:45 | 2022-01-28 14:01
20220208 | 20220208037 | 37 | Construction Detail needed for Asphaltic Shoulder Widening | Since there are no cross sections provided, will the department provide a construction detail or typical section showing the intended pavement structure for the STH 17/70 Intersection Widenings to be constructed in Stage 1A? Should it be assumed that there will be a lower layer of pavement that needs to be constructed in this area that corresponds with the Prepare Foundation for Asphaltic Shoulder bid item? | Page 13 of the plans shows the layout of the edge of asphalt of the limited shoulder widening and corresponding note next to the point table gives the total asphalt thickness. There will be a lower layer based on the standard specifications. | Fred Schunke | 2 | 2022-01-27 12:48 | 2022-01-28 13:32
20220208 | 20220208037 | 37 | HMA Aggregate Size for Item 390.0208 Base Patching Asphaltic | Standard spec 315.2 via 390.2 requires that an asphaltic mixture with 1-inch nominal size aggregate (Gradation No. 2, i.e. a 2LT or 2MT mix type) is required for the base patching material. Would the department please change this to item 465.0110, Asphaltic Surface Patching, to allow a 19mm or 12.5mm nominal aggregate size mix to be used? Removals would also need to be accounted for in quantities for item 204.0110, instead of the current item. | Item 390.0203, Base Patching Asphaltic was specifically chosen to provide a more structurally competent repair to address the pavement issues in the limits shown. Please use this item. | Fred Schunke | 3 | 2022-01-28 12:00 | 2022-01-31 14:36
20220208 | 20220208037 | 37 | Will Shaping Shoulders be Added? | There are no details or items provided in the plan which would indicate the departmentâ€™s intent for the area where the asphalt shoulder will be removed in Stage 3 from STA 613+00 to 627+50 Left. The plans show removing approximately 10-ft width of asphalt pavement, and constructing a new shoulder to 10-ft wide at the widest point in the same area. It is assumed additional ï¿½â€ Base Aggregate Dense will be needed to replace the asphalt shoulder that is removed, but it appears that additional grading work will be needed to incorporate the remainder of the existing shoulder, back into the new shoulder. Will item 305.0500, Shaping Shoulders, be added to the project, or are there other bid items to cover this scope of work? | New 305.0110 Base Aggregate Dense ï¿½ Inch is being added to the shoulders at these locations via addendum. 305.5(2) indicates payment for Base Aggregate Dense bid items is full compensation for preparing the foundation; and for placing, shaping, compacting, and maintaining the base. Item 305.0500, Shaping Shoulders will not be added. | Fred Schunke | 4 | 2022-01-28 12:03 | 2022-01-31 14:38
20220208 | 20220208037 | 37 | Will an item be added for Prepare Foundation for Asphaltic Paving? | There are numerous areas for driveways behind new curb and gutter, as well as new areas of asphalt pavement at the boat landing and driveways after shoulder removal, as well as the milled surface; all these areas will require effort to fine grade, clean, or otherwise prepare for asphalt paving. Will item 211.0100, Prepare Foundation for Asphaltic Paving (project), be added to the job to cover this work, or should the bidders assume that all required preparation is incidental to other bid items? | Item 211.0100, Prepare Foundation for Asphaltic Paving (project) will be added via addendum. | Fred Schunke | 5 | 2022-01-28 12:05 | 2022-01-31 14:38
20220208 | 20220208037 | 37 | Project Schedule | Will the department please provide the preliminary schedule used in the project design and development for review? | The design schedule can be found at the following location: https://wisdot.box.com/s/s1ms4c764d31zarpmrtg4ysy4wdtrg9y or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2022-02-02 10:48 | 2022-02-03 09:27
20220208 | 20220208037 | 37 | Clarification to Response for Question #1, Re: Flagging of STH 70 | I am looking to clarify the response to question #1. The response states that 2 lanes of traffic must be maintained on STH 70 at all times, but also says that flagging operations will occur at the STH 17 intersection, and for the STH 70 tapers - These statements contradict one another. Due to the limitations for overall roadway width, and space required to physically construct the work as shown (within the area from the west limits to approx. the Mud Creek bridge) it is anticipated that STH 70 traffic will need to be reduced to a single lane via flagging during certain aspects of the milling and paving operations to construct the work through this area. The work at the STH 70 tapers cannot be constructed without temporarily reducing STH 70 to a single lane, but this is inherently contradictory to the statement that requires the contractor to maintain one lane of traffic in each direction on STH 70. Can you please clarify these contradictory statements? | To clarify â€“ yes, during the milling and paving operations work at the STH 70 taper areas, STH 17 intersection and other sideroads traffic along STH 70 will utilized single lane flagging operations as listed in the staging notes in the plans. While performing work at all other locations maintain a minimum of one lane of STH 70 traffic in each direction. | Fred Schunke | 7 | 2022-02-03 11:59 | 2022-02-03 15:50
20220208 | 20220208037 | 37 | Traffic Control for Lane Closures Over Weekends | Article 3, Para 4 of the Special Provisions states â€œâ€¦entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lightsâ€¦ From noon Fridays to 6:00 AM Mondays.â€ Due to the duration for the scope of work related to placement of temporary pedestrian facilities, followed by curb and pavement removals, and then curb replacement, curb ramp construction, cure time, asphalt patching in front of the curb, and finally removal of temp pedestrian facilities prior allowing to traffic to use the outside lane (which closed during stage 2), it appears impractical to perform all of this work between Monday at 6am to Fridays at noon, which would be necessary to allow the outside lane to be entirely clear of traffic control equipment. During Stages 2 & 3, when lane closures are allowed on STH 70, can the equipment related to the lane closures remain in place over the weekend, or will the department expect all lanes of STH 70 to be fully open and clear? | Yes, the lane closures during stage 2 & 3 particularly for the curb ramp and curb & gutter work are anticipated to remain in place over the weekend as free flow traffic will remain in a single lane in each direction. The only exception of this is during the dates listed in the Holiday and Special Event Work Restrictions as outlined in Article 4 paragraph 3. | Fred Schunke | 8 | 2022-02-03 12:55 | 2022-02-03 15:57
20220208 | 20220208038 | 38 | HMA Item | The project calls for 240 tons of 4 LT 58-28S for the bridge approaches. Will the DOT consider changing this item to Asphaltic Surface? | The region has agreed to change this to Asphaltic Surface. An addendum will be issued. | Mike Coleman | 1 | 2022-01-14 16:53 | 2022-01-19 14:24
20220208 | 20220208042 | 42 | Paving Operations | The Specials say to pave surface lift with 14 days of the lower lift on page 2 of the special provisions. There is a good chance that the lower lift may not be completed within the 14 days and allowing time for SMA test strip. | The requirement that, â€œThe contractor shall coordinate construction activities so that traffic does not travel on the lower HMA pavement layer for longer than 14 (fourteen) calendar days prior to placement of the upper HMA pavement layer.â€ will be removed from the Prosecution and Progress special provision article in an upcoming addendum. | Fred Schunke | 1 | 2022-01-31 15:31 | 2022-02-02 11:32
20220208 | 20220208042 | 42 | 72 Hr Rule | This job is not very conducive to milling and filling because the milling depth is more than the first lift of Asphalt which means you can only produce 1300 tons of Asphalt per day when you are milling 2500 tons per day. Mill and fill is also complicated by the varying depth of milling and varying width of milling. If you do not mill and fill because of the 72 hour rule and the abundance of wide pavement on most of this project it will be inefficient to try and keep separate lane closures less than a mile and have 2 miles between lane closures without going over 72 hours. | The requirement that, â€œThe contractor shall coordinate construction activities so that traffic does not travel on the milled asphaltic surface for longer than 72 hours prior to placement of the lower HMA pavement layer.â€, currently in the Prosecution and Progress special provision article will be revised so that 72 hours is changed to 96 hours in an upcoming addendum. | Fred Schunke | 2 | 2022-01-31 15:40 | 2022-02-02 11:32
20220208 | 20220208042 | 42 | Paving Operations | Can we leave an uneven lane overnight? Would DOT supply drums to put on the joint? | An uneven lane can be left overnight if allowed by the standard specifications and the engineer. Please refer to standard specifications 104.6.1.2.3 and 450.3.2.5(6), and Standard Detail Drawing SDD 13C19-03. The department will not supply drums to be placed along the HMA pavement longitudinal joints. | Fred Schunke | 3 | 2022-01-31 15:41 | 2022-02-02 11:33
20220208 | 20220208042 | 42 | Safety Concern | On page 13 of the plans the detail shows the deceleration lane and the intersection being milled to a shallower depth than the main line milling which could trap water on the outer edge of mainline in a rain event if not paved the same day? | In the event of significant rain between the milling and paving operations, there is potential for a small amount of standing water to be present at select intersections. However, this is not substantial enough to be a safety concern. No changes will be made to the contract. | Fred Schunke | 4 | 2022-02-01 11:00 | 2022-02-03 15:05
20220208 | 20220208043 | 43 | Granular Backfill Grade 2 | Is this material being used as the trench backfill shown in the detail on sheet 9? If so, is hauling out the existing material incidental to the pipe replacement or should there be a quantity for common excavation? | Hauling material is incidental to pipe construction as noted in section 522.5. The construction detail for culvert pipe construction will be updated via addendum to clarify where Granular Backfill Grade 2 pay limits are located. | Jill Fehrman | 1 | 2022-01-18 07:40 | 2022-01-26 08:32
20220208 | 20220208043 | 43 | Guardrail Grading | There is not any common excavation or cut quantity shown in the plans however the cross sections show a cut of the existing shoulders in the guardrail areas. If that material is not being cut out, could you verify the borrow and BAD 1 1/4" quantities reflect that? | The earthwork table incorrectly addressed these areas. Am addendum will be issued to Update the common/borrow quantities and clarify the construction detail. | Jill Fehrman | 2 | 2022-01-18 07:44 | 2022-01-26 08:39
20220208 | 20220208050 | 50 | Log removal | The plan indicates for a number of logs on the slopes to be removed. Under which item is this work to be paid? | The removal of the existing timber logs is incidental to bid items 203.0270 â€œRemoving Structure over Waterway Debris Capture System B-4-413â€ 1 EA & 206.1000 â€œExcavation for Structures Bridges B-4-124â€ 1 LS. | Mike Coleman | 1 | 2022-01-24 10:18 | 2022-01-24 15:49
20220208 | 20220208050 | 50 | Top of Pile Elevation? 16-inch Auger-Cast Piling | Special provision 23 C.2 paragraph 8 Casing to extend from top of pile elevation indicated on the plans to a minimum distance 2.5-ft below the bottom of proposed abutment. I do not see a "top of pile" EL indicated on the plans. Is the bottom of the abutments considered "top of pile" | The top of pile is dimensioned from the bottom of the abutment on the abutment sheets. This is dimensioned as 7â€™-6â€ from top of pile to bottom of abutment for the west abutment (except the wing piles which are dimensioned as 6â€ min.) and 2â€™-0â€ from top of pile to bottom of abutment for the east abutment. Per the special provisions the casing needs to extend 2.5-ft min below the bottom of the proposed abutment. This results in a min. casing length of 10â€™-0â€ for the west abutment (except the wings piles which would only need 3â€™-0â€ min. casing length) and 4â€™-6â€ min. casing length for the east abutment. | Fred Schunke | 2 | 2022-02-03 13:36 | 2022-02-03 16:03
20220208 | 20220208052 | 52 | Soils Report, Miscellaneous Quantities & Earthwork Tabulations | Can the department please provide the soils report for this project? Also, can excel versions of the miscellaneous quantities and earthwork tabulations be provided as well? | The requested files can be found at the following location: https://wisdot.box.com/s/r1v6t4jncrpvdz96hpa961jy34feat0f or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-01-17 09:24 | 2022-01-24 11:28
20220208 | 20220208052 | 52 | Geotechnical Report | Can the Department provide the Geotechnical Report for the project? |  |  | 2 | 2022-01-18 09:19
20220208 | 20220208052 | 52 | Barrier System Grading Shaping Finishing | Is there any common excavation or borrow material needed for this item? | Yes, some locations behind the proposed beam guard next to Lake Belle View will require supplemental fill material to level off steep slopes near the proposed posts. 175 CY of Borrow is anticipated to be included within the Barrier System Grading Shaping Finishing bid item at this location. | Mike Coleman | 3 | 2022-01-20 09:10 | 2022-01-24 15:27
20220208 | 20220208052 | 52 | Belleville Watermain | Does the installation of the water main in Belleville have to take place in 2023 or can it take place in 2022? | The water main work is anticipated to take place in conjunction with the other work operations on the southern half of the project in year two when the segment between Belleville and Paoli will be closed to through traffic, minimizing vehicle volumes. By sequencing the work this way, traffic traveling between Belleville and Madison will be able to proceed to Paoli unimpeded by any proposed project work on STH 69 in year one. This will also allow for the mill and overlay operations within the Village following water main placement to time out better with the other proposed paving work on the southern half of the project. | Mike Coleman | 4 | 2022-01-20 09:50 | 2022-01-24 16:15
20220208 | 20220208052 | 52 | Salvaged Topsoil | All typical sections have a note to "place 6" salvaged topsoil", but on page 19 of the plan it states 4" salvaged topsoil. Which one is it? Typically it would be 4". | 4â€ of Salvaged Topsoil may be used for the majority of the restoration areas throughout the project. However, in locations where the proposed roadway goes off-alignment and the old roadway is to be obliterated next to a farm field, a 12â€ depth of Salvaged Topsoil should be assumed in the area of the old roadbed to enhance the potential for future farming operations if the land was sold to the adjacent property owner through surplus land sales. This mainly affects the obliterated roadway segments in the following locations: â€¢ Frenchtown Road (west) â€¢ County A (west) â€¢ The section between roughly STA 231+00 and 236+25 LT â€¢ The section between roughly STA 363+00 and 369+50 RT â€¢ The section between roughly STA 398+00 and 401+00 RT â€¢ The section between roughly STA 408+00 and 422+00 LT These areas of deeper topsoil needs and clarifications to the proposed typical sections will be clarified in an upcoming addendum. | Mike Coleman | 5 | 2022-01-20 13:30 | 2022-01-24 15:51
20220208 | 20220208052 | 52 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | We will be updating the CPRC Class III pipes between 12 and 36 inches to Culvert Pipe Class III-B Nonmetal of the appropriate diameter. The associated apron endwalls will also be changed to Apron Endwalls for Culvert Pipe of the appropriate diameter instead of the concrete endwalls that were originally called out to accompany the CPRC items. These changes will be addressed through an upcoming addendum. | Mike Coleman | 6 | 2022-01-21 11:55 | 2022-01-25 07:45
20220208 | 20220208052 | 52 | EBS / EBS Fill Detail | What is the intent of the EBS fill detail on page 22 of the plan. Is EBS allowed outside the 2:1â€™s in areas where there is not EBS? Or is the detail assumed to be for the entire project? If that is the case then EBS is only allowed in the small triangles outside the 0.5:1â€™s? Also, the EBS fill detail is showing that within areas where EBS is excavated the fill material being brought back in basically needs to be granular all the way up to subgrade? Typically, on many other jobs granular material backfill would only go to original ground (top of EBS excavation) then the remainder of the fill could be common or borrow material. What is the reason for this? If this is what is wanted then areas where EBS is to be excavated and there is also common material within those areas that material cannot go directly into the fill after the EBS backfill material is placed? In some areas of EBS excavation there is in excess of 15,000 CY of cut material within those areas. | The intent of the detail is to reinforce expectations for how the EBS limits were defined and to delineate areas where backfill material would be considered part of the â€œroadway foundationâ€ and thus could not include organics, silts, clays, or marshy materials. As denoted in the detail, materials from EBS excavation would be allowable outside of the 0.5:1 slope from the bottom of the EBS excavation limits. Materials from EBS excavation can also be used as fill material elsewhere on the project as long as they are not being used in the roadway foundation. Note that the Roadway Foundation is defined as â€œthe area underlying the proposed roadway within the limits of assumed 1:1 slopes extending outward and downward from the subgrade shoulder pointsâ€ in a normal roadway cross section without EBS per the Roadway Foundation definition found in Standard Specification 101.3. The detail does not specify granular material for backfilling EBS sections â€“ itâ€™s simply reinforcing the fact that organics, silts, clays, or marsh materials are not allowed in this area and that the backfilling these marginal areas will be subject to the approval of the field engineer to ensure that poor materials arenâ€™t incorporated. Granular material and/or suitable common or borrow material from elsewhere on the project would be acceptable. | Fred Schunke | 7 | 2022-01-25 10:36 | 2022-01-27 14:25
20220208 | 20220208052 | 52 | EBS | Concerning the Earthwork Summary and EBS. We are questioning the amount of usalbe EBS that is listed in the tables. The majority of the fills in this project are shallow so we are wondering: if it is unsuitable for the roadway, would it not also be unsuitable for these shallow fills. Perhaps more should be figured as waste on the project. | Materials from EBS excavation are allowable outside of the 0.5:1 slope from the bottom of the EBS excavation limits per the construction detail included on page 22 of the plans. Materials from EBS excavation can also be used as fill material elsewhere on the project as long as they are not being used in the roadway foundation. Note that the Roadway Foundation is defined as â€œthe area underlying the proposed roadway within the limits of assumed 1:1 slopes extending outward and downward from the subgrade shoulder pointsâ€ in a normal roadway cross section without EBS per the Roadway Foundation definition found in Standard Specification 101.3. | Fred Schunke | 8 | 2022-01-25 15:29 | 2022-01-27 14:26
20220208 | 20220208052 | 52 | EBS / EBS Fill Detail #2 | This is a secondary question to the original. In your answer to the original question, you stated "The detail does not specify granular material for backfilling EBS sections â€“ itâ€™s simply reinforcing the fact that organics, silts, clays, or marsh materials are not allowed in this area and that the backfilling these marginal areas will be subject to the approval of the field engineer to ensure that poor materials arenâ€™t incorporated. Granular material and/or suitable common or borrow material from elsewhere on the project would be acceptable." We understand that organics and marsh materials would not be allowed for backfill. But then you state that silts, clays materials are not allowed in the EBS backfill area. Please answer this question, if material with silts and clays are not allowed then what material can be used to backfill the EBS? After job researching it is known that the typical common and borrow material around the area has clay and silt content. It is 100% suitable common and borrow material as the rest of the project will be built using this material but we canâ€™t use this material in the EBS fill area because it states that? Secondly, can it be assumed that material to backfill the EBS excavation ONLY would have to be granular? Then once EBS excavation is backfilled up to original ground, suitable common or borrow material (which may have silt and clay content) can be used to build the road? If this is the case then why isnâ€™t there a select borrow item (with a requirement) for backfilling the EBS excavations? The plan currently leaves a lot of open-ended statements with a lot of room for interpretation by both the contractor and DOT. Please clarify what is wanted so all contractors bidding know what is exactly wanted. | If potential Common or Borrow material is suitable to use within the roadway foundation per the standard specifications, it is suitable for backfilling EBS areas as well unless otherwise directed by the engineer. | Fred Schunke | 9 | 2022-01-31 10:45 | 2022-02-02 11:12
20220208 | 20220208052 | 52 | Salvaged Topsoil/Salvaged Topsoil Special | Per Addendum 1 and the notes on plan sheet 19, the pay item for Salvaged Topsoil is to include areas to be placed at 12" thickness or other areas as directed by the engineer. Typically specifying a salvaged topsoil depth thicker than the standard 4" depth includes an additional bid item, Salvaged Topsoil Special, with the appropriate quantity by the SY to perform the item that is 3 times more work than the standard Salvaged Topsoil bid item. Please add this additional bid item to account for the areas in which 12" of salvaged topsoil are required to be placed. | Prospective contractors should bid Salvaged Topsoil as presented in the plans. If placing the 12â€ sections are deemed more difficult or costly, factor in additional anticipated effort in the areas of roadway obliteration (as identified in the detail) to inform the bid price. | Fred Schunke | 10 | 2022-02-01 08:34 | 2022-02-02 11:14
20220208 | 20220208052 | 52 | Response to Question 10 | Please provide the quantities and plan view locations in which the 12" of Salvaged Topsoil is requested as incidental to the bid item of Salvaged Topsoil at a 4" depth. Looking at the cross sections in the station ranges provided, it looks like the old road core extends through the proposed ditch and into the new inslope of the roadway. Is it the intent to cover these areas with 12" of topsoil? As written the detail given on revised plan sheet 19 does not provide the information required to include the additional costs requested as incidental to the Salvaged Topsoil bid item. | The intent of the 12â€ topsoil section is to restore areas of ground that were previously developed for the existing roadway structure to a more farmable condition in sensitivity to potential future surplus land sales. Areas contained within the new ditch slopes (i.e., not available for farming) would not need to be restored with a deeper topsoil section. With that in mind, the expectation would be that the remaining area within the obliterated roadway subgrade shoulder points would likely benefit from the enhanced topsoil section to ensure that any remaining old roadway base aggregates were sufficiently covered. Upon examination of the existing typical sections and using the limits offered in the construction detail updates included with Addendum #1, a quick estimate of approximately 17,120 SF of Salvaged Topsoil using a 12â€ depth was derived. Note that the actual limits for the deeper topsoil layer will be directed by the field engineer and will be largely dependent on the exposed surface conditions left after completing removals in these obliterated areas. | Fred Schunke | 11 | 2022-02-02 12:32 | 2022-02-03 14:46
20220208 | 20220208052 | 52 | Response to Question 9 | Does the response to Question 9 indicate that if suitable common or borrow excavation that can be used to build a roadway foundation is not accepted by the engineer and the contractor is directed by the engineer to provide different material for backfill that this will be considered extra work? | As the contract documents state, materials for backfilling the EBS areas should be approved by the engineer prior to placement. If the contractor receives approval from the engineer to place roadway foundation materials in the specified EBS sections and the material is found to be unacceptable after placement and compaction in accordance with Standard Specification 207, then the removal and replacement of that material would be administered as specified in Standard Specification 205. If the contractor does not receive approval from the engineer prior to material placement in EBS sections and it fails to meet performance standards, the contractor will be responsible for correcting the subgrade at their cost. | Fred Schunke | 12 | 2022-02-02 12:36 | 2022-02-04 08:05
20220208 | 20220208052 | 52 | EBS Backfill | In the EW Summary it states "EBS excavation to be backfilled with suitable material from excavation elsewhere on the project or borrow material unless otherwise noted in the plans". In the aggregate summary under select crushed it shows 9185 ton for STH 69 EBS backfill. Is there a specified area that we are to use the select crushed quantity, or a certain type of condition in which we are to use select crushed. Normally in poor soil conditions EBS is backfilled entirely with select crushed. | The Select Crushed Material line item for EBS backfill is to account for the additional 1â€™ of EBS anticipated between STA 397+00 and 424+00 as identified on page 285 of the plans. Select Crushed Material was specified for EBS backfill in this instance since the undercut was anticipated to be small. Similarly, the undistributed line item for Select Crushed Material in the aggregate table accounts for other areas of EBS excavation outside of the more substantial zones of high EBS probability called out in the plans. Per the Geotechnical Report, these undistributed EBS areas were estimated to comprise approximately 5% of the roadway surface area and are anticipated to require a 1â€™ undercut below subgrade. | Fred Schunke | 13 | 2022-02-02 14:13 | 2022-02-03 14:47
20220208 | 20220208052 | 52 | EBS/EBS Backfill | Based on the soil borings and field observations, the majority of EBS included in the earthwork is classified as "organic" or "peat". Shouldn't this be classified and paid per standard specifications as Marsh Excavation along with typically a Select Borrow backfill item? Including this large quantity in the Common Excavation results in a blended unit price and puts the risk of overrun up to 25% of the EBS quantity on the contractor. Using the Marsh Excavation would be the appropriate pay item as this would represent the actual unit price to perform the work and would be paid for the actual quantity performed. Is seems that the language of "as directed by the engineer" is also putting risk on the contractor when this type of backfill is usually included as a Select Borrow bid item. Please revise the plans with the appropriate bid items of Marsh Excavation and Select Borrow as the use of EBS/Common Excavation and the notes regarding the backfill does not seem appropriate. | According to Standard Specification 205.2.5, Marsh Excavation is for excavation below the original ground level of marshes and swamps underlying proposed embankments. The presence of â€œorganicâ€ or â€œpeatâ€ material slated for removal does not inherently classify an area as a marsh or a swamp. The Geotechnical report prepared for this project and the soil borings helped identify the areas of higher organic soil content, but a need for the Marsh Excavation item was not identified. Note that the areas of higher organic soil content have been denoted on the plans and accounted for in the excavation quantities to help prospective contractors and the field engineering team understand where and to what degree the soils may prove more challenging. | Fred Schunke | 14 | 2022-02-02 16:50 | 2022-02-03 15:50
20220208 | 20220208052 | 52 | Response to Questions 14 | The response to this question and the definition given for Marsh Excavation in the Standard Specifications is exactly what is represented in the cross sections from Sta. 358 to Sta. 370, where approximately 50% of the EBS quantity is located. A majority of the other two large EBS locations also meet this definition. Why aren't these areas classified as Marsh Excavation as has been identified by the language in the Standard Specifications? | If the prospective contractor feels that there will be increased difficulty performing grading operations within this station range, they should use that to inform their proposed bid price. Note that the area called out in this question is currently an active farm field, so classifying it as a marsh or swamp in accordance with the standard specification definition doesnâ€™t seem appropriate. | Fred Schunke | 15 | 2022-02-04 09:50 | 2022-02-04 12:27
20220208 | 20220208052 | 52 | Response to Question 12 | If the engineer does not approve Common or Borrow Excavation that is suitable for foundation construction for use as EBS backfill prior to placement, what material is the contractor to provide for this backfill? Select Crushed material? If you are looking for a granular material that can be used in wet conditions that will most likely be encountered in these EBS locations, shouldn't a Select Borrow item be included in the contract? It seems that by using notes in detail drawings that the intent is to put the risk on the contractor to provide select materials that may not be encountered in the Common Excavation or required for use under the bid item of Borrow Excavation. | As stated in the response to Question #12 and as given in the contract documents, materials for backfilling the EBS areas should be approved by the engineer prior to placement. If wet or other challenging conditions are encountered, the contractor and field engineer are expected to collaborate on a strategy that will overcome the challenges. The appropriate solution will likely change on a case-by-case basis. If the contractor feels that the Borrow material they will need for this project should exhibit certain properties, then they should use that to inform their pre-bid research and their proposed bid price. | Fred Schunke | 16 | 2022-02-04 09:59 | 2022-02-04 12:28