## qandasearchletting_results
Date: | 2022-08-08
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20220809 | 20220809001 | 1 | Prosecution and Progress, Pavement Marking Operations | Is the intent for the pavement marking to be placed on the same day the pavement is placed or milled? Or is the temporary pavement marking required to be placed as the work zone moves during the day? | Our intent is to have the same day temporary pavement marking placed by the end of the work day. | Mike Coleman | 1 | 2022-07-27 14:04 | 2022-07-29 07:53
20220809 | 20220809001 | 1 | Special Provision #4 & #16 | Special Provision 4 states to place the first lift on the same day as milling to prevent a drop off. Special Provisions 16 requires distressed pavement milling and paving prior to the lower layer being placed. This places an additional activity between the milling and paving operation which ultimately slows down production along with the staffing and crew that will be â€œon callâ€ in case the distressed milling is needed. Is it practical to required distressed milling for a mill and fill and still obtain a quality product? | Distressed Milling will be removed via an upcoming addendum. | Mike Coleman | 2 | 2022-07-27 14:05 | 2022-08-03 12:18
20220809 | 20220809001 | 1 | Special Provision #4 | Special Provision 4 requires placing the first lift on the same day as milling. This road has an AADT of 370. Applying a same day mill and fill seem very restrictive. Will the department consider requiring paving within 72 hour after milling? | The existing typical section has 3â€ of asphalt over 7â€ or so of recycled asphalt millings. The proposed section has 3.5â€ of milling. Binder layer needs to be placed as soon as possible knowing that we are getting into the existing asphalt millings. Stability is unknown and exposing the millings to extended periods of traffic or construction truck use could cause additional repairs. The department will stand by requiring that the binder be placed within the same day of milling, bid accordingly. | Mike Coleman | 3 | 2022-07-27 14:06 | 2022-07-29 07:56
20220809 | 20220809001 | 1 | Temporary markings on lower layer | Good morning, there does not appear to be any temporary markings (as required under special provision #3) included for the lower layer. Will an addendum be issued to add these markings? Thank you. | The designers checked the AWP estimate to confirm there are three pavement marking items and their quantities are correct: 646.1020 Marking Line Epoxy 4-Inch (for centerline and edge lines) 646.4520 Marking Line Same Day Epoxy 4-Inch (for centerline) 649.0120 Temporary Marking Line Epoxy 4-Inch (for centerline) There are two lifts, 1.75â€ each. From the special provisions: The special provisions state in Pavement Marking Operations in Section 3: - Provide pavement marking of the centerline in all milled and paved areas the same day before opening the work zone to two-lane, two-way traffic. The special provision state in Section 4 Traffic: - Roadway paving shall be done with a single stage under flagging. Traffic shall not be allowed to drive on any surface that has tack coat applied to it. Place first lift on the same day as milling to prevent drop off on the pavement. The pavement marking plans state: - USE MARKING LINE SAME DAY EPOXY 4-INCH YELLOW DASHES AND SOLID LINES TO RE-ESTABLISH CENTERLINE ON NEW ASPHALT PAVEMENT. APPLY MARKING LINE EPOXY 4-INCH FOR CENTERLINE AFTER RUMBLE STRIPS INSTALLED. Our intent is for the contractor to do the following - Mill existing pavement, pave first lift in the same day. Keep traffic to one-lane (flagging operation) during milling and first lift paving to prevent the 3.5â€ drop off. No pavement marking needed on the milled surface since it will be paved before opening to two-way traffic. Use bid item Temporary Marking Line Epoxy 4-Inch to place centerline markings on the first lift. - Pave the second lift, use the bid item Marking Line Same Day Epoxy 4-Inch to place centerline markings. - Add centerline line rumble strips - Place final Marking Line Epoxy 4-Inch centerline and edge line markings The contractor could be referencing a need for temporary markings to be placed on the base after milling, but because of the drop off limitation and the unknown condition of the base (weâ€™re milling all of the existing pavement), we donâ€™t believe this additional quantity of temporary pavement marking is needed if they follow the special provisions. | Mike Coleman | 4 | 2022-08-01 07:08 | 2022-08-01 12:43
20220809 | 20220809003 | 3 | Article 10. Blanchards Cricket Frog | Article 10.1.b discusses the possibility of mowing vegetation. Usually, there is a mowing SPV for this work. Is mowing not anticipated or is the item missing? Also, Article 10.1.c states that Iowa County will seed these areas as shown in the Erosion Control Plan. Can you tell me where these areas are in the plan or are these areas not noted? | Mowing will be required before any ground disturbance per article 10.1.b, the mowing SPV was not included. An addendum will be issued to include the mowing SPV. In addition, Article 10.1.c states that Iowa County will seed these areas as shown in the Erosion Control Plan, the County will not be doing the seeding, it will be the contractor responsibility. This will also be included in the addendum. | Mike Coleman | 1 | 2022-07-11 11:35 | 2022-07-18 06:44
20220809 | 20220809003 | 3 | Article 21. Pipe Liner Verification | Article 21 states the requirements for item 520.9750.S, but the bid item is not listed on the project. Can you clarify or add the bid item? | The bid item 520.9750.s is intended to be used if the culvert pipe is under water or if the pipe size cannot be verified. For this project, the size was verified therefore this bid item 520.9750.S will not be needed. | Mike Coleman | 2 | 2022-07-11 11:45 | 2022-07-14 06:37
20220809 | 20220809003 | 3 | Special Provision #26 | Is this just when work in town is be completed or throughout the duration of the project? How quickly must the sweeping be completed after being directed by the engineer? | The intention with adding street sweeping as a special provision is that we would use it only in the Village of Linden during the curb ramp replacements. Included to make sure we can control dust and that we keep the travel ways clean. Street Sweeping must occur within 24 hours after being directed by the engineer. | Mike Coleman | 3 | 2022-08-03 10:09 | 2022-08-04 08:30
20220809 | 20220809005 | 5 | Shaping Shoulders vs. Prepare Foundation for Asphaltic Shoulders: | Please review note *** on Finished Typical sections and Misc. Quantity sheet 106. Which Pay Item will be paid to remove aggregate shoulder materials to facilitate widening the roadway for placement of CIR and HMA Pavement? | An addendum was issued to clarify | Mike Coleman | 1 | 2022-07-28 15:27 | 2022-08-04 11:48
20220809 | 20220809005 | 5 | Shaping Shoulders/Prep Foundation for Asphaltic Shoulders: | Is it the intent of the shaping shoulders/prep foundation for asphaltic shoulders item to haul the removed aggregate shoulder materials off of the project for disposal? In most places only 2â€™ of existing aggregate shoulder needs to be removed to facilitate placement of CIR material to a 17â€™ lane width. Would it be acceptable to remove 2â€™ instead of 3â€™ of material in these areas? | The intent is to remove and haul the existing aggregate shoulder material off-site. Removal of the 3 feet of existing shoulder material is required. | Mike Coleman | 2 | 2022-07-28 15:28 | 2022-08-04 10:49
20220809 | 20220809005 | 5 | CIR Slopes: | Existing pavement is sloped to a uniform 2% across the lane and 3â€™ paved shoulders. Placing 4â€ of CIR material with a 12â€™ lane at 2% and a 5â€™ shoulder at 6% will be very difficult and hard on equipment. Ride quality will suffer as a result. Can the section be changed to place CIR 17â€™ wide at a uniform 2% slope? | This project has been withdrawn from the letting. | Mike Coleman | 3 | 2022-07-28 15:29 | 2022-08-08 08:07
20220809 | 20220809010 | 10 | Salvage and Reinstall Signs | Under which bid item are the signs that are being salvaged and reinstalled paid for? | An addendum will be issued to clarify. | Mike Coleman | 1 | 2022-07-12 10:04 | 2022-07-14 06:26
20220809 | 20220809010 | 10 | High Friction Surface Treatment | Have you any details on the placement of the HFST, and will it need to be done in two stages to allow for local traffic? |  |  | 2 | 2022-08-03 09:56
20220809 | 20220809012 | 12 | MGS Quantities | Please confirm whether the quantities for MGS 3 and MGS Thrie Beam Transition are correct or backwards. | The MGS 3 and MGS Thrie Beam Transition are switched. An addendum will revise the quantities as 200 LF of MGS Guardrail 3 and 79 LF of MGS Thrie Beam Transition. | Mike Coleman | 1 | 2022-07-13 09:10 | 2022-07-14 06:25
20220809 | 20220809012 | 12 | Scheduling | From my understanding of the schedule, the project will need to be heated and housed during the cold weather months with the project being constructed in halves. What is the purpose of the project being constructed during the cold weather months? | The project requires the bridge to be constructed during the winter and early spring to avoid major disruptions to Memorial Day weekend and the summer seasonal traffic along USH 41. | Mike Coleman | 2 | 2022-07-15 11:57 | 2022-07-18 09:51
20220809 | 20220809012 | 12 | Bar Couplers #5, Item 62 | Please look at the bid quantity for the #5 bar couplers, it appears the quantity was doubled. There should be approximately 579 transverse deck bars that require couplers. | Agreed that the quantity for Bar Couplers #5 is in error. An addendum will be issued. | Mike Coleman | 3 | 2022-07-26 07:40 | 2022-07-26 08:53
20220809 | 20220809012 | 12 | Winter Construction Concerns | Has the Department analyzed the availability of asphalt during winter months? Has the Department considered the impacts of recoating the steel beams in winter. Does the Department anticipate work during the months of December/January/February/March? - no weather days are allowed during those months so what will constitute and extension for severe weather. Can the design schedule be provided for the project? | The item for asphaltic mixture for extreme conditions was included in the contract for anticipated approach paving work to be done in stage 2 during the early part of March 2023. Means and methods for weather protection may be required for the recoating of steel beams and the concrete masonry bridges item during winter. The Department anticipates work occurring during the months of December, January, February, and March. Language was included in the special provisions regarding winter work and low production rates were assumed as extensions for severe weather will not be granted for those months per the standard specifications. Anticipated severe weather days for April and May will be granted per the anticipated adverse weather days table. The design schedule can be found at the following location: https://wisdot.box.com/s/qojkobrwi3e12rb0m16vf9yx4rbjwl11 or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2022-07-27 13:37 | 2022-07-28 07:57
20220809 | 20220809012 | 12 | Stage 2 Contractor Falsework Requirement | Stage 2 removal limits depict a contractor designed support of the stage line overhang. Has the designer considered any alternatives to what can effectively be done to support the required loads given the stream restrictions and project schedule? Can the Department provide the loads in which the contractor is required to design for? | Temporary supports could be constructed that extend from the existing girders on each side of the overhang to support the stage line overhang. This is similar to what may be done to support a typical deck edge overhang during construction. Other support alternatives may also be possible. The Department will not provide loads for design. The loads should be generated by the contractor as part of the temporary support SPV provision. | Mike Coleman | 5 | 2022-07-27 13:52 | 2022-08-03 09:03
20220809 | 20220809012 | 12 | As Built: Shear Studs or Shear Angles | The as built plans online show contractor option of shear angles or shear studs. Does the Department know which option was utilized during original construction? | The contractor will need to assume either option of shear studs or shear angles were used during the original construction shown in the 1971 as-built. | Mike Coleman | 6 | 2022-08-01 12:14 | 2022-08-02 06:16
20220809 | 20220809013 | 13 | Casting Type Z - MH Opening and Adjustment Rings | Please verify it is ok to have a standard round 27" (ID) opening with round 27" (ID) adjustment rings below these type Z castings. This would be a cost savings measure as the MH fabricator will not have to make a special MH and rings for this Type Z Casting with the flat front frame. Thanks. | The proposed standard round 27" (ID) opening with round 27" (ID) adjustment rings below the type Z castings would not be allowed as there would be a â€œholeâ€ off of the front face of the casting. A link to the sketch of the 27â€ adjustment rings can be found at the following location: https://wisdot.box.com/s/a5ko0xkny29tczvis9zs9f9zhw7if63d or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-07-13 10:42 | 2022-07-21 06:39
20220809 | 20220809013 | 13 | 36" SCP Thickness | 36â€ is listed twice and I cannot find a thickness specified. 238 Storm Sewer Pipe Class III -A 36-inch 240 Storm Sewer Pipe Class III -B 36-inch | There are two items for the 36-inch storm sewer because we are dealing with two different fill heights. Manufacture needs to come from the Product Approval List (PAL). See standard spec 608 for the allowable materials and the AASHTO Standards the pipe needs to conform to. | Mike Coleman | 2 | 2022-07-25 11:11 | 2022-07-26 08:12
20220809 | 20220809013 | 13 | Nitrile Gaskets | Is there any information as to the actual location of the contaminated soils on this project. I am trying to confirm how many of the nitrile gaskets that are called for are for pipe or fittings or valves. According to the chart in the plan sheets, the quantities required for the specific listed locations do not equal the total quantity required. | The gaskets were meant to be undistributed in the event contaminated soils are encountered near 2219 South Avenue (Sta. 52+75 â€“ 54+75, LT). The Phase 2.5 hazmat report states that excavation from South Avenue construction isnâ€™t expected to impact the contaminated soils as they have been capped, however, there is always a potential for them to exist. The City of La Crosse typically likes to have an undistributed quantity of Nitrile gaskets in the event contaminated soils are suspected during the project. The actual number of Nitrile gaskets required will be determined in the field by the City of La Crosse inspector. | Mike Coleman | 3 | 2022-07-29 11:30 | 2022-08-03 06:42
20220809 | 20220809013 | 13 | Stage 1 Removing Buildings Daytime Weekday Hours | Please verify if the Stage 1 Removing Buildings scope can be done during daytime weekday hours? The advertised landfill operation hours are as follows...Summer Hours Mon-Fri: 6:30 AM to 4:30 PM April through October. Winter Hours Mon-Fri: 7:00 AM - 4:00 PM November through March. | The Stage 1 Removing Buildings scope can be completed during daytime weekday hours. The Stage 1 Traffic Control Note 1 on page 199 of the plan states, â€œStage 1 work within the roadway shall be completed with a detour during weekend and night time full closures, (see detour plan for more information). Building removals and site clearances to be completed during daytime hours.â€ | Mike Coleman | 4 | 2022-08-01 13:30 | 2022-08-02 08:30
20220809 | 20220809013 | 13 | Soil Boring Information | Can you please provide the soil boring information for this project? Thanks. | The soils report can be found at the following location: https://wisdot.box.com/s/a5ko0xkny29tczvis9zs9f9zhw7if63d or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 5 | 2022-08-01 14:41 | 2022-08-02 08:34
20220809 | 20220809013 | 13 | Square Yards on Project | After measuring everything up, I am seeing that the SY in Misc. Quantities match up if you measure to face of curb and not the flange? Is there gonna be an addendum coming out to change the quantities | An emergency addendum will be issued this morning to correct the quantities. | Mike Coleman | 7 | 2022-08-02 10:46 | 2022-08-05 07:28
20220809 | 20220809013 | 13 | Removing Buildings and Site Clearance on Sheet 71 | Please verify what Proposal Line Number includes the three buildings to be removed on sheet 71 south of USH 14. I believe they are in Parcel 142. | The 3 buildings shown on sheet 71 have been removed, with seeding and erosion mat over it. | Mike Coleman | 8 | 2022-08-02 16:12 | 2022-08-05 07:29
20220809 | 20220809013 | 13 | Building Demo Asbestos/Hazardous Materials | Has there been any testing done for Asbestos or other hazardous materials in the buildings to be removed? If not, is this incidental to the Removing Building Items? | No testing for asbestos or hazardous materials have been completed. This will be incidental to the Removing Buildings items. | Mike Coleman | 9 | 2022-08-03 06:34 | 2022-08-05 07:32
20220809 | 20220809014 | 14 | November 18, 2022 Completion for Exit/Entrance Ramps | In the Specials it says: Exit Ramp to Hudson SWEF -Complete construction operations at the Hudson SWEF exit ramp taper prior to November 18, 2022. And Entrance Ramp to Hudson SWEF - Complete construction operations at the Hudson SWEF entrance ramp taper prior to November 18, 2022. Do not reopen until completing the ramp paving and shouldering through the ramp entrance gore. What work is this referencing? Stage 1 work - shoulder work? Stage 2B - New Concrete Ramps? When does DOT expect to issue the Notice to Proceed for this Project? | The work being referenced in the specials is the SWEFâ€™s new concrete ramps in stage 2B (STA 325+96R â€“ Station 340+75R (approx.) and 385+50R (approx.) â€“ 394+29R). The Notice to Proceed will depend on when the contract is executed and the winning bidderâ€™s proposed start date per Article 3, â€˜Prosecution and Progressâ€™ in the contract special provisions. The Department will work as quickly as possible with the contractor after award to get the Notice to Proceed issued. | Mike Coleman | 1 | 2022-07-19 11:30 | 2022-07-20 07:41
20220809 | 20220809014 | 14 | Roof | Vented or non-vented nail base? Specs call out both. Specs call out vented soffit. Would not have if the nail base is not vented. | Section 07 22 00 Nail Base Insulation: A non-vented system is specified. The OSB or CDX sheathing needs to be fire rated. The completed system can be constructed of multiple layers of components in the field if needed. Section 07 46 00 Prefinished Metal Soffit Panels: The specified soffit panels shall be flush metal â€œnon-ventedâ€ panels in lieu of vented panels as identified. | Mike Coleman | 2 | 2022-07-28 05:45 | 2022-07-29 07:59
20220809 | 20220809014 | 14 | SWEF Entrance and Exit Ramp Timeframes | 1) What is the intent/reasoning behind having the entrance/exit ramps through the gores complete by Nov. 18, 2022? Given the bid let timing, award, NTP, fall weather, etc. this is a tight timeframe. 2) Article 3 calls out the Nov. 18, 2022 deadline for the entrance/exit ramps through the gores. However, Article 5 'Traffic", calls that the entrance/exit ramp taper can be completed during off-peak traffic periods or during Stage 3. Stage 3 is the first stage of the 2023 season and would be in conflict with Article 3 date. Please clarify/resolve the conflicting language. | 1. The purpose of this requirement is to provide a pavement surface at both the exit and entrance ramp locations (by Nov 18, 2022) that can be plowed/maintained over the winter to avoid (or at least minimize) snow/dirt/debris from the construction area encroaching onto the adjacent interstate roadway resulting in a safety concern. 2. The phrase â€œduring Stage 3â€ should be removed from the Hudson SWEF site construction section in Article 5. The section should instead read, â€œConstruction of the exit and entrance ramp tapers can be completed during off-peak traffic periods or when EB IH 94 traffic is shifted onto temporary pavement in the median. An addendum will be issued | Mike Coleman | 3 | 2022-07-28 10:48 | 2022-07-29 08:00
20220809 | 20220809014 | 14 | Blocking | Sheet 197 (A409) Detail 1 â€œEave Low Sideâ€ shows no reference to four layers of wood blocking. Sheet 199 (A411) Detail 4 â€œLow Side Roofâ€ shows the four layers of blocking. As does the other details on the page. Donâ€™t see a call out for these three details. Is this blocking needed? | Yes, the blocking that is shown on the large details and not on the small-scale drawings is needed. The project team will add it to the small-scale drawing on a revised plan sheets in an upcoming plan addenda. | Mike Coleman | 4 | 2022-07-28 11:42 | 2022-07-29 07:52
20220809 | 20220809014 | 14 | SWEF Entrance & Exit Ramp Timeframes #2 | As the previous questions have already laid out there is a lot of work that would need to occur for these ramp tapers and by the time the contract is executed, etc. its not going to happen. This work can happen in 2023 when traffic is shifted onto temp pavement as long as the contractor leaves existing entrance and exit ramps in place over winter, correct? | The proposal would be acceptable alternative to what is proposed in the contract documents. Revised requirements allowing for this option will be included in an upcoming contract addenda. | Mike Coleman | 5 | 2022-08-01 15:32 | 2022-08-04 12:52
20220809 | 20220809014 | 14 | Communications Tower Foundation | I see on sheet 142 (C-102) where it calls out a 44.5x44.5 tower foundation. If you go to sheet 154 (T-502) detail A, they donâ€™t show a â€œtower foundationâ€. Just says â€œfinished gradeâ€. The tower itself appears to have round sono tubes (3) to some depth to support it. What is required for the foundation, sono tubes or a 44.5' square on concrete? Please provide more details. | Keynote B on C-102 reads â€œTower Foundation (44â€™-6â€ x 44â€™-6â€ Pad shown); Verify with final tower and foundation plansâ€. The tower and tower foundation are to be designed by a tower manufacturer selected by the Bidder. The designs need to meet the requirements outlined in the specification (Section 33 38 00). Foundation size and details will be dictated by that design. | Mike Coleman | 6 | 2022-08-02 11:48 | 2022-08-03 06:44
20220809 | 20220809014 | 14 | HVAC | â€œThere are multiple places in division 23 that are referencing a specification section 23 09 14. This section does not exist, please provide this section or modify the existing sections as necessary. Two examples are pages 451 and 487 were products are referenced back to the 23 09 14 section.â€ | The sections will be modified with revised language to remove refence to this section (23 09 14). The revised language will be included with an upcoming project addenda. | Mike Coleman | 7 | 2022-08-02 18:25 | 2022-08-04 14:49
20220809 | 20220809014 | 14 | Item 334 - Geotextile Type DF Schedule B | It appears the Item 334 - Geotextile Type DF Schedule B (SY) is for under the Communications Tower for a weed barrier, which is in an area that is included the Lump Sum area for item: Special 300. Communications Tower. Geotextile Type DF Schedule B will be paid under what pay item - 334 or 528? | The Geotextile Type DF Schedule B will be paid under 334. | Mike Coleman | 8 | 2022-08-03 15:20 | 2022-08-04 11:46
20220809 | 20220809014 | 14 | 4MT - Stage 1 @ 1" | The 4MT is shown to be used within the mill and overlay of the outside shoulder rumble strip at 1". We are not allowed to place 4MT with this thickness per specifications. Please confirm if they quantity will be switched to asphaltic surface and the corresponding 4MT quantity get reduced. | The 4MT quantity for the mill and overlay of the outside shoulder will be moved to Asphaltic Surface (item will be added) and the 4MT quantity will be reduced. This will be addressed with an upcoming addendum. | Mike Coleman | 9 | 2022-08-03 16:23 | 2022-08-04 12:12
20220809 | 20220809014 | 14 | Schedule | With the late letting and the need to schedule the building construction, will an alternative schedule of construction be allow with engineer (Department) approval |  |  | 10 | 2022-08-05 10:08