## qandasearchletting_results
Date: | 2022-10-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20221011 | 20221011001 | 1 | Design Schedule | Can the Design Schedule please be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/zdnqbb0b27tutufrgh85gsnewknj7g2h or can be accessed on the HCCI October bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-09-08 07:57 | 2022-09-13 11:19
20221011 | 20221011003 | 3 | Drainage Tables in Excel Format | Can the drainage tables for storm sewer pipe & structures be provided in excel format? | The requested drainage tables in four Excel files, 030205_mq_ss_1229-04-71/72/73/77, located in the following Box folder: https://wisdot.box.com/s/f4wwaf04rsjmqcx76tlx3ftoz7waghdk | Fred Schunke | 1 | 2022-09-07 21:46 | 2022-09-15 13:25
20221011 | 20221011003 | 3 | Existing Retaining Walls R-414 & 415 | Can the approved shop drawings be provided for the portion already installed MSE wall R-40-414 & R-40-415 be provided? | Please access the stateâ€™s Highway Structures Information System (HSI) for this information (https://trust.dot.state.wi.us/hsi/HSIController). It includes as-built plans and inspection reports for the existing structures along the corridor. | Mike Coleman | 3 | 2022-09-07 21:49 | 2022-09-19 11:48
20221011 | 20221011003 | 3 | Design Schedule | Can the DOT design schedule be provided for the project. | The design has been updated. The new one can be downloaded from the previous link. The latest design schedule has been uploaded to the following Box Folder: https://wisdot.box.com/s/f4wwaf04rsjmqcx76tlx3ftoz7waghdk | Fred Schunke | 4 | 2022-09-12 09:52 | 2022-09-16 12:13
20221011 | 20221011003 | 3 | UPRR Special Conditions | Can you post the UPRR special conditions noted in Article 1? | The UPRR Special Conditions can be found at the following location: https://wisdot.box.com/s/f4wwaf04rsjmqcx76tlx3ftoz7waghdk or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 5 | 2022-09-12 11:09 | 2022-09-13 10:54
20221011 | 20221011003 | 3 | Concrete Barrier | Is the 4'-0" concrete pad below the S-42 style barrier paid for under the barrier or the pcc concrete pavement that is adjacent? | The pad below the barrier will be paid with the adjacent concrete pavement item. See note 14 on the concrete barrier construction detail (sheet 75). | Fred Schunke | 6 | 2022-09-13 08:25 | 2022-09-15 13:26
20221011 | 20221011003 | 3 | Marking Line Grooved Tape 8" | Good morning, Line item #0912 calls for regular 8"(non-contrast) permanent tape while Line Item #0906 calls for grooved contrast 4" permanent tape. Is this correct or will there be a change issued to match grooved tape items on this project? Thank you | The 8â€ grooved permanent tape will be changed to 8â€ grooved contrast permanent tape via Addendum #1. | Fred Schunke | 7 | 2022-09-14 07:31 | 2022-09-16 12:18
20221011 | 20221011003 | 3 | Noise barrier N-40-103 retaining panels | Plan sheet 2785 indicates that bottom panels on this structure shall be earth retaining. Do these panels need to be sound absorptive on the exposed area, or are these intended to be solid concrete with no absorptive material? | Earth retaining panels for the noise barrier wall may be solid concrete without sound absorptive materials. Aesthetic treatments on the exposed faces of these panels to be as shown on the plans. | Fred Schunke | 8 | 2022-09-14 09:57 | 2022-09-16 12:18
20221011 | 20221011003 | 3 | Soil Borings | Can you provide the Soil Borings for the project? | The Geotech Reports can be found at the following location: https://wisdot.box.com/s/f4wwaf04rsjmqcx76tlx3ftoz7waghdk or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 9 | 2022-09-15 14:21 | 2022-09-21 13:04
20221011 | 20221011003 | 3 | Noise barrier N-40-102 | Plan sheet 2774 shows special post spacings at 24' instead of the usual 15'. Would WisDOT accept two spacings at 12' instead of one at 15'? Noise wall suppliers indicate that manufacturing set-up and panel designs cannot be made longer than 15'. | The Departmentâ€™s approved products list for noise barrier walls includes multiple suppliers whose online information states that 24â€™ long panels are available: Durisol NB24; JBM Solutions, Inc. JBM75; and Faddis Concrete Products AcoustaCrete. The 24â€™ post spacings identified on the plans were located to avoid specific conflicts. - At the sign structure near noise barrier wall Sta. 2098+75, the noise barrier wall drilled shafts must be placed as shown to avoid capacity reductions of the sign structure shafts, as well as the noise barrier wall shafts due to close proximity to each other. Two additional sets of 24â€™ post spacings were assumed north and south of the sign structure as indicated by the alignment (PI-9 through PI-14); those could be revised to 12â€™ post spacing, but that will need to be coordinated with the lighting foundation proposed at approximate wall Sta. 2099+00. - At the existing sanitary sewer line crossing the noise barrier wall at approximately Sta. 2104+60, the 24â€™ post spacing was set to avoid this existing utility. The 24â€™ post spacing to the south could be revised to 12â€™ post spacings. Alternatively, the post spacings along the noise barrier wall in this vicinity may be revised for shorter spacings as long as a 5â€™ minimum distance from the posts to the existing sanitary sewer line is provided. The contractor is responsible for identifying and avoiding conflicts and for revising post layout as needed. The layout shown on the plans is one proposed and feasible option using available panel lengths from multiple suppliers on the Departmentâ€™s approved products list. | Mike Coleman | 10 | 2022-09-15 15:44 | 2022-09-21 12:21
20221011 | 20221011003 | 3 | MSE wall R-40-412 & R-40-413 | Can the approved shop drawings be provided for the portion already installed MSE wall R-40-412 & R-40-413 be provided? | Please access the stateâ€™s Highway Structures Information System (HSI) for this information (https://trust.dot.state.wi.us/hsi/HSIController). It includes as-built plans and inspection reports for the existing structures along the corridor. | Mike Coleman | 11 | 2022-09-17 16:58 | 2022-09-20 07:08
20221011 | 20221011003 | 3 | R-40-649 and for wing walls at B-40-921 | Provide the friction angle of the foundation materials for R-40-649 and for wing walls at B-40-921 to perform Factor of Safety against sliding calculations Provide friction angle and total unit weight of retained fill for wing walls at B-40-921 | Refer to Appendix C â€œDesign Parametersâ€ sections of the geotechnical reports for R-40-649 and B-40-921, (https://wisdot.box.com/s/f4wwaf04rsjmqcx76tlx3ftoz7waghdk or via the HCCI October bid letting page under Supplemental Information), for friction angle of the foundation materials. Refer to sheets 2629 and 2982 of the contract plans for friction angle and total unit weight of the retained fill. | Mike Coleman | 12 | 2022-09-17 17:01 | 2022-09-22 06:42
20221011 | 20221011003 | 3 | Controller | The specs on page 282 of 460 in the middle of the page note "Provide Siemens M62 controller, but many of the intersection plans notes in the lower right corner (starting with page 1070) list controller type: ECONOLITE. Can you please confirm which controllers are to be used in the contractor furnished traffic signal control cabinets? | : Use a Siemens M62 controller for the city of Glendale traffic signals at the Port Washington Rd and Bender Rd intersection and the Port Washington Rd and Clovernook Ln intersection. The controller for the Good Hope Road and Port Washington Rd intersection will be provided by Milwaukee County. Controllers at the remaining signalized intersections will be provided by the State. | Mike Coleman | 13 | 2022-09-20 14:53 | 2022-09-23 07:13
20221011 | 20221011003 | 3 | R-40-641 Existing Details | Provide details for permanent sheet pile sections used in existing portion of R-40-641 or update CIP coping detail on plan sheet 21 of the R-40-641 structure plan to show the overall width of the new coping. | The top width of the cast-in-place concrete coping at the existing sheet piling wall segments is intended to be 5â€™-0â€ as shown on the Typical Sections on sheets 8 and 9. The 2017 design plans for walls R-40-641 and 642 state the required sheet piling properties (minimum section modulus and minimum depth). However, the specific sheet piling sizes installed with that construction are not captured on the as-built plans (which are not available on HSI). Field adjustments to coping are expected to get the proposed work to fit conditions in the field. The as-builts for R-40-641 and R-40-642 can be found at the following location: https://wisdot.box.com/s/f4wwaf04rsjmqcx76tlx3ftoz7waghdk or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 14 | 2022-09-20 15:24 | 2022-09-26 08:28
20221011 | 20221011003 | 3 | Special 0960. Contractor Staging Area | If the contractor doesn't need the specified "Contractor Staging Area" providing in the plans, does the contractor need to complete all the requirements within the Special 0960. Contractor Staging Area item? | Completion of all requirements for the Contractor Staging Area, Item SPV.0060.0960 is required. | Mike Coleman | 15 | 2022-09-21 10:46 | 2022-09-22 14:16
20221011 | 20221011003 | 3 | Special 0960. Contractor Staging Area | If this Contractor Staging Area is for the contractor, shouldn't the contractor determine how much security is required? The fence and lighting should be determined by the contractor if that is needed or not and shouldn't be required under this item. These items may not be required due to the type of material staged within this area. These items should be determined by the contractor based on their needs. | Fencing and lighting items included in the plans for the contractor staging area are required. These items are intended for delineation and safety regarding public use of the park and ride. | Mike Coleman | 16 | 2022-09-21 10:56 | 2022-09-22 14:16
20221011 | 20221011009 | 9 | Covering Type I & Type II Signs | Would you please check the Unit description and estimated quantities for Line item 170 and 172-Covering Type I & Type II Signs. The units are listed in one place as Days and as Each in another. The estimated quantities also seem to be a great deal more than identified on the plan. | The covering sign items in the estimate should be revised to the following: Covering Signs Type I â€“ 2 EACH Covering Signs Type II â€“ 7 EACH An addendum will be submitted to make this revision. | Mike Coleman | 1 | 2022-09-20 14:00 | 2022-09-22 14:14
20221011 | 20221011011 | 11 | Lower Lift HMA type | With the lower lift meeting the minimum thickness requirements for a level 4 mix. Can it be changed to a 4MT meeting the PWL requirementswith the same AC type? | Upon confirming with WisDOT, who prepared the pavement design report for this project, the lower level will be revised to 4MT58-34V. The upper layer shall remain at 5MT58-34V. We will be preparing an addenda next week for the plan and quantity changes associated with this revision. | Mike Coleman | 1 | 2022-09-19 09:43 | 2022-09-26 08:29
20221011 | 20221011011 | 11 | HMA for Culvert patches | Should the mix for culvert patches be Asphaltic Surface instead of PWL? The culverts have to be completed prior to the milling and there is no way to have a test strip put on the project prior to the culverts. | On Page 18 of the plan set (Culvert Pipe Replacement Detail) it shows paving with Asphaltic Surface in the culvert replacement areas prior to mainline milling. After the mainline pavement is milled it will be paved with HMA as part of the regular paving operation. A quantity of 4,125 tons has been included in this project, partially to account for the culvert replacement areas. The MQ table titled â€œPWL Mixture Use Tableâ€ is incorrect and will be updated in a forthcoming Addenda. | Mike Coleman | 2 | 2022-09-21 14:14 | 2022-09-26 08:22
20221011 | 20221011011 | 11 | Removing Distressed Pavement Milling | Will this be marked out prior to mainline milling operations? It would be beneficial to have the areas marked in advance in order to be able to plan accordingly and do the removal in one operation instead of 2. | Regarding the item â€œRemoving Distressed Pavement Millingâ€, marking the areas in advance will be an item that the engineer in the field will complete ahead of milling operations. The construction engineer will mark out the areas ahead of the mainline milling operation and the check the marked areas to verify if Removing Distressed Pavement Milling will be required after the large mainline milling machine passes, but before the smaller milling machine passes for the shoulders. A note to the engineer in the field will be added and the Prosecution and Progress article will be revised to reflect this. We are currently working on an Addenda for this project and will include these items. | Mike Coleman | 3 | 2022-09-21 14:22 | 2022-09-26 08:31
20221011 | 20221011009 | 9 | Bird Deterrent System | Does this just need to be installed so birds cannot nest in the joint to be repaired? There isn't any other work getting done on the box so would the entire box need to be netted? | The entire box should be netted to prevent swallows from using the structure at all. | Mike Coleman | 2 | 2022-09-21 16:30 | 2022-09-30 06:55
20221011 | 20221011009 | 9 | Removing Structures at 239+37 and 239-47 | Will these be paid out under the Removing Structures items? They are also listed under the removing small culvert item. | Culverts at 239+37 and 239-47 should be paid only under the Removing Structures bid item. The new quantity for removing small pipe culverts should be 9 EACH instead of 11 EACH. An addendum will be completed to make this change. | Mike Coleman | 3 | 2022-09-21 16:32 | 2022-09-22 14:13
20221011 | 20221011009 | 9 | MGS Guardrail 3L | Is there a detail for how this is getting installed? Are any CRT posts getting installed? | Figure post spacing thru the areas labeled with 3L with the posts removed over the structure. Place CRT posts as shown on SDD drawings for EAT and for a distance of 12.5â€™ on either side of the 3L segments. The 3L bid price should reflect the change in posts required adjacent to the 3L section. C-27-1002 â€“ 20 CRT posts will be required plus those required for EAT. 3K is required in all quadrants here so CRT posts will be required 12â€™6â€ at 3â€™3â€ spacing on either side of the structure. (5 on each side of the structure, 10 per traveling direction, which means 20 per structure to cover NB & SB) plus those required for EAT. C-27-1003 â€“ 16 CRT posts will be required plus those required for EAT. 3K is required in on NB so CRT posts will be required 12â€™6â€ at 3â€™3â€ spacing on either side of the structure. (5 on each side of the structure, 10 total for NB) for SB we will need 3 on each side of structure, so 6 total for SB. | Mike Coleman | 4 | 2022-09-21 16:38 | 2022-09-22 08:28
20221011 | 20221011003 | 3 | CAD Files | Looking through the CAD files I see no design files for the 72 project (UPRR Section) except for alignments. No surface files, no edge lines. Would like the permanent railroad and temporary access road files. | The UPRR design files can be found at the following location: https://wisdot.box.com/s/lekbbbtu2690b0in1xdnwjrsxck9zd4d or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 17 | 2022-09-22 10:06 | 2022-09-27 06:50
20221011 | 20221011003 | 3 | UPRR Bridge is Unconstructable & Not safe | The UPRR Bridge is unconstructable and extremely not safe per the current staging within the plans. Port Washington (PW) Road (from Karl Campus to Bentwood Lane) needs to be closed to construct the East Abutment, Pier 3, the Structural Steel for spans 3 & 4 and demo of the existing UPRR. If PW is not closed there is no room to assemble the structural steel, stage and set spans over PW and NB IH-43 Lanes. The current provide staging area on Karl Campus Road is on the wrong side of the existing UPRR Bridge for the structural steel work and any other materials stored there must cross live traffic to get installed (extremely unsafe for the traveling public and workers). Jean Nicolet (JN) Road is closed on the west side which is needed to construct the west side of the UPRR Bridge. If PW can't be closed for the entire construction duration of the UPRR and Demo (which is required to meet the current schedule), at least allow alternating sideroad closures. PW or JN, not at the same time | Regarding the construction staging area, please recognize that some of the residential properties on the east side of N Port Washington Road and north of the existing UPRR bridge have been acquired as relocations under plat 1229-04-21/24 and are available for construction staging for the east half of UPRR bridge construction and demolition activities. This work is to be coordinated with the proposed roadway construction of N Port Washington Road during this stage. Please also note that the contract Special Provisions, subject to conditions written therein, do allow for night-time closures of N. Port Washington Road. Compensation for local road closures is included in item 643.5000 - Traffic Control. Karl Campus Drive is intended to be used as access to remove the existing UPRR tracks. Please refer to Article 52. Given that N Port Washington Road will be operating as bidirectional single lanes, the contractor will be limited to right-in/right-out access to the work zone near the east abutment from N Port Washington Road. Revisions to the Special Provisions will be made via Addendum #2 to reflect this. The night-time closures and right of way acquisitions north east of the existing UPRR bridge provides sufficient space to build the new east abutment, set new spans 3 and 4 and demo the existing UPRR bridge. Regarding pier 3, addendum #2 will include construction of additional temporary pavement to shift traffic on N Port Washington Road east along the existing east abutment to allow for additional space to build the new pier 3. | Mike Coleman | 18 | 2022-09-22 13:52 | 2022-09-29 06:22
20221011 | 20221011003 | 3 | B-40-1026, B-40-1027, B-40-1028 STAGING AND REMOVAL | Why is the temporary diversion typical section show a 20' width on pages 104 & 105? The permanent stream under the new bridges is only 6' between the slope toes. There is not enough room for a 20' temp channel. | The temporary diversion channel typical section width is based on the Q10 flow rate of 694 cfs, and not having adverse impacts upstream. The permanent stream has a 6ft low flow stream, then 18.5ft overbank to 2:1 side slopes. Please refer to sheets 104 and 105 regarding staged removal of the existing box culvert. As noted, temporary shoring used to accommodate the diversion channel is incidental to the bid item â€œTemporary Water Diversion Indian Creekâ€. | Mike Coleman | 19 | 2022-09-22 15:04 | 2022-09-26 09:58
20221011 | 20221011003 | 3 | Special 0960. Contractor Staging Area | It appears based on previous questions and answers this Contractor Staging Area is mandated. If this is the case please use existing bid items to pay for items that are required under this SPV, like Asphaltic Surface Milling, Pavement Sawing, Base Aggregate, Breaker Run, 18" CMP, Asphalt, Curb & Gutter, E-Mat, Fertilizer, Seed, Pavement Markings, Lighting and Temporary Fence. | The Department has secured a section of the Brown Deer Rd park and ride lot for the contractors to utilize as a staging area. It has been set up as an â€œEACHâ€ item to provide flexibility in accommodating how the contractor decides to use it. The resultant quantities needed to restore it will be dependent on how they do so. Therefore, it will remain as an â€œEACHâ€ item. | Mike Coleman | 20 | 2022-09-22 15:15 | 2022-09-26 11:13
20221011 | 20221011002 | 2 | Special Provision #4 Traffic | The last paragraph states "Flagging operations will be allowed along all roadways to accommodate the roadway and structure work between 1 hour after sunrise and 1 hour before sunset." This seems to be an unnecessary restriction. Can this restriction be removed? | Flagging restrictions will be revised to from sunrise to sunset. All work operations and equipment need to be out of the work zone by this time. The revised language will be included with an upcoming project addenda. | Mike Coleman | 1 | 2022-09-23 11:15 | 2022-09-30 06:52
20221011 | 20221011002 | 2 | Spec Prov #4 Traffic | The last paragraph states "Delays due to flagging may not exceed 5 minutes in any direction......." This is an asphalt paving job with an August completion date. Paving will occur in hot months stretching out the work zone to allow mix to cool. It is in the contractor's best interest to keep traffic moving to allow trucks to deliver material to the operation. Can the 5 minute restriction be removed or extended to a more realistic time restriction? | The allowable delay due to flagging will be increased to 15 minutes. The revised language will be included with an upcoming project addenda. | Mike Coleman | 2 | 2022-09-23 11:20 | 2022-09-30 06:52
20221011 | 20221011003 | 3 | B-40-1026, B-40-1027, B-40-1028 STAGING AND REMOVAL - Temporary Diversion Channel | Based on a previous question and answer, the temporary diversion channel is suppose to be 20' wide but on page 104 and 105 (stage 2a and 4a) when the water stays in one box culvert cell it doesn't meet the minimum 20' wide diversion channel requirement because the existing box culvert is only 15' wide. Why is this diversion channel designed for a Q10 storm, isn't Q2 usually used for temporary construction? Please consider reducing the temporary channel width requirement. If not please give direction on how to achieve the 20' width in stage 2a and 4a. | The temporary channel width has been reduced to 15ft with an estimated water surface elevation of 658 for the Q10 flow. This revision is included in addendum 2. The Q10 flow was coordinated with DNR due to the highly urbanized watershed. | Mike Coleman | 21 | 2022-09-26 11:23 | 2022-09-29 06:24
20221011 | 20221011011 | 11 | Removing Distressed Pavement Milling | So the Milling should be priced as a separate operation and cannot be completed when the mainline mill goes through on pass one? | A separate bid item â€œRemoving Distressed Pavement Millingâ€ has been included because we had heard from contractors on other projects that they found efficiency with performing a consistent depth milling along the length of the project and then coming back to the areas marked (by the engineer in the field) as â€œdistressedâ€ with their smaller milling machine (often used for shoulders / intersections, etc.) to take care of the additional depth required in these â€œdistressedâ€ areas. The intent is that the engineer in the field will mark the areas that are observed to require the additional depth of milling prior to the primary milling operations. Once the primary milling is complete, the engineer in the field will again review these previously marked areas and confirm whether additional milling is necessary. The contractor can then address the areas that the engineer in the field has confirmed require the additional treatment. If the contractor chooses to, it could be possible to complete the additional milling depth in the areas marked as â€œdistressedâ€ by the engineer in the field prior to the milling operations under the bid item for â€œRemoving Asphaltic Surface Millingâ€ during the initial milling pass. If this is the case, no additional payment will be made for the item â€œRemoving Distressed Pavement Millingâ€. | Mike Coleman | 4 | 2022-09-26 13:38 | 2022-09-29 06:19
20221011 | 20221011007 | 7 | 6" Crosswalks | The pavement marking drawings in the plan show 6" Epoxy crosswalks, the proposal and misc. qty's show 6" Paint crosswalks. All other permanent pavement markings are Epoxy, was this supposed to be as well? | An addendum will be issued to add the 6" epoxy crosswalk item. | Mike Coleman | 1 | 2022-09-26 13:43 | 2022-09-27 09:37
20221011 | 20221011003 | 3 | Earthwork Tables | Can the earthwork summary and data tables be provided in excel format? | The earthwork tables can be found at the following location: https://wisdot.box.com/s/f4wwaf04rsjmqcx76tlx3ftoz7waghdk or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 22 | 2022-09-26 14:17 | 2022-09-27 10:34
20221011 | 20221011011 | 11 | Contract Time | The proposal has this project set as a 65 working day contract. Will the Department please review the following points and consider extending the time allowed. Section 3 of the special provisions state "replace culvert pipes prior to beginning of the milling operations on STH 13 unless otherwise approved by the engineer in the field". There are a total of 41 culvert pipes with 35 required road cuts and we anticipate the culvert work to take 50 working days. Milling and lower lift HMA 17 days. Upper lift HMA 11 days. Intersection and driveway HMA 4 days. Aggregate shouldering, beam guard, and paint 10 working days. All totaled we feel there is at least 92 working days on this project. We appreciate your time to look into this. | We have reviewed the timechart again for this project and investigated the production rates used, along with the time constraints applied to the project, environmental obligations established by WDNR, etc. and are able to adjust the time of the project to 85 working days. The project special provisions contained language to indicate that this project is on an expedited schedule and may require extraordinary forces and equipment, which includes multiple crews, etc. An addenda will be prepared to cover a number of items and will also include an adjustment to the number of working days established for the completion of this project. | Mike Coleman | 5 | 2022-09-26 14:50 | 2022-09-29 06:21
20221011 | 20221011003 | 3 | Pre-Stage Earthwork Quantities | It appears there are no earthwork quantities for any of the pre-stage work on Port Washington, Good Hope and Brown Deer Road (removing the existing islands and/or medians to allow for the temporary base aggregate and temporary asphalt to be installed for temporary crossovers)? It appears the Base Aggregate and Asphalt is accounted for? | Updated earthwork tables, including pre-stage earthwork, will be included in Addendum 2. | Mike Coleman | 23 | 2022-09-26 14:57 | 2022-09-29 06:26
20221011 | 20221011003 | 3 | Earthwork Tables in Excel | Can the earthwork tables from pages 3066 to 3133 be provided in excel format? | The earthwork tables can be found at the following location: https://wisdot.box.com/s/f4wwaf04rsjmqcx76tlx3ftoz7waghdk or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 24 | 2022-09-26 17:20 | 2022-09-27 10:34
20221011 | 20221011003 | 3 | R-40-648, sheet 2976, 1'-7" max dimension on detail for CIP modified single face parapet . | We are requesting clarification concerning the minimum and maximum required panel embedment into the coping/moment slab. The contract documents for R-40-648 state a 1â€™-7â€ max. dimension from the top of the coping to the top of the MSE panel as shown. We are questioning the accuracy of this maximum dimension, if that is the maximum, what would be the minimum? This appears to be a non-typical detail for WisDOT projects that we have designed previously and therefore believe this dimension could be an error. This detail seems to be consistent of all the MSE walls on this project. | The dimensions shown on the detail are consistent with the dimensions on WisDOT Bridge Manual Standard Drawing 14.02. | Mike Coleman | 25 | 2022-09-26 18:10 | 2022-09-29 06:26
20221011 | 20221011003 | 3 | Earthwork Summary Page 1606 | It appears Stage 1B - PORT WASHINGTON ROAD - NORTH 115+50-136+71 = 20,907 CY of Common excavation is overstated because it includes Stage 2A quantity also - both sides of the roadway. Please verify. | Updated earthwork sheets will be included in Addendum 2. | Mike Coleman | 26 | 2022-09-27 12:01 | 2022-09-29 06:27
20221011 | 20221011003 | 3 | 641 wall - Unit 2 wall | Sheet 1 of the R-40-641 plans shows unit 2 to be secant piles with CIP concrete facing but sheet 2 of the plans shows unit 2 being secant piles with full height prestressed precast concrete panels. The typical sections on sheet 7 of the plan shows unit 2 being secant piles with CIP concrete facing. Please advise what unit 2 is supposed to be faced with on the R-40-641 structure. | The precast panel call-out at R-40-641 Unit 2 on the elevation view on sheet 2 is incorrect. The entirety of Unit 2 is to have a cast-in-place facing, as shown on the Typical Sections on sheet 7, on the wall facing details on sheets 14-16, and in other details throughout the plans. Precast facing panels are to be used only at Unit 3, which is the existing sheet piling wall unit. | Mike Coleman | 27 | 2022-09-27 18:12 | 2022-09-29 06:28
20221011 | 20221011004 | 4 | HMA Quantities | The stationing for the HMA Pavements in the Miscellaneous Quantities (sheet 16) shows 50â€™ as do the Plans (sheet 20). Based on that stationing, the quantities appear to be overstated. Please confirm stationing vs quantity for bid items #36 Tack Coat, #40 HMA Pavement 3MT and #42 HMA Pavement 4MT. | The stationing for bid items 455.0605 Tack Coat, 460.6223 HMA Pavement 3MT, and 460.6224 HMA Pavement 4MT is 648+27 to 648+77 and 651+55 to 652+05 as shown on the plans. However, the quantities should be revised to the following: 455.0605 Tack Coat: 25 GAL, 460.6223 HMA Pavement 3MT: 72 TON, 460.6224 HMA Pavement 4MT: 24 TON. An addendum will be issued to address these changes. | Mike Coleman | 1 | 2022-09-28 11:28 | 2022-09-30 06:51
20221011 | 20221011007 | 7 | Guardrail Construction | In the traffic section there is a note that the shoulders should be closed and reopened during nonworking hours, and to reopen the shoulders the guardrail needs to be complete. There is also a note that the guardrail can be down for 72 hours. When the guardrail is removed, contractor needs to complete the slope grading prior to guardrail being replaced and does require a minimum of 72 hours to complete all work. As such, will the Department change the language to allow for the shoulder closure to stay in place. | We will be submitting the addendum forms addressing this question next week prior to the emergency addendum deadline. We plan to allow shoulders to remain closed for the duration of the guardrail work and increase the time from 72 hours to 5 calendar days. | Mike Coleman | 2 | 2022-09-28 13:25 | 2022-09-30 11:37
20221011 | 20221011007 | 7 | Railroad Construction | In section A.4 â€˜work by railroadâ€™ (page 7 of the specials), it mentions that the railroad is removing the crossing surface and replacing the surface. After the contractor excavates the pavement how long will it take for the railroad to perform their work? Is the 15 calendar closure suspended during that time? | We plan to update the ILDâ€™s via an addendum removing the railroad work stipulation since the railroad work will be done by a 3rd party and is out of the contractorâ€™s control. The intent as specified in the Traffic Section under â€œConstruction Operationsâ€ is to have this railroad work done during the road closure and detour stage. We plan to submit the addendum next week prior to the emergency addendum deadline. According to Jared Kinziger: The railroad work â€œis one to three days of work typically, â€œnot contractuallyâ€ for the RR. It is up to the contractor to coordinate/schedule of this work with the RR during the detour per standard spec. Note the RR is a 3rd party in the delay part of the spec book. Also, for this project type â€rehab the crossingâ€, if the RR doesnâ€™t show up or doesnâ€™t want to do this work, we are not going to hold up our highway contractor so a delay is very unlikely unless somehow the RR would run into an issue if they couldnâ€™t complete this very simple work and we couldnâ€™t pave. This would be extremely unlikely.â€ | Mike Coleman | 3 | 2022-09-28 13:26 | 2022-09-30 11:37
20221011 | 20221011003 | 3 | Breaker Run | The typical section on page 1195 of the plan indicates the placement of 12" of breaker run for the temporary widening at Sta 1096+00 - 1185+00 SB. However, the Base and Subbase table in the Miscellaneous Quantities on page 1700 of the plan does not show a quantity of breaker run from Sta 1084+00 - 1185+00. Has the quantity of breaker run been omitted or is it included in a total elsewhere in the Miscellaneous Quantities? | An updated Breaker Run table will be included in Addendum 2. | Mike Coleman | 28 | 2022-09-28 15:51 | 2022-09-29 11:54
20221011 | 20221011003 | 3 | Pipe Underdrain Wrapped | Is the wrapped pipe underdrain for the temporary Stage 1 widening that is shown in the typical sections on page 1195 of the plan to be backfilled with native material? | Underdrain trench is to be backfilled with Base Aggregate Open Graded per the plans. An updated Miscellaneous Quantity sheet will be included in Addendum 2. | Mike Coleman | 29 | 2022-09-28 16:15 | 2022-09-29 11:54
20221011 | 20221011001 | 1 | AC Type - 460.4210.S: HMA Pavement Interlayer | Item '460.4210.S: HMA Pavement Interlayer' calls for PG 58-34 AC. This AC is not utilized in SW Region. Can the AC type for this item be changed to PG 58-28 AC? | After consultation with the region pavement engineer and design team, we will NOT allow a change to PG 58-28. The STSP shall remain as currently advertised. | Mike Coleman | 2 | 2022-09-29 14:59 | 2022-09-30 11:37
20221011 | 20221011003 | 3 | Regarding note sheet 3 of 22 structure plans B-40-1026 Page 2682 | Full removal of the Box B-40-23 does not appear to be needed. The floor and part of the walls appear to not conflict with the new channel work. Removal of the floor drastically complicates the excavation, bypass channel and temp shoring required. Would the Department consider leaving the floor in place? | Per the Departmentâ€™s coordination with the DNR, removal of the entire box culvert is required. | Mike Coleman | 30 | 2022-09-29 15:24 | 2022-10-04 08:36
20221011 | 20221011003 | 3 | Concrete Masonry Retaining Wall Quantity Verification, R-40-641/642 | Please verify concrete and reinforcing quantities for structures R-40-641 and R-40-642. The following are specific plan discrepancies: 1. Per General notes sections for Unit #3 of both walls, the concrete and reinforcing steel for the footings and copings is incidental to the concrete panel walls. The estimated quantities table shows pay quantity for Concrete Masonry Retaining Walls in Unit #3. What is this pay quantity for? 2. Units #4 and #5 Concrete Retaining Wall quantities are 91 cy and 352 cy respectively. Our takeoffs for both units are coming in significantly less. Please verify plan quantities are correct and provide a breakdown for our review. We are seeing 10â€ thick wall facing with 1â€™4â€x2â€™ coping on top and no other concrete. What will be the pay thickness in the secant wall sections as this will vary with the wall face. Is the concrete to fill the void between secant piles incidental? | 1. The concrete and reinforcing steel for the coping and wall panel footing are incidental for Unit 3 for both R-40-641 and 642. There should be no concrete quantities included in the quantities tables for Unit 3. 2. The concrete in the â€˜valleysâ€™ between the R-40-641 Unit 2 and Unit 4 secant shafts is to be paid for under Concrete Masonry Retaining Walls. Taking this into account, the Unit 2 quantity is 804.2 CY and the Unit 4 quantity is 31.8 CY (Unit 4 revised volume also corrects a summation error). The corrected quantity for Unit 5 is 239.3 CY. The changes in quantities for Concrete Masonry Retaining Walls also affect the quantities for Ice Hot Weather Concreting and Incentive Strength Concrete Structures. Quantity updates will be included in a forthcoming addendum. | Mike Coleman | 31 | 2022-09-30 13:51 | 2022-10-06 06:31
20221011 | 20221011007 | 7 | Pavement Markings | Good morning, It appears the plan has enough temporary paint for 2 applications(1 for the milled surface and I'm not sure what the other one would be for). In addition, should there be a same day epoxy marking item for the center line on the surface daily after paving rather than the standard epoxy item included in the proposal? Will an addendum be issued to clarify your intentions for the temporary paint and epoxy center line item? Thank you. | The plan is to have two centerline marking applications: one for the milled surface and one for the tapered longitudinal joint. See Construction Detail, â€œPavement Marking Detail for Tapered Overlapping Joints in HMA Pavementsâ€ in the plans. Since this joint is allowed to remain for up to 72 hours per the Special Provisions, this second application was added to cover such a scenario. We will add same-day centerline markings, and remove the â€œMarking Line Epoxy 4-Inchâ€ for the centerline markings for the length of the project. An Addendum will be issued to address this. | Mike Coleman | 4 | 2022-10-01 08:30 | 2022-10-04 08:46
20221011 | 20221011009 | 9 | Completion | Good morning, On page 2 of 38 it states this project is "within the 2022 construction season". Will an addendum be issued stating "within the 2023 construction season"? | Yes, an addendum will be issued. | Mike Coleman | 5 | 2022-10-01 08:44 | 2022-10-03 08:23
20221011 | 20221011003 | 3 | Bridge B-40-24 Removal Limits. | Reference B-40-921 plan sheet 6 of 56 - Note 4 which indicates : â€œThe entirety of the structure will be removed and paid for under removing structure B-40-24â€. The WIDOT standard specifications require 2â€™0â€ below finished grade. Is it WODOTâ€™s intent to remove the footings and piling? If so what elevation limits we be required for removal? | Existing structure B-40-24 is within UPRR right-of-way and therefore UPRR standards for demolition and removal apply. UPRR Demolition Guidelines indicate in Section III Note D to remove all substructures at least 3â€™ below final finished grade. Note that a demolition diagram and sequence per Special Provision article 22 will need to be approved by the UPRR engineer and the engineer before proceeding with demolition. | Mike Coleman | 32 | 2022-10-03 08:55 | 2022-10-04 08:44
20221011 | 20221011003 | 3 | Ancillary Structure Concrete and Black reinfrocing steel quantities | Please verify quantities for line items #410 and #412. We are finding a total of 172 cy of Ancillary Concrete and 17,560# of uncoated reinforcing steel. Quantities are found in structures S-40-3033/3034/3035/3036/3037/3038/3039/3036. Is there another structure we are not finding? | Additional quantities are provided in the 1229-04-73 signing Miscellaneous Quantity tables (see sheets 1892-1915). | Mike Coleman | 33 | 2022-10-03 09:54 | 2022-10-04 08:45
20221011 | 20221011003 | 3 | Drilling Shaft 36" Quantity | Verify quantity of item #420 - Drilling Shaft 36". We are finding a total of 612' in sign structures S-40-461/3033/3034/3035/3036/3037/3038/3039/3040/3043/3046/3047/3048/3049/3055/3056/3057. | Additional quantity is provided in CAT 1300 in the 1229-04-73 ID. | Mike Coleman | 34 | 2022-10-03 10:40 | 2022-10-04 08:46
20221011 | 20221011003 | 3 | SPV 22. UPRR Requirements | SPV 22 Section A currently does not have a maximum limit set for submittal/resubmittal review time for anything related to the UPRR structure. Without a current maximum limit on review time by DOT/UPRR, the Contractor does not have any control over meeting the interim completion date given in SPV 5.L.6. Please add a maximum review time for submittals and resubmittals for the UPRR structure to SPV 22 Section A. | 6 weeks, provided the submittal is complete per UPRR guidelines. | Mike Coleman | 35 | 2022-10-03 13:59 | 2022-10-05 06:06
20221011 | 20221011004 | 4 | CTH PP Roadway | Portions of the CTH PP SB roadway are in conflict with the removal of the existing substructure and construction of the proposed substructure. The plan does not provide existing cross sections for CTH PP SB or quantity for the removal and replacement of roadway that is in conflict with substructure work. The plan does not include quantity for the repair of roadway damaged by falling debris during the removal of the existing cast-in-place box girder superstructure or a debris containment item to prevent debris from falling onto facilities located under the structure. | Removal of the existing bridge and construction of the proposed bridge will require removal of and replace in kind a portion of the existing curb and gutter and should on CTH PP. An addendum will be issued to address these changes. Protection of the existing roadway on CTH PP is covered under the standard specification 107.14; therefore, the bid item 203.0330 â€œDebris Containmentâ€ will not be required on this project. | Mike Coleman | 2 | 2022-10-03 15:38 | 2022-10-05 10:28
20221011 | 20221011004 | 4 | B-5-465 Slope Shaping | The elevation view and typical section on sheet 1 of the B-5-465 structure plan shows a variation between the existing and proposed ground lines along the length of the structure from abutment to abutment. The earthwork table within the miscellaneous quantities and the cross sections provided in the plan do not include the area between bridge abutments or along the CTH PP SB reference line. As such, the plan does not include any earthwork quantities for shaping of the ground line to the proposed elevation. | The excavation and earthwork needed beneath the structure and abutments is covered between the work required for removal of existing structure (Bid Item 203.0220), excavation for the proposed structure (Bid Item 206.1000), and the slope paving standard specification (section 604.5). Minimal earthwork quantities are anticipated as the existing profile is generally close to the proposed surface and proposed structure will not involve any major changes to the bridge geometry. | Mike Coleman | 3 | 2022-10-03 15:39 | 2022-10-05 10:30
20221011 | 20221011004 | 4 | Removing Concrete Slope Paving | The plan does not include quantity for removing existing concrete slope paving. | The work for removing existing concrete slope paving should be included as part of bid item 203.0220 â€œRemoving Structureâ€. | Mike Coleman | 4 | 2022-10-03 15:39 | 2022-10-05 10:30
20221011 | 20221011003 | 3 | B-40-921 Secant Shaft Drill Staging | Structure B-40-921 has a specific stage plan for the installation of the secant shafts on sheet 26 of 56. In this plan it has secondary shafts in all four corners of this abutment which creates a quality control issue as the secondary shafts do not have a form of resistance on the front end of the abutments that help guide verticality while drilling. Can the drilling contractor install sacrificial clsm shafts on the front side of the abutments to guide in secant pile installation? | The contractor may install sacrificial CLSM shafts, upon submittal approval of details and materials by the engineer and the UPRR engineer and at no cost to the department. Show in the prospective submittal that the sacrificial shafts will not interfere with any other present or future scope of work as described in the contract documents; or if portions are interfering, they shall be removed at no cost to the department. | Mike Coleman | 36 | 2022-10-04 11:05 | 2022-10-05 10:26
20221011 | 20221011003 | 3 | Early Shop Drawing Notice to Proceed | Due to the expedited schedule will the Department be adding language to help facilitate the procurement timeframe of long lead items such as structural steel, pre-cast T Wall sections, MSE Wall Panels, and Noise Wall Pre-cast Panels? On previous projects the department has added language as follows, â€œUpon initial award of the contract, the contractor is authorized to immediately begin shop drawing preparation according to 506.3.2 for the structural steel for permanent structure B-40-921. Do not place the mill plate order for structural steel or begin any other work in the contract until receiving written notification to proceed from the engineer and UPRR engineer. In the event the contract is ultimately not executed, the department will reimburse the contractor for the reasonable costs of the advance preparation of the shop drawing and mill plate order.â€ | No, that will not be done for this project. | Mike Coleman | 37 | 2022-10-04 11:28 | 2022-10-06 06:30
20221011 | 20221011003 | 3 | Union Pacific Railroad permitting | During the non-mandatory prebid meeting when asked if the appropriate permits have been obtained with Union Pacific Railroad (UPRR) the Department noted that Office of Commissioner of Railroads (OCR) gave an official ruling to UPRR for this project. With recent projects UPRR has commonly filed appeals with the OCR Ruling. Does the Department have UPRR approval on the advertised UPRR structure Plan and all work commencing on UPRR Right-of-way; including but not limited to B-40-921, R-40-649, track construction, proposed drainage improvements (jack and bore operation), and access roads? | UPRR has approved the structure plans, the drainage improvements and the access roads. Approval of the track plans is in the final stage. | Mike Coleman | 38 | 2022-10-04 14:08 | 2022-10-07 07:42
20221011 | 20221011001 | 1 | Item 0054 - 390.0501.S | The item "Base Patching Asphaltic for HMA Interlayer" is 1 EA for the project - essentially a lump sum item on something that can vary greatly. Can further information (SY, number of locations, etc) be given for this item, or the unit of measure changed? The item description allows for engineer direction (additional quantity/work?), making this item difficult to quantify to bid and facilitate in the field (what is needed vs. what plan indicates). | The item is an STSP so we will not be changing the unit of measurement. You can remind the bidders that the engineers estimate of locations that require patching for this bid item is shown on the plan details. | Mike Coleman | 3 | 2022-10-04 15:15 | 2022-10-05 10:32
20221011 | 20221011003 | 3 | SPV Article 5. Prosecution and Progress , T. Railroad Construction Coordination | In attempts to coordinate with cement / concrete suppliers to obtain Type 1 cement to complete this contract work as specified in section T of Prosecution and Progress the Type 1 cement is not available to procure. Please advise on acceptable alternatives to complete this contract without the use of Type 1 cement. | UPRR has continued to require Type 1 cement on UPRR structures for recent WisDOT projects and has denied use of Type 1L cement in UPRR structural concrete. Although Type 1 cement is in high demand, contractors on recent WisDOT projects have procured it for UPRR structures. We encourage further investigation. | Mike Coleman | 39 | 2022-10-04 16:46 | 2022-10-06 06:33
20221011 | 20221011003 | 3 | Earthwork Summary - Brown Deer Road Qtys | It appears these areas on the earthwork summary are double up on Common Excavation & Embankment (like EB & WB quantities are in both stages): STAGE 2 EB BROWN DEER ROAD - WEST 605+15 - 616+67 7,263 CY STAGE 2 EB BROWN DEER ROAD - EAST 618+29 - 628+80 12,056 CY STAGE 3 WB BROWN DEER ROAD - WEST 605+15 - 616+67 7,121 CY STAGE 3 WB BROWN DEER ROAD - EAST 618+29 - 628+80 12,458 CY | Earthwork quantities are correct as shown. Stage 2 constructs EB lanes, Stage 3 constructs WB lanes per the traffic control sheets. The â€˜Eastâ€™ and â€˜Westâ€™ listed in the roadway name refer to Brown Deer Rd East or West of I-43. | Mike Coleman | 40 | 2022-10-04 19:21 | 2022-10-06 06:33
20221011 | 20221011003 | 3 | MSE Wall - TYPICAL WALL EXCAVATION LIMITS DIAGRAM | It appears all the MSE Wall - TYPICAL WALL EXCAVATION LIMITS DIAGRAMs are incorrect. It shows the incidental excavation in front of the MSE wall is from the existing grade, which is not correct. Common excavation is paid from the existing grade to the subgrade first, then below the subgrade any excavation for the MSE wall is incidental. Please correct these details for all the MSE walls. Reference plan sheet 2973 for an example. | Excavation and backfill diagrams shown on wall plans R-40-412, 413 and 642 are correct as shown and indicate that excavation in front of the wall is covered as Common Excavation. For R-40-647, there is an existing parking lot for a condo/apartment building in front of the wall. The improvements to the existing parking lot are a result of the wall being constructed and therefore all excavation in front of the wall is included in the wall construction and not paid for under Common Excavation. As noted in the special provision Wall Concrete Panel Mechanically Stabilized Earth section C.1, excavation limits are as stated in the special provision â€œunless shown or noted otherwise on the planâ€. For walls R-40-640 and R-40-648, the quantities for excavation in front of the wall were reviewed and are paid for under Common Excavation. The diagrams on the plans will be updated in the forthcoming addendum. | Mike Coleman | 41 | 2022-10-04 20:00 | 2022-10-06 06:34
20221011 | 20221011003 | 3 | R-40-641 Soldier Pile Concrete Quantity | Verify Concrete Masonry Soldier Pile Footing quantity is correct for R-40-641. Volume calculation of sum footing lengths from solider pile data table does not equate to plan quantity for this structure. All footing lengths appear to be 3' off. Similar calculations for R-40-642 match plan quantities. | The plan volumes for Concrete Masonry Soldier Pile Footing for wall R-40-641 are incorrect. The correct volumes are Unit 1 = 130 cy, Unit 5 = 473 cy, Total = 603 cy. Quantity updates will be included in the forthcoming addendum. | Mike Coleman | 42 | 2022-10-04 20:19 | 2022-10-06 06:35
20221011 | 20221011003 | 3 | Project Schedule | Due to our estimate of receiving our Purchase Order, ordering and receiving raw mill materials and our current shop fabrication schedule, we are anticipating a delivery of structural steel for B-40-921 in a timeframe that will not allow the contractor to complete the interim Union Pacific corridor stage by September 24, 2023. Will the WisDOT consider extending this interim completion date? | No, the interim completion date of September 24, 2023 will remain in force, as shown in the projectâ€™s Special Provisions. | Mike Coleman | 43 | 2022-10-05 08:51 | 2022-10-07 10:15
20221011 | 20221011004 | 4 | Removing Structure Granular Backfill | It appears the bottom of existing substructure may be lower in elevation than that of the proposed bottom of substructure. Will granular material be required as a subfoundation course to bring the grade to proposed elevation after structure removal is complete? | Granular backfill material will not be required. | Mike Coleman | 5 | 2022-10-05 09:06 | 2022-10-06 13:51
20221011 | 20221011011 | 11 | Notch Joint | The note on page 13 of the plans has a notch joint being constructed on a HMA mat thickness less than 1.75" minimum specification and then being removed via item removing notched wedge joint. I do not see the item "Removing HMA pavement Notched wedge joint" in the proposal? | Construction detail has been edited to remove the longitudinal wedge joint on the surface layer of the asphalt. An addendum will be submitted this morning with the revised detail. No additional bid items were added. | Mike Coleman | 6 | 2022-10-05 10:38 | 2022-10-06 10:25
20221011 | 20221011011 | 11 | Notch Joint | Correction to question #6 the detail is on page 15 not 13. | Construction detail has been edited to remove the longitudinal wedge joint on the surface layer of the asphalt. An addendum will be submitted this morning with the revised detail. No additional bid items were added. | Mike Coleman | 7 | 2022-10-05 10:40 | 2022-10-06 10:25
20221011 | 20221011003 | 3 | Breaker Run Quantities | On Plan Sheet 1701 the breaker run quantities seems incorrect. Stage 3 IH 43 SB 1078+88 - 1154+00 = 10,377 tons (seems like the quantity is missing the outside shoulder beyond the barrier wall, 4'or so) IH 43 SB 1185+00 - 1282+50 = 46,108 tons (seems like the quantity is missing the outside shoulder beyond the barrier wall, 4'or so) and BROWN DEER RAMP D 1252BDD+38 - 1262BDD+96 = 202 tons (this is not close to the 1-1/4" qty of 2,033 ton, so the Breaker Run is way under stated) Please verify these quantities. | The overall Breaker Run quantity for station range 1078+88 - 1154+00 is correct. The 3â€™ shelf (outside of the proposed pavement) shown in the Stage 3B cross sections adjacent to the southbound inside shoulder was originally quantified in Stage 4, instead of Stage 3. This has been updated in Addendum #3. Quantities for station ranges 1185+00 - 1282+50 and 1252BDD38 - 1262BDD+96 have been updated in Addendum #3. | Mike Coleman | 44 | 2022-10-05 11:32 | 2022-10-07 07:32
20221011 | 20221011003 | 3 | S. Fish Spawning - Special Provision | Page 29 of the Special provisions state there will be no instream disturbance from March 1st thru June 15th, then Indian adds another restriction of June 1st thru August 15 (unless protections are installed before March 1st). So Indian Creek can't be touched from March 1st thru August 15th? When are you suppose to remove the existing box culvert and divert water back/forth in the diversion and build the new structures? And follow the staging plan on plan sheets 104 & 105? Traffic is on the existing box culverts before March 1st of every year, so you can't start before then or put any protection in place. So you have to wait until after August 15th, and that is not enough time to complete the work within the timeframe given in the schedule. The design schedule provided doesn't account for this restriction either, therefor these restrictions need to be modified or removed. |  |  | 45 | 2022-10-05 12:07
20221011 | 20221011003 | 3 | Estimated Contract Award Date | Can WisDOT give an estimated Contract Award date for this project? If it is beyond the normal 1-2 weeks after the bid date, this needs to be known to determine potential added liquated damages and/or acceleration costs that needs to be considered within the bid by all contractors. | It is anticipated that the contract will be awarded per standard timelines. | Mike Coleman | 46 | 2022-10-05 12:16 | 2022-10-07 07:36
20221011 | 20221011003 | 3 | Wall R-40-642 Bid Item 328 Temporary Shoring | Please provide location and/or detail. We cannot find this indicated on plans or determine a need. | As characterized by inclusion of the shoring quantity under Unit 1 in the quantity table, the temporary shoring quantity is intended for use at the interface between the Unit 1 MSE fill wall and the Unit 2 soldier pile & lagging cut wall (e.g., to shore the soil of the Unit 2 soldier pile & lagging cut wall, so that Unit 1 MSE fill wall area can be excavated and MSE straps and fill installed). | Mike Coleman | 47 | 2022-10-05 13:22 | 2022-10-07 07:37
20221011 | 20221011003 | 3 | UPRR Bridge B-40-921 - Structural Steel Delivery | Based on conversations with multiple vendors it appears that a delivery of structural steel for this bridge is not likely to occur prior to the interim milestone completion date listed in the special provisions. Please revise this date to allow more time to construct this bridge so unnecessary liquidated damages do not need to be added to the bid. | No, the interim completion date of September 24, 2023 will not be revised. It will remain in force, as shown in the projectâ€™s Special Provisions. | Mike Coleman | 48 | 2022-10-05 13:28 | 2022-10-07 10:19
20221011 | 20221011002 | 2 | Distressed Pavement Milling | Will this be marked out prior to mainline milling? To help plan the operations need to complete the work. | It is anticipated that distressed areas will be marked out prior to milling, however additional areas may be discovered as initial milling is being completed. | Mike Coleman | 3 | 2022-10-05 13:42 | 2022-10-06 13:52
20221011 | 20221011001 | 1 | Base Patching Asphaltic for HMA Interlayer | This might be duplicate, tried asking before but it didn't look like it went through, delete it if you got both: Sheets 99-112 show two types of base patching in the interlayer area, â€œBase Patchingâ€ and â€œPlunge Mill Jointsâ€. Per the special provisions, the â€œPlunge Mill Joints are 2â€ â€“ 1/3 of the pavement for depth. Can this also be used for the â€œBase Patchingâ€ areas, or are they to be full depth per Section 390, or 9â€ in depth per the existing typical sections? Section 390 references Section 315 which calls for a 1â€ nominal mix. Can a different mix be used, 3 LT/MT/HT? Sheets 99-106 have a legend where the â€œBase Patchingâ€ cross-hatch type matches the areas shown on the sheets whereas sheets 107-112 the legend showing â€œBase Patchingâ€ cross-hatch type does not match the areas on the plan. Are these areas on sheets 107-112 also Base Patching Asphaltic? Please reconsider SY or TN pay for better field management. | The base patching areas shall be full depth. (No change to the STSP) No different mix shall be used. (No change to the STSP) The hatch pattern shown in the legend for â€œBase Patchingâ€ on sheets 107-112 should have matched the hatch pattern shown in the plan view. The basis of payment for the bid item â€˜Base Patching Asphaltic for HMA Interlayerâ€™ shall remain as â€˜EACHâ€™. (No Change to the STSP) | Mike Coleman | 4 | 2022-10-05 14:19 | 2022-10-06 13:54
20221011 | 20221011007 | 7 | Common Excavation Quantities | It appears as though the Excavation Common and the Grading, Shaping and Finishing Culvert Pipes and Apron Endwalls tables quantities are redundant. Can you verify if that's the case? If they aren't, can you identify what the difference might be? | The Miscellaneous Quantity table â€œExcavation Common & Foundation Backfillâ€ only includes the area between the finished shoulder points as shown in the construction detail â€œNew Culvert Pipes with Transitionâ€. Any excavation outside of the shoulder point is not paid for as a part of this item. The item â€œGrading, Shaping and Finishing Culvert Pipes and Apron Endwallsâ€ includes the area bounded by the finished shoulder point and the slope intercepts at each endwall location. Note that these quantities within the â€œGrading, Shaping and Finishing Culvert Pipes and Apron Endwallâ€ table are for informational purposes only. The intent of this item is to pay for the restoration as one â€œEachâ€ item for each endwall after culvert installation instead of paying for each individual unit of work required for slope restoration. | Mike Coleman | 5 | 2022-10-05 15:08 | 2022-10-06 10:41
20221011 | 20221011003 | 3 | B-40-921 Pier 3 Constructability | Current staging on Port Washington Rd by the new B-40-921 structure does not allow for construction of Pier 3 in any stage of the project. Both the Pier 3 footing and the temporary shoring around Pier 3 as shown on sheet 9 of 56 of the structure plans lie directly in the existing SB lane of Port Washington Rd. Stage 1A, 1B, 2A and 2B does not shift traffic nor provide adequate room in order to construct Pier 3 and the temporary shoring as shown in the B-40-921 plan as the SB traffic lane of Port Washington Rd is consistently shown driving over the top of Pier 3. Please advise how Pier 3 is supposed to be constructed within the current plan staging. | The question refers to a prospective traffic staging conflict that appears to occur on sheet 9 of 56 in the B-40-921 plans. Note that the subject sheet 9/56 is a Construction Phasing sheet used to describe construction of the new structure and demolition of the existing structure while maintain railroad operations. The roadway traffic staging is only shown conceptual in nature on these Construction Phasing sheets; details of the temporary paving required for the proposed traffic shift to build Pier 3 are described on revised sheets 354-355 issued in Addendum #2. | Mike Coleman | 49 | 2022-10-05 15:14 | 2022-10-07 07:39
20221011 | 20221011003 | 3 | October #3. MSE Wall winter backfill | It appears there could be winter work constructing the MSE walls. There is no provision allowing for winter backfill material under the pertinent special provision for said walls. What material may be used for winter backfill of said wall types? | The specifications included in the contract do not include any seasonal or temperature limitations, so the walls can be constructed at any time as long as the quality control requirements are met. Because of that, MSE winter backfill has not been included in the contract. Additional payment will not be made to facilitate winter construction of the walls, if the contractor decides to build them then. Each wall is its own individual bid item, so contractors have the opportunity to account for various factors in their bid prices | Mike Coleman | 50 | 2022-10-05 15:30 | 2022-10-07 07:40
20221011 | 20221011003 | 3 | Line 1370 Structural Concrete Collar Pay Item Clarification | On sheet 845 there are two details for structural concrete collars (one for manholes and one for inlets) below these details it states "INCIDENTAL TO NEW STRUCTURE AND NEW PIPE ITEMS". Additionally below both of these details it states "FOR LOCATIONS SEE MISCELLANEOUS QUANTITIES SHEETS" When referencing the STRUCTURAL CONCRETE COLLAR pay item in the miscellaneous quantities on sheet 1788 there are a total of 206 each under this pay item. In reviewing these connections it isn't clear what the intention is on which pipe connections are to receive the collar as a pay item and which are incidental. Some of the connections seem to have temp drainage or trench drain connections but their doesn't seem to be a clear depiction on which connection is being paid for and which is incidental. Can further explanation be provided as to how/when line 1370 is to be paid and when the collar detailed on sheet 845 is incidental? | All 36-inch pipes and greater connections require the structural concrete collar detail to ensure a water tight seal. Connections below 36-inch follow standard connection specifications. | Mike Coleman | 51 | 2022-10-05 21:13 | 2022-10-10 07:14
20221011 | 20221011003 | 3 | Stage 1A & 1B Typical Section | Stage 1A & 1B is not constructible without adding Common Excavation/Embankment, Breaker Run & Base Course. The typical sections and cross sections show the Asphalt edge vertically aligned with the Breaker Run & Base Course edge. There must be an extension of 2' of the Breaker Run & Base Course so the Asphalt can be placed and so it doesn't break off causing future traffic problems. All other permanent work has this 2' extension passed the Asphalt and/or Concrete edge. Please add additional quantities for this. | Extension of base aggregate is shown on the Stage 1 cross sections. Quantities will be paid for as shown on the cross sections. Stage 1A and 1B typical sections will be updated in a future plan revision. | Mike Coleman | 52 | 2022-10-06 09:54 | 2022-10-10 07:15
20221011 | 20221011003 | 3 | Answer to Question #40 Brown Road Qtys | Earthwork Summary - Brown Deer Road Qtys It appears these areas on the earthwork summary are double up on Common Excavation & Embankment (like EB & WB quantities are in both stages): ST 2 EB BROWN DEER - WEST 605+15 - 616+67 7,263 CY ST 2 EB BROWN DEER - EAST 618+29 - 628+80 12,056 CY ST 3 WB BROWN DEER - WEST 605+15 - 616+67 7,121 CY ST 3 WB BROWN DEER - EAST 618+29 - 628+80 12,458 CY If these quantities are right, then the cross sections are wrong or the Earthwork Data sheets are. If you do the cross section end area of STA 616+50 for Stage 2 EB you get 103 SF, the earthwork data sheets shows = 256 SF. Then if you do the cross section end area of STA 616+50 for Stage 3 WB you get 146 SF, the earthwork data sheets shows = 254 SF. It doesn't work. But if you add WB & EB from the Cross Sections together you get 103 + 146 = 249 SF, which equals the Earthwork Data number in both stages. So it must be doubled up. Another check is the WB is wider than EB, the cut can't be the same? | Upon further evaluation, Brown Deer Rd earthwork was duplicated in Stage 2 and Stage 3. Earthwork tables in each will be updated in a post-let plan revision. | Mike Coleman | 53 | 2022-10-06 12:15 | 2022-10-10 07:25
20221011 | 20221011005 | 5 | Reconstruct inlets on the project | There are 4 reconstruct inlets on the project that are in very bad shape. Would these be better as a remove and replace inlet? |  |  | 1 | 2022-10-06 12:46
20221011 | 20221011005 | 5 | Existing 24" pipe at 117-10 | The existing 24â€ pipe at 117+10 are 8â€™ sections. The plan says to remove 6â€™ and relay 10â€™. To accomplish this, you would have to cut one of the pipes at 2â€™. This would eliminate a bell or Spicket end and leave you with a 2â€™ piece that would have to attach to the end wall with no real connection. Is this your intent? |  |  | 2 | 2022-10-06 12:49
20221011 | 20221011003 | 3 | R-40-642 Soldier Pile Tiebacks | will the soldier piles with tiebacks be required to be provided by a vendor on the WisDOT approved fabricator list or will a traditional pile supply vendor be allowed? | The soldier piles with tiebacks warrant a shop drawing from a steel fabricator on the Departmentâ€™s Approved Products List. | Mike Coleman | 54 | 2022-10-06 13:22 | 2022-10-07 07:41
20221011 | 20221011001 | 1 | Flyash in concrete mixes | Can straight cement mixes be used? Can Straight cement mix be used for base patching? Can straight cement mixes be used given there is a flyash shortage? | The Supplementary Cementitious Material requirement of ASP 6 (effective with the May 2022 Letting) Spec Section 501.3.2.2.2 will remain in effect for this letting. 501.3.2.2.2 Supplementary Cementitious Material Replace the entire text with the following effective with the May 2022 letting: (1) Replace 15 to 30 percent by weight of the total cementitious material content with approved SCMs for class I concrete as specified in 715. (2) Replace a maximum of 30 percent by weight of the total cementitious material content with approved SCMs for class II and class III concrete as specified in 716. (3) Limit Class F fly ash sources not on the APL to maximum 15 percent. (4) Minimum SCM content may be waived by the engineer. Supplementary Cementitious Materials are defined in Standard Spec 501.2.4.2. | Mike Coleman | 5 | 2022-10-06 20:25 | 2022-10-07 10:20
20221011 | 20221011003 | 3 | 5MT 58-34V | Is the AC type correct? 58-34 is not used in the south region. Please advise. |  |  | 55 | 2022-10-09 21:14