## qandasearchletting_results
Date: | 2022-11-07
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20221108 | 20221108001 | 1 | Interim Completion and Liquidated Damages- IH 94 EB/WD | Interim Completion and Liquidated Damages â€“ IH 94 EB/WB Mill and Overlay: May 26, 2023 In this section it states that work is to be done by May 26, 2023, including box culvert extensions. No box culvert extensions are on IH 94 EB/WB they are on IH 90/94. Does this mean all box culvert extensions are to be done by May 26, 2023? | The Interim Completion and liquidated Damages section will be updated in an Addendum. The box culverts are not a part of the Interim Completion Date work. | Jill Fehrman | 1 | 2022-10-18 10:51 | 2022-10-21 14:52
20221108 | 20221108001 | 1 | Schedule | Can the schedule be provided? | The design schedule can be found at the following link: https://wisdot.box.com/s/y96t18jm8ie2mcjw9yvwgjc787e031f2 | Jill Fehrman | 2 | 2022-10-18 14:01 | 2022-10-21 15:09
20221108 | 20221108009 | 9 | Soils Report | Plan Sheet 2, last note states that there is a soils report for the project. Can this be made available for review? Thanks | The soils report for this project is available and a copy can be obtained by contacting Brandan Burger at Brandan.Burger@dot.wi.gov or can be downloaded from the following location: https://wisdot.box.com/s/jhbq49ghlko6ih2xhspw21okbc47woku or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-10-12 11:14 | 2022-10-18 06:45
20221108 | 20221108009 | 9 | pulverize and relay | Construction Details on Sheet 15 thru 19 require constructing this roadway a single lane at a time. This technique will limit the effectiveness of the pulverize and relay process for several reasons, a few being: inability to balance material between lanes reducing ride quality, centerline drop-off requirements may or may not be met (requiring extra grading or re grading time for placing temp fillets), difficulty to match/compact 2.5â€ below a newly placed pavement at centerline (new edge will be damaged) and extra mobilizations to complete work. Can these requirements be changed to allow for a full width pulverizing operation? Thanks | Upon further discussion with Grant County, a full width pulverize operation is acceptable for this project. Adjustments to the paving details will be added in a future addendum. | Mike Coleman | 2 | 2022-10-12 12:06 | 2022-10-18 06:48
20221108 | 20221108009 | 9 | rural side roads | can a detail be provided for typical rural side roads? Are side roads to be pulverized? how much new asphalt needs to be placed on side road approaches? | The sideroad transitions will be pulverized and relaid similar to the mainline of the project with the proposed 4.5â€ of new HMA pavement remaining consisting throughout the project. The transition in elevation from the proposed CTH H pavement elevation to the existing sideroad pavement elevation should take into account the elevations of the proposed concrete curb and gutter at the sideroad intersection radii. A detail will be added in a future addenda. | Mike Coleman | 3 | 2022-10-12 12:57 | 2022-10-18 06:49
20221108 | 20221108017 | 17 | Specials, Section 13.C.7.3 Surfacing | Contractor concerned with language in that section. Potential that a paving contractor would not bid the project because of the risk associated specifically paragraphs (4) and (5). | Paragraph (4) is to remain. This was added to address issues with water weeping through lower and upper HMA lifts placed on a CIR layer exposed to moisture after meeting the initial curing requirements. This language has potential to reduce risk of the contractor paving on a CIR layer that will cause moisture issues in the HMA layers. Paragraph (5) can be removed from the CIR spec language. An addendum will be issued to clear this up. | Mike Coleman | 1 | 2022-10-12 13:16 | 2022-10-13 06:53
20221108 | 20221108017 | 17 | Specials, Section 13.C.7.3 Surfacing | Section 13.C.7.3 paragraph (4), what is considered a measurable rain event? | Paragraph (4) is to remain. This was added to address issues with water weeping through lower and upper HMA lifts placed on a CIR layer exposed to moisture after meeting the initial curing requirements. This language has potential to reduce risk of the contractor paving on a CIR layer that will cause moisture issues in the HMA layers. â€œA measurable rain event is any measurable precipitation accumulation. At the discretion of the engineer.â€ | Mike Coleman | 2 | 2022-10-12 13:18 | 2022-10-13 06:54
20221108 | 20221108017 | 17 | Notes on Chevron Signs | Starting on page 7 of the plan there are notes to aim chevron signs toward approaching traffic rather than perpendicular to the roadway. What method of sign installation will allow this with 2 signs on each post? We believe that each chevron sign will need its own post in order to adhere to this note. | Per the MUTCD and TEOpS manuals, chevrons are to be aimed toward traffic rather than perpendicular to the roadway. The notes starting on page 7 are reiterating required criteria for chevron installations. The MUTCD also states chevron alignment signs shall be installed in line with and at approximately a right angle to approaching traffic, which will also be allowed. To place two chevron signs on one post, you may utilize the following alternatives: turn the signpost, adjust sign hole drilling, and/or use an adjustable sign bracket. An addendum will be issued to identify adjustable sign bracket quantities, locations, and guidance. | Jill Fehrman | 3 | 2022-10-13 14:26 | 2022-10-21 14:50
20221108 | 20221108018 | 18 | Guardrail Operations Article | The 24-hr requirement between guardrail removal and installation seems highly restrictive and inefficient. Some of the guardrail lengths are quite long, and generally, shoulder grading and graveling operations happen between guardrail removal and installation. Also, it isn't clear in the EAT locations if the existing guardrail needs to be removed to grade and pave the EAT widenings before building the inslope widenings, shouldering and installing the guardrail. Is it possible to remove this requirement? | The 24-hr requirement will be removed and the maximum time between guardrail removals and guardrail installation will be increased to seven calendar days when a fixed object is present, and 14 days when no fixed object hazard is present. The revised language will be included, and associated traffic control quantities will be updated in an upcoming project addenda. | Mike Coleman | 1 | 2022-10-13 15:00 | 2022-10-19 07:02
20221108 | 20221108022 | 22 | Sidewalk Staking | With the sidewalk not being a set dimension from roadway is the state's inspection team going to give field locations for the sidewalk, or should there be an added construction staking sidewalk item. | A bid item for staking the multi-use path will be added in an upcoming addendum. | Mike Coleman | 1 | 2022-10-14 08:26 | 2022-10-25 06:21
20221108 | 20221108028 | 28 | Asphaltic Surface Driveways and Field Entrances Bid Item | Item number 30 on the bid form shows 351 tons for the "asphaltic surface driveways and field entrances". On the plans, the only place that this would be needed would be the strip to the south of the road behind the new curb. This area does not seem to compute to 351 tons of new asphalt. I just want to see if this area is supposed to be shown bigger on the plans, or if the quantity might be wrong? Thank you! | The quantity is incorrect and will be revised via addendum. | Mike Coleman | 1 | 2022-10-18 11:01 | 2022-10-19 13:29
20221108 | 20221108029 | 29 | Backfill for EBS | There is an Excavation Common quantity of 4004 CY for EBS but no quantity for CABC to backfill. | A quantity for EBS backfill is required and will be added via addendum. | Mike Coleman | 1 | 2022-10-18 09:14 | 2022-10-19 13:28
20221108 | 20221108033 | 33 | Corps of Engineers Section 404 Permit | Will you please provide a copy of the Section 404 Permit? Mr. Baird said he could not do so to a single bidder during the letting period. | The 404 Permit can be found at the following location: https://wisdot.box.com/s/pvro9zrf5f3c0hb335d3red6ndfrf491 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-10-14 08:54 | 2022-10-17 13:05
20221108 | 20221108033 | 33 | Item 52 Quantity error | It appears the quantities for the approach slab coated rebar were not added into the totals for Item 52. Bid quantity is listed as 137,490 LBs, the total without the approach slabs but should be 160,440 LBs. | The contractor is correct the quantity should be 160,440 LB. This will be included in an upcoming addendum that we are preparing to provide additional utility information. This revision has been submitted to BOS for their review and approval. | Mike Coleman | 2 | 2022-10-17 09:04 | 2022-10-19 07:02
20221108 | 20221108040 | 40 | Asphaltic Surface Thickness | The typical sections do not show the thickness of the asphalt trail. Could this be added to typical sections? | Yes we will provide this information in an upcoming addendum. | Mike Coleman | 1 | 2022-10-12 13:41 | 2022-10-13 06:54
20221108 | 20221108043 | 43 | Grading and Shaping Intersection | Is there any more information on the Grading and Shaping Intersection item for Corporate way? Cut/Fill quantities, profiles or cross sections would help in determining the price of the item. | An addendum will be issued to better define the proposed work. | Mike Coleman | 1 | 2022-10-07 09:48 | 2022-10-13 06:50
20221108 | 20221108043 | 43 | Office Trailer | Would the department consider removing item #0032 Field Office Type B due to it being a 10 working day contract. | The Field Office item will be removed with an upcoming addendum. | Jill Fehrman | 2 | 2022-10-13 11:28 | 2022-10-14 17:19
20221108 | 20221108045 | 45 | Staging | With the staging shown in the plan, is the intent of this job to be a mill and fill project? Is it intended for the public to not travel on a gravel surface? If not, can it all be milled at one time? If staging stays in place can stages 1 & 2 be combined? | The existing pavement needs to be removed. The staging can be combined, but one lane of traffic must be maintained at all times. Apache Ave provides access to several dead-end roads. The public will be allowed to drive on a gravel base. | Mike Coleman | 1 | 2022-10-17 18:56 | 2022-10-19 10:32
20221108 | 20221108049 | 49 | Borrow Pits | Does Vilas County have any borrow pits (or areas to source borrow material) that they can purchase material from? | The county has material available and contractors should call Vilas County Highway Commissioner Troy Schalinske (715-479-4641) for details. | Mike Coleman | 1 | 2022-10-18 08:46 | 2022-10-18 08:47
20221108 | 20221108059 | 59 | substitution for breaker run | Would the department allow a substitution of 3" Base Aggregate Dense for Breaker Run due to the limited quarries in the project area? | After further review, we are leaving the Breaker Run Stone bid item in the contract as originally stated. Changing this item to 3â€ Base Aggregate Dense would introduce a tighter gradation requirement and additional testing requirements. | Mike Coleman | 1 | 2022-10-19 16:33 | 2022-10-25 06:25
20221108 | 20221108023 | 23 | Pavement Marking Quantities | Good morning, on plan sheet 173, it has 4" quantities that add up to 39,042 but has a total of 55,878 on the MQ sheet. Can you please confirm the total quantity needed for this project and if an addendum will be issued? Thank you. | The correct quantity for Marking Line Epoxy 4-Inch is 39,042 LF. An addendum is forthcoming. | Mike Coleman | 1 | 2022-10-24 07:00 | 2022-10-25 06:24
20221108 | 20221108022 | 22 | "Submersible" Electrical fuses and Slpice Blocks | Electrical Lighting Plan sheets 37-40 construction Note 1 ask the contractor to provide submersible fuses and splice blocks. Can the electrical engineer provide a manufacture(s) and catalog number(s) for the submersible fusees, submersible fuse holders and submersible splice block? | Example products of submersible fuse holders (and corresponding fuses), and splice connector blocks can be found at the following location: https://wisdot.box.com/s/bmmy3nev1uea049lpek7rd8ud6k566cx or can be accessed on the HCCI November bid letting page under Supplemental Information. Most manufacturers will have equivalent products that can be acceptably installed in lieu of these. This does not absolve the contractor of responsibility for ensuring the products meet the specs. Contractors will still need to work through their suppliers/distributers and provide product cut sheets for approval. | Mike Coleman | 2 | 2022-10-24 11:06 | 2022-10-31 06:38
20221108 | 20221108036 | 36 | Backfill EBS | On sheet 20 the earthwork table shows that areas of EBS are to be backfilled with excess pulverized material. How is the backfill material paid for? Will it be paid as Base Aggregate 1-1/4â€ item and if so, does the 1-1/4â€ quantities need to be adjusted? | The backfill material should be Base Aggregate 1 1/4-Inch. The note in the earthwork table and quantity for Base Aggregate 1 ï¿½-inch will be revised via addendum. | Mike Coleman | 1 | 2022-10-24 11:16 | 2022-10-26 05:21
20221108 | 20221108040 | 40 | Contract Time | Per the specials, the clearing on this project should occur prior to March 31st. Is the intention that the work be done without charging working days as the intersection cannot be closed until June 19th? Or will contract time be suspended after the clearing is complete? Per the specials, after Curb and Gutter is placed, it is noted that it will take WE Energies 2 weeks for the lighting work. For this 2-week period are working days suspended when this work will be the controlling item? | 1. This work is anticipated be able to be completed without closing the intersection. Working days will be not charged during clearing operations. A future addendum will be released updating Special Provision language to clarify. 2. WE Energies has agreed to work with and around the contractor when installing the lighting. They plan to coordinate with the contractor to determine what works best and can split up their work to accommodate the contractorâ€™s schedule. It is not anticipated that their work would require a suspension of the contract. A future addendum will clarify this language in the Special Provisions. | Mike Coleman | 2 | 2022-10-24 11:20 | 2022-10-25 11:06
20221108 | 20221108007 | 7 | Special Provision #3 | What is the intent of prime contractor representation during all controlling work operations? The size and complexity do not see to warrant this level of supervision. | This will be removed via an upcoming addendum. | Mike Coleman | 1 | 2022-10-24 13:24 | 2022-10-25 11:05
20221108 | 20221108008 | 8 | Special Provision #3 | What is the intent of prime contractor representation during all controlling work operations? The size and complexity do not see to warrant this level of supervision. | This will be removed via an upcoming addendum. | Mike Coleman | 1 | 2022-10-24 13:24 | 2022-10-25 11:05
20221108 | 20221108031 | 31 | 0294 SPV.0060 10.000 EACH Special 274. Poles Type 10 Modified Special 26 Ft | Factory is not able to locate a drawing in plan set for SPV.0060 10.000 EACH Special 274. Poles Type 10 Modified Special 26 Ft. Please provide more details so it can be priced out. Thanks | An addendum will be issued to add the detail. | Mike Coleman | 1 | 2022-10-24 17:50 | 2022-11-03 08:49
20221108 | 20221108006 | 6 | Asphaltic Surface Driveways and Field Entrances | On sheet 116 of the miscellaneous quantities, there is 300 tons for driveways and sideroads paid under the 4 LT item. On almost all DOT projects there is a separate item for Asphaltic Surface Driveways and Field Entrances. Can the Department please add an item for driveways on this project? This will help avoid unnecessary testing requirements on driveways as well as avoid average weighting driveways with mainline paving. | An addendum will be issued to add the item Asphaltic Surface Driveways and Field Entrances. | Mike Coleman | 1 | 2022-10-25 08:22 | 2022-10-31 06:14
20221108 | 20221108003 | 3 | Schedule | Can the department provide the design schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/laj5x0qgxw4sjujcqksrgqnpl876wgw0 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-10-25 12:14 | 2022-10-27 06:51
20221108 | 20221108021 | 21 | Schedule | Can the department provide the design schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/usj82mzwirrlne2yv7n9z2z3j3rvp2v3 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-10-25 12:14 | 2022-10-26 11:35
20221108 | 20221108039 | 39 | Schedule | Can you please provide a schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/2qt22ypno8veb51qo9259vrhie9csrgz or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-10-25 13:45 | 2022-10-26 11:40
20221108 | 20221108039 | 39 | Borings | Are there any borings for the project? | The Geotech Reports can be found at the following location: https://wisdot.box.com/s/2qt22ypno8veb51qo9259vrhie9csrgz or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-10-25 13:46 | 2022-10-26 11:40
20221108 | 20221108041 | 41 | Adjusting Manholes | Line 34 is the item 611.8110 adjusting manhole covers. As the special provisions indicate that structures to be adjusted are sanitary manholes could (or should) the item be be changed to an SPV item of adjusting sanitary manholes? | There are no chimney seals on the sanitary manholes so they will be adjusted the same as a storm sewer manholes and paid as such under item 611.810 | Mike Coleman | 1 | 2022-10-25 15:30 | 2022-10-26 12:04
20221108 | 20221108001 | 1 | Asphalt Millings | Will the DOT allow the contractor to take possession of the top 2" of existing SMA that is on the project? | The contractor may take possession of the top 2-inches of asphalt (SMA Mix). An addendum will be issued to revise the language. | Mike Coleman | 3 | 2022-10-25 15:55 | 2022-11-02 05:36
20221108 | 20221108001 | 1 | SMA | SMA is a mix and density QMP item. In the mixture testing table on page 211, it states that SMA mixture and density acceptance is per QMP. On page 212, it states that SMA mixture and density acceptance is per PWL. Is the language on page 212 for SMA incorrect? | This has been corrected in addendum #1 | Mike Coleman | 4 | 2022-10-25 15:59 | 2022-10-26 12:03
20221108 | 20221108059 | 59 | 1 1/4" backfill for storm sewer | Per the storm sewer trench detail on sheet 19, the shallow storm sewer is to be backfilled with 1 1/4" base from halfway up the pipe to subgrade. Is it the State's intention to pay for this material by the ton under the base item or is it considered incidental to the storm pipe item? | The intent is to pay for this 1 ï¿½-Inch base by the ton under the contract bid item. Areas where this is called out in the plans are listed in the miscellaneous quantity table for 1 ï¿½ - Inch base aggregate dense. It is not intended that this material is incidental. | Mike Coleman | 2 | 2022-10-26 14:05 | 2022-10-31 06:30
20221108 | 20221108025 | 25 | Typical Section | Is a typical section available for the excavation, breaker run, and base aggregate placement? | Common Excavation (EBS), Breaker Run, and Base Aggregate Dense 1 ï¿½-Inch are to be used at locations and depths as dictated by field conditions based upon the result of the proof roll, as directed by the engineer. Breaker run will be placed for excavation below subgrade; base aggregate to be used to match the existing base layers above EBS, as well as for any other locations where additional base aggregates are needed. Base Aggregate Dense ï¿½-Inch shall be used for shoulders and aggregate driveway surfaces, as shown in the plans and as directed by the engineer. | Mike Coleman | 1 | 2022-10-26 14:10 | 2022-10-27 12:15
20221108 | 20221108061 | 61 | Field Office | Since this project is only 12 calendar days do we need to provide a field office? | The field office is required per contract. | Mike Coleman | 1 | 2022-10-26 14:30 | 2022-10-27 12:18
20221108 | 20221108005 | 5 | Pier Construction | Is it the intention to remove the complete structures, install cofferdam, construct pier and remove cofferdam before March 1st? Or is it intended to remove the structures and the project sit until July 31st to start working on cofferdam and pier and rest of project? With 60 days to complete time would stop until july? | It is the intention for this project schedule to remove the complete structures, install cofferdam, construct pier, and remove cofferdam before March 1st. | Mike Coleman | 1 | 2022-10-26 14:34 | 2022-10-27 13:41
20221108 | 20221108061 | 61 | QMP Density | The QMP HMA Pavement Nuclear Density provision is not included in the proposal. If the department wants the contractor to complete the density testing this should be added. The project is small enough that the density could be waived by the department under 460.3.3.3 | QMP HMA Pavement Nuclear Density is not required. | Mike Coleman | 2 | 2022-10-26 14:35 | 2022-10-27 12:17
20221108 | 20221108056 | 56 | QMP Density | The proposal does not include the QMP HMA Pavement Nuclear Density special provision. If the department wants the contractor to complete the testing this will need to be included. | QMP HMA Pavement Nuclear Density Special Provision will be added via addendum. | Mike Coleman | 1 | 2022-10-26 15:51 | 2022-11-01 05:54
20221108 | 20221108056 | 56 | Prosecution & Progress | Under Prosecution & Progress it states that the Notice to Proceed will be issued such that work shall start no later than August 22,2023. Can the contractor provide a time frame for construction of the project anytime within the 2023 construction season? | The intent of the â€œwork shall start no later than August 22, 2023â€ is to ensure the asphalt paving is completed prior to November 1st and that this project doesnâ€™t carry over into the 2024 construction season. This was based on the number of working days in the contract and percentage of probable working days for late season paving. The Contractor can provide a time frame for construction of the project anytime within the 2023 construction season. If approved by the engineer, the notice to proceed could be issued later than August 22, 2023. | Mike Coleman | 2 | 2022-10-26 15:55 | 2022-10-28 11:02
20221108 | 20221108057 | 57 | QMP Density | The proposal does not include the QMP HMA Pavement Nuclear Density special provision. If the department wants the contractor to complete the testing this will need to be included. | QMP HMA Pavement Nuclear Density will be added via addendum. | Mike Coleman | 1 | 2022-10-26 15:59 | 2022-11-03 09:57
20221108 | 20221108062 | 62 | Field Office | This project is only 10 working days; do we need to provide a field office? | The field office item will be removed via addendum. | Mike Coleman | 1 | 2022-10-26 16:06 | 2022-10-27 11:13
20221108 | 20221108062 | 62 | Prosecution & Progress | Under Prosecution & Progress it states that the Notice to Proceed will be issued such that work shall start no later than August 14,2023. Can the contractor provide a time frame for construction of the project anytime within the 2023 construction season? | The project can be done between May 1st â€“ October 15th during the 2023 construction season. The intent was to avoid cold weather HMA paving. | Mike Coleman | 2 | 2022-10-26 16:08 | 2022-10-27 12:13
20221108 | 20221108065 | 65 | Prosecution and Progress | Under Prosecution & Progress it states that work shall start no earlier than June 1, 2023. It also states that the Notice to Proceed will be issued such that work shall start no later than August 26,2023. Can the contractor provide a time frame for construction of the project anytime within the 2023 construction season? | The contractor should provide a time frame for construction between June 1, 2023 and September 15, 2023. These dates are based on staying out of HMA cold weather paving timeframes per FDM 19-5-3.2 Usage Guidance for Other Items. | Mike Coleman | 1 | 2022-10-26 16:48 | 2022-11-01 11:21
20221108 | 20221108065 | 65 | QMP Density | The proposal does not include the QMP HMA Pavement Nuclear Density special provision. If the department wants the contractor to complete the testing this will need to be included. | This contract has less than 10,000 SY of HMA pavement and density testing and documentation is not recommended per FDM 19-21-5.2.3 QMP HMA Pavement Nuclear Density; STSP 460-020. Item 460.2000 Incentive Density HMA Pavement is used instead. | Mike Coleman | 2 | 2022-10-26 16:49 | 2022-11-01 11:22
20221108 | 20221108065 | 65 | Working Days | This is a smaller project, however 5 working days is not much time to work with. Would the department consider adding more working days? Possibly 5 for a total of 10 working days? | We believe 5 days is sufficient time to complete the project based on production rates and similar projects. However, contract time extensions will be considered if warranted during construction. Working day, time charges will be assessed based on standard specification 108.9.2. Contract time extensions will be considered based on standard specification108.10. | Mike Coleman | 3 | 2022-10-26 17:21 | 2022-11-01 11:22
20221108 | 20221108065 | 65 | Field Office | This project is 5-10 working days; the department may want to consider removing the requirement/item for a field office to reduce project cost if possible. | The bid item for field office will remain in the contract. | Mike Coleman | 4 | 2022-10-26 17:26 | 2022-11-01 11:23
20221108 | 20221108005 | 5 | Instream Disturbance | Is the removal of the cofferdam sheeting after March 1st considered in stream disturbance. | Removal of cofferdam sheeting after March 1st is acceptable. The cofferdam sheeting shall be removed no later than March 15th. All accumulated sediment behind the cofferdam shall be removed before the removal of the cofferdam material. | Mike Coleman | 2 | 2022-10-27 08:14 | 2022-11-01 11:20
20221108 | 20221108022 | 22 | Nov WIS DOT 22 Crawford | Light poles and pull box for stations 26-39 are missing from the electrical plan sheets. Can electrical lighting plan(S) be provided showing the missing light pole and pull box locations for stations 26-39? | An addendum will be issued to add the missing sheets | Mike Coleman | 3 | 2022-10-27 10:51 | 2022-10-31 06:29
20221108 | 20221108061 | 61 | Existing Typical Section | The existing typical section shows the existing roadbed is 24ft wide. The existing road does not appear to be 24ft wide. Not sure if there is work being completed by others to widen the roadway before construction or if provisions need to be added to the project for widening the road? | The existing roadway widths are shown in the typical sections in the plans. | Mike Coleman | 3 | 2022-10-27 12:28 | 2022-10-28 06:52
20221108 | 20221108003 | 3 | Cold In Place Specials | Specials, Section 13.C.7.3 Surfacing Contractor concerned with language in that section. Potential that a paving contractor would not bid the project because of the risk associated specifically paragraphs (4) and (5). I understand that there is a change in this specification forthcoming. Will the change be included in this project? | Yes, this change is being made by the design team and the addendum is forthcoming. | Mike Coleman | 2 | 2022-10-27 12:42 | 2022-10-28 11:04
20221108 | 20221108034 | 34 | Temporary Crosswalk Pavement Marking | Plan pages 51 - 63 show using Temporary Marking Line Removable Tape, 4-Inch to be applied for the temporary crosswalk locations. However, the Miscellaneous Quantities on page 71 specify Temporary Marking Line Paint, 4-Inch. Please clarify if Tape or Paint is to be used for this application. Thanks | The correct item is Temporary Marking Line Paint 4-Inch as shown in the Miscellaneous Quantities on Sheet 71 and the Estimate of Quantities. The Legend on Sheet 51 will be updated via addenda. | Mike Coleman | 1 | 2022-10-27 12:43 | 2022-10-28 06:52
20221108 | 20221108039 | 39 | Excavation Below Subgrade/Undercutting | Per special provisions 15.C.1 Roadway Preparation, â€œany unsuitable soil or material shall be removed and replaced with acceptable materialâ€ and â€œsoft or yielding subgrade shall be corrected and made stable before construction proceedsâ€. Will base repair/EBS be paid through a change order? | Yes, it would be paid by change order, but none is anticipated. | Mike Coleman | 3 | 2022-10-27 13:22 | 2022-11-02 05:33
20221108 | 20221108039 | 39 | Pulverizing and Split Lifting | Per section 325.3 of the Standard Specifications, compacted lifts greater than 8 inches are to be split into lifts less than 8 inches. What are the split lift compaction requirements for pre-pulverizing and for compaction after the cement stabilization? | The design team will be submitting an addendum to address this. They want a single lift of compaction so we will modify to a single 12" lift. | Mike Coleman | 4 | 2022-10-27 13:23 | 2022-11-02 05:31
20221108 | 20221108036 | 36 | Earthwork Method of Measurement | The Earthwork Summary of Page 20 of the plan includes an allowance of 900 cy of cut for the potential expansion of the pulverized material. Please confirm that the Department will calculate the volume of the material removed by utilizing the pulverized surface versus the existing asphalt roadway surface. | The 900 cy of common excavation for the expanded pulverized material will be removed from the common excavation quantity and the chart on page 20. Payment and measurement for all common excavation (including the removal of excess pulverized material) will be calculated from the existing surface to the proposed subgrade surface. No adjustments will be made for the expansion of the pulverized materials. An addendum will be issued that will show this change. | Mike Coleman | 2 | 2022-10-27 15:25 | 2022-11-02 12:20
20221108 | 20221108053 | 53 | Field Office | Would you consider taking the field office out of this proposal? It is a small project that could be completed in as few as 10-12 days. | The field office shall remain in the contract. | Mike Coleman | 1 | 2022-10-28 10:23 | 2022-11-01 05:57
20221108 | 20221108017 | 17 | CIR | I understand the department has made an additional change to Section C.7.3 (4) of Item #327.100S Cold In Place Recycling. Will this change be included in a 2nd addendum for this projec? | This revision was included in addendum #03. | Mike Coleman | 4 | 2022-10-28 12:19 | 2022-10-31 06:45
20221108 | 20221108053 | 53 | Intersection Paving | There is no breakdown in the Miscellaneous Quantities for the intersection paving. Is the intersection HMA quantity in the 4MT58-34S item? If so is the Asphaltic Surface item undistributed, intersections or patching? | The intersections would fall under the third line on the table with the label Intersections/Entrances and will be measured and paid for under the Asphaltic Surface item. The Asphaltic Surface item is for intersections, patching or repair areas, and any miscellaneous areas not covered under the other bid items. There is a Special Provision for the Asphaltic Surface item. | Mike Coleman | 2 | 2022-10-28 13:25 | 2022-10-31 10:12
20221108 | 20221108039 | 39 | Full Depth Reclamation 8" and 12" | Has there been a mix design done on this project? Is there a mix design required on this project and if so will the contractor be allowed to pulverize a short section of each project to get the samples for the mix design without being charged days on the project. The mix design itself could take about a month. Can the cement have a separate bid item and the water have a separate bid item since the application rates in the special provision may or may not match the mix design. |  |  | 6 | 2022-10-28 14:36
20221108 | 20221108022 | 22 | Conductor splice Splice blocks - ROOM / SPACE | There are a large number of splice blocks(up to 12) required to be installed in the base of the light pole with limited room / space. Installation along with serviceability and future access to the splice blocks in the base of the pole would be difficult. Can consideration be given to adding a pedestal or transformer base to the bottom of the pole which would allow ample space to install and service the splice blocks? | Addendum #2 will add a bid item for a circular transformer base to be installed that can house splicing and provide more room to work in. City has approved this approach | Mike Coleman | 4 | 2022-10-31 07:47 | 2022-11-03 12:20
20221108 | 20221108049 | 49 | items 628.1905,628.1910 | It seems that these items are missing from the bid sheets |  |  | 2 | 2022-10-31 09:15
20221108 | 20221108041 | 41 | Field Office | As this is a short term project in an urban setting with limited to no area to set a field office on the project, could the field office item be eliminated? | Field office shall remain in contract. | Mike Coleman | 2 | 2022-10-31 09:40 | 2022-11-01 05:58
20221108 | 20221108022 | 22 | Long 2" conduit runs with #12 Pull wire | See Plan sheet 48 - Lighting Conduit and wire" Schedule indicates conduit runs with pull runs. Some of these longer runs are 765-ft up to 1,075-ft. Due to the long conduit runs should consideration be given to adding pull boxes in these longer runs to facilitate the installation of the #12 pull wire and future conductors / wiring? | These conduit runs are for future fiber, which can be blown much further than electrical conductors (we have seen up to 2,500â€™). The single #12 AWG wire is for locating, and I believe the contractor will be able to pull that single conductor this length. | Mike Coleman | 5 | 2022-10-31 10:37 | 2022-11-04 07:07
20221108 | 20221108021 | 21 | Milled Surface | Per page 3 of the special provisions, the milled surface can be open to through traffic for 72 hours and provide an even cross sectional profile of the roadway at the end of each days milling operations. Can the department remove 'perform milling and paving operations one lane at a time' to eliminate the conflicting language? | Due to the amount of traffic servicing this commercial area, the milling and paving operations need to be done in a way that accommodates the traffic. At the end of the day there either has to be a milled or paved surface open to traffic; traffic cannot be exposed to base aggregate layers. So, that is why we are saying one lane at a time. If the question is on the even cross-section at the end of the day, the first paragraph addresses unequal surfaces. | Mike Coleman | 2 | 2022-10-31 12:19 | 2022-11-01 11:15
20221108 | 20221108003 | 3 | HMA Paving Details | Previous cold-in-place projects have required a minimum cross section of a wedging layer of asphalt prior to placing surface HMA. The details show 2.25-inches of HMA to be placed in one lift on cold-in-place. Will the department change the detail to show a wedge and overlay and add HMA tons to account for a wedging layer? |  |  | 3 | 2022-10-31 13:14
20221108 | 20221108052 | 52 | 20 Working Days | Would the department consider increasing the 20 working days as a good number of contractors and the city all have portion of work on this job? We feel the schedule is very aggressive. | The City agreed to add 5 working days to the contract. An addendum will be issued. | Mike Coleman | 1 | 2022-10-31 13:56 | 2022-11-03 11:44
20221108 | 20221108060 | 60 | Office Trailer | Would the department consider removing item #0060 Field Office Type B due to it being a 20 working day contract. | The Field Office item will remain in the bid proposal for this project. | Mike Coleman | 1 | 2022-10-31 14:00 | 2022-11-03 06:05
20221108 | 20221108001 | 1 | Unreadable & Missing Plans | Can you interpret pages 67-71 of the posted plan. (Traffic Control Staging). The words are jumbled and do not make sense. The Misc. Quantities show a lane shift in Stage 2b but the plan doesn't show a detail of the lane shifts. It gives station markings but not any detail to what we will be doing at those station markings. Should there be temp markings for the lane shifts (i.e. temp paint and grinding or temp tape)? |  |  | 5 | 2022-10-31 14:01
20221108 | 20221108063 | 63 | Office Trailer | Would the department consider removing item #0063 Field Office Type B due to it being a 20 working day contract. |  |  | 1 | 2022-10-31 14:02
20221108 | 20221108064 | 64 | Office Trailer | Would the department consider removing item #0064 Field Office Type B due to it being a 20 working day contract. | The Field Office shall remain in the contract. | Mike Coleman | 1 | 2022-10-31 14:03 | 2022-11-01 06:01
20221108 | 20221108049 | 49 | Geotechnical Data | Can you provide any soil boring data for this project area? | The Geotech Reports can be found at the following location: https://wisdot.box.com/s/7v4ctp4j4cowgpvhp17xjag9u6hv84am or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2022-10-31 14:21 | 2022-11-01 11:19
20221108 | 20221108015 | 15 | Asphalt Stabilization | Looking at the Spec for Pulverized Asphalt Base Layer Item SPV.0180.01; Asphalt Stabilizing Agent Item SPV.0195.01 there is not spec for density requirements for this work does that mean it will be placed with ordinary compaction efforts or assumed that QMP density is incidental to the item? | This work will be completed with standard compaction methods identified in SPV.0180.01 Pulverized Asphalt Base Layer and under standard specification 301.3. This contract has less than 40,000 SY of Pulverized and Relay material and density testing and documentation is not recommended per FDM 19-21-5.2.2 QMP Mill and Relay Compaction, Item 374.1010.S; QMP Pulverize and Relay Compaction; Item 374.1020.S; STSP 370-020. | Mike Coleman | 1 | 2022-10-31 15:12 | 2022-11-02 12:18
20221108 | 20221108030 | 30 | Northern Long Eared Bat | Article 3 indicates restrictions around Northern Long Eared bats. It is anticipated that some small trees will be required to be removed in order to install storm sewer and riprap slope. No clearing and grubbing included in contract and may require coordination with USFWS. | None of the trees that are to be removed are expected to exceed the 3â€ diameter needed to be included in a clearing and/or grubbing item. No further coordination with USFWS will be needed. | Mike Coleman | 1 | 2022-10-31 16:16 | 2022-11-02 05:41
20221108 | 20221108030 | 30 | Utility Information | What is the depth of the fiber optic line at the toe of the riprap slope? | The utility didnâ€™t provide a depth of their line at this location; however, they did indicate that there would be no conflicts with the proposed work. Please note, the fiber optic line should extend beyond through the project limits and under the rip rap shown in the plans. | Mike Coleman | 2 | 2022-10-31 16:17 | 2022-11-02 12:19
20221108 | 20221108030 | 30 | Deck Saw Cut Joints | Existing overlay has saw cuts running in line with piers. Will this be required to be completed again? Does this coincide with parapet deflection joints? | Sawed contraction joints over the piers are not required. This does not coincide with the parapet deflection joints and sawed contraction joints adjacent to parapet deflection joints are not required. | Mike Coleman | 3 | 2022-10-31 16:18 | 2022-11-02 05:42
20221108 | 20221108001 | 1 | Plan Sheets not Legible | There are quite a few plan sheets that are not clear enough to read. Pages 66 - 71 MQ Sheets 175, 180, 188 â€“ 192, 194 â€“ 195, 198, 203 Earthwork Data Sheets 381 - 410 | The re-plotted plan sheets (11x17) can be found at the following location: https://wisdot.box.com/s/y96t18jm8ie2mcjw9yvwgjc787e031f2 or can be accessed on the HCCI November bid letting page under Supplemental Information. An addendum will be issued. | Mike Coleman | 6 | 2022-11-01 07:09 | 2022-11-01 07:12
20221108 | 20221108005 | 5 | 404 permit | Please provide 404 permit for this project. | You can find the DNR Certificate of Permit Coverage, Army Corp Transportation Regional General Permit (this project is Category 2: Modification â€“ Linear Transportation); and the DNR Final Concurrence Letter can be found at the following location: https://wisdot.box.com/s/lkfl0cs018r0b1jpcebg52e3lsl3b01i or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2022-11-01 07:42 | 2022-11-02 05:39
20221108 | 20221108063 | 63 | 4MT or 4LT | Will the state please confirm the mix type they would like on this job. The plans on page 9 show 460.5224 as a 4LT 58-28S and the specs show 4MT 58-28S. Please confirm. | 4MT is the correct mix type. The MQ sheet was incorrect. All other plan documents are correct. An addendum will be issued to correct this. | Mike Coleman | 2 | 2022-11-01 08:06 | 2022-11-02 05:43
20221108 | 20221108015 | 15 | Field Office Type C Eliminated | With this project only being 15 working days would the DOT be open to eliminating the Field Office? This project is only going to run for 1-1.5 months total with the traffic prewarns included with it being eliminated DOT could save some project costs. | The bid item for field office will remain in the contract. | Mike Coleman | 2 | 2022-11-01 10:00 | 2022-11-02 05:38
20221108 | 20221108001 | 1 | 7" Drop Off | There is no standard or detail to address the 7" drop off between lanes when constructing the 7" milling/paving on IH 94 and IH 90. Please advise how to construct while keeping the safety of traveling public as well as workers in mind. | The project will follow the standard specification 104.6.1.2.3 Drop-Off Protection for the 7â€ drop off. | Mike Coleman | 7 | 2022-11-01 10:04 | 2022-11-02 08:59
20221108 | 20221108015 | 15 | Existing project shoulders & Prep Foundation for Shoulders | Looking at the Typical Sections that are in the plan it shows 3'-4' shoulders what could be assumed is 3/4" base. When driving through the project and looking at it the shoulders are pretty much covered with grass and sod from over the years. So with the prep foundation for asphalt shoulders the intent is to pull that material up onto the road and pulverize it along with the roadway? If that material is incorporated the subbase might have some issues, so wouldn't it be better to remove that grass and sod and install new aggregate base or asphalt millings then pulverize the roadway and then relay it back out? | Any suitable existing 3â€™-4â€™ base aggregate shoulder should be removed and spread onto the existing pavement before pulverizing and will be paid for using bid item 211.0400 Prepare Foundation for Asphaltic Shoulders. Any unsuitable existing 3â€™-4â€™ base aggregate shoulder (i.e. covered with grass and sod) would be considered deleterious material and should be removed and disposed of; and will be paid for using bid item 211.0400 Prepare Foundation for Asphaltic Shoulders. New base aggregate or asphalt millings does not need to be supplemented for the disposed of existing 3â€™-4â€™ base aggregate shoulder. Payment for bid item 211.0400 Prepare Foundation for Asphaltic Shoulders includes incorporating suitable material or disposing of unsuitable material. We anticipate a majority of the existing 3â€™-4â€™ base aggregate shoulders within the project limits would be considered unsuitable material and should be removed and disposed of. The contractor and inspector will need to inspect the existing base aggregate shoulder prior to construction for suitability of incorporation into the Pulverized Asphalt Base Layer. | Mike Coleman | 3 | 2022-11-01 10:09 | 2022-11-03 08:04
20221108 | 20221108035 | 35 | Excavation Common and Borrow Table | Can you explain what the unusable pavement quantity is for in borrow column of the Excavation Common and Borrow table? If it's "unusable pavement" how can it be used for borrow? | The volume of â€œExcavation Commonâ€ includes a combination of soil and existing pavement. The â€œBorrowâ€ quantity in the table is equal to the required Expanded Fill quantity minus the â€œExcavation Commonâ€ quantity. Since a portion of the material removed under â€œExcavation Commonâ€ will be unusable existing pavement material, additional Borrow will need to be brought to the site to compensate for the unusable material. The estimated quantity of unusable pavement material is therefore added back in to the estimated â€œBorrowâ€ quantity to account for the additional material that will need to be brought in. | Mike Coleman | 1 | 2022-11-01 13:25 | 2022-11-02 05:40
20221108 | 20221108037 | 37 | Bid item #18 Prepare Foundation for Asphaltic Shoulder | Under bid item #18 Prepare Foundation for Asphaltic Shoulder it is anticipated to encounter material that will need to be hauled away due to the sod height being above the existing road surface. Will the Department add an item to haul and dispose of the unsuitable materials? | The department considers hauling and disposing of surplus or unsuitable shoulder material a part of bid item 204.0400 Prepare Foundation for Asphaltic Shoulders. No additional bid item will be added for hauling or disposing of surplus or unsuitable material. | Mike Coleman | 1 | 2022-11-01 14:19 | 2022-11-02 08:58
20221108 | 20221108001 | 1 | Allowed Lane Closure times | Special Provisions state that the roadway must be open to two lanes of traffic according to the table in 5. Traffic / Work Restrictions. This table for the most part restricts weekend work, which is understandable. S.P. then go on to state that nighttime single lane closures are allowed outside of the above times. Are lane closures allowed ANY time that isn't specified in the restricted table? Or are they only allowed as stated at "nighttime". If only allowed at "nighttime", what are the daily allowed times for single lane closures? Thanks | Follow the language for lane closure restrictions. Conflicting information will be removed by addendum. | Mike Coleman | 8 | 2022-11-01 16:03 | 2022-11-03 10:44
20221108 | 20221108033 | 33 | Utilities at Bridge | Is there any information on the gas line shown in potential conflict with piling at wing 4, east abutment. Please provide depth of gas line and any as builts available. Also provide any information on the abandoned water main north of the bridge. Depth, type of pipe, etc. It appears there could be a potential conflict with piling at wing 2 at the west abutment. | Per an email received from We Energies â€“ Gas the gas main that runs under wing 4 is a 6â€ PE main inside an 8â€ PE casing, and the elevation is believed to be at approximately 742.50. A sheet from Burlingtonâ€™s work plan showing the existing watermain size and depth can be found at the following location: https://wisdot.box.com/s/pvro9zrf5f3c0hb335d3red6ndfrf491 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2022-11-01 16:33 | 2022-11-03 07:07
20221108 | 20221108001 | 1 | Traffic Control for Box Culvert Extensions | It is difficult to determine from the traffic control plans whether or not the traffic shifts will allow for sufficient work area to complete the box culvert extensions without additional lane closures. Does the department anticipate that this work will be completed during daytime with traffic shifts or will this all have to be done at night with lane closures? Would lane closures only be required for material deliveries and exports (removals, rebar, readymix, etc.)? | The Department anticipated culvert extensions to be completed in Stage 2. Westbound extensions were anticipated to be completed under the staged traffic shift and the Eastbound extensions were anticipated to be completed with lane closures. | Mike Coleman | 9 | 2022-11-01 16:38 | 2022-11-03 10:45
20221108 | 20221108005 | 5 | Pier Access w/o 404 permit | Follow up to question #3: If a 404 permit has not been applied for or approved, what will be allowed to be placed in the river to access the existing piers for demolition and the new pier construction? Causeway? Tramway? | You can find the DNR Certificate of Permit Coverage, Army Corp Transportation Regional General Permit (this project is Category 2: Modification â€“ Linear Transportation); and the DNR Final Concurrence Letter can be found at the following location: https://wisdot.box.com/s/lkfl0cs018r0b1jpcebg52e3lsl3b01i or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 4 | 2022-11-02 07:13 | 2022-11-07 09:47
20221108 | 20221108049 | 49 | Traffic Control & Flagging | During the full closure of CTH S, will flagging be required for construction activities? | Flagging will be needed if construction is taking place on a segment of CTH S that is open to local traffic. | Mike Coleman | 4 | 2022-11-02 10:00 | 2022-11-03 06:01
20221108 | 20221108049 | 49 | Time between Pulverizing & Paving | Article 3 of the Special Provisions states: "Begin leveling layer paving operations no more than 48 hours from the start of pulverizing operations." Can this language be eliminated? It would be advantageous to allow the contractor more sufficient time to pulverize and relay the roadway before starting paving operations. Ideally, pulverizing could be completed during the 7 day closure of CTH S to minimize traffic through the work zone, the 48 hour restriction will not allow enough time for the contractor to take advantage of the closure to perform this work, because logistically the paving shouldn't start until the tie ins are completed, and the remainder of the roadway base course is fine graded. 48 hours from the start of pulverizing is insufficient to begin paving operations, and seems unnecessary. | The timeframe for placing the lower layer after pulverizing will be extended out to 7 days. An addendum is forthcoming. | Mike Coleman | 5 | 2022-11-02 10:36 | 2022-11-03 06:04
20221108 | 20221108052 | 52 | Manhole adjustments | In the special provisions it stated that we need to give the City of Menomonie Public works department 14 days prior to needing the manholes adjusted. We would like to know if they will be lowering them prior to milling and raising them up after the binder is installed. Will they be plated and brought up after surface by Public Works forces? Will the manholes have concrete placed around them at finished grade? | In talking with the city, they indicated they will not be doing any plating before milling or any paving. They would ask the contractor to mill around them and then the city will come out and adjust or reconstruct the sanitary manholes and set them at finished grade so that the contractor can pave around (lower layer) and over (upper layer) them. | Mike Coleman | 2 | 2022-11-02 13:18 | 2022-11-03 11:46
20221108 | 20221108022 | 22 | Pull Box Steel Communications (inch) 01. 36x42-inch | We are not sure how this pull box is made. Can a detail drawing be provided for the "Pull Box Steel Communications 01. 36x42-inch? | Addendum #2 will replace this bid item with a communication vault type 1, which should be constructed according to WisDOT SDD 9H9 | Mike Coleman | 6 | 2022-11-02 13:42 | 2022-11-03 12:21
20221108 | 20221108019 | 19 | Anchor Bolt Length | The plans do not state to use 21-inch railing anchor bolts in the abutment wings as would be typical. | Contractor shall follow the standard drawing 30.16 â€“ Tubular Steel Railing Type â€˜Mâ€™ notes for anchor bolt length in the wingwalls. Note was erroneously omitted in the current plan. An addendum is being issued to add the standard drawing. | Mike Coleman | 1 | 2022-11-02 15:32 | 2022-11-04 11:21
20221108 | 20221108031 | 31 | Management of Hazardous Solid waste | Per the special provisions and Addendum 1 Under section A it is noted that " This work consists of excavating and loading solid waste material into roll off boxes provided by others. The roll off boxes will be delivered to the site and removed by others." Looking for clarification that there are no costs associated beyond excavation and loading these Hazardous Solid waste materials. That all disposal / hauling / roll off containers costs will be handled by the department. | The contaminated soil that only this article deals with is â€œHazardous Waste Soilâ€ (not to be confused with regular run of the mill hazardous material, or petroleum contaminated soil). The concentrations of lead in this soil are high enough that it cannot be directed to a landfill in the state of Wisconsin (unless it is pre-treated). All Hazardous Waste disposal, for state of Wisconsin Government needs (not just WisDOT â€“ all agencies) is routed though the statewide Haz-Waste disposal contractor, Veolia. Outside of the contract for the subject project, a work order will be established between WisDOT central office and Veolia to manage this material (roll-off boxes, hauling and disposal). | Mike Coleman | 2 | 2022-11-02 16:20 | 2022-11-03 08:07
20221108 | 20221108001 | 1 | Traffic Control Work Restrictions | In the traffic specials it says "entirely clear the traveled way and outside shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic" Does this mean the equipment can be put in the shoulder or does the equipment need to be picked up and removed from the job completely? | All equipment will need to be removed unless placed outside the clear zone. | Mike Coleman | 10 | 2022-11-03 09:21 | 2022-11-04 07:17
20221108 | 20221108049 | 49 | 65 Working Days, | In the specials it states that the utilities need 1. Choice Tel - 2 weeks 2. Frontier - 35 working days We Energies - 20 working days Seems like most of the contract time will be used up by the Utilities? There work should be completed before the contractor even starts! | They will be relocating on the new alignment and the area needs to be grubbed and rough graded before they can relocate their facilities. | Mike Coleman | 6 | 2022-11-03 09:24 | 2022-11-07 08:44
20221108 | 20221108015 | 15 | 211.0400 Prepare Foundation for Asphaltic Shoulders | Since the department anticipates a majority of the existing 3â€™-4â€™ base aggregate shoulders within the project limits would be considered unsuitable material and should be removed and disposed of. Will there be a bid item for 1-1/4" Base to supplement the shoulder material that is removed? | New base aggregate does not need to be supplemented for the disposed of existing 3â€™-4â€™ base aggregate shoulder. It is not imperative to incorporate the existing base shoulder material. The deviation in vertical profile is not critical for this type of improvement project, as long as the Pulverizing Asphalt Base Layer depth is kept relatively consistent. | Mike Coleman | 4 | 2022-11-03 09:37 | 2022-11-04 07:08
20221108 | 20221108033 | 33 | B-51-154 Geotechincal Report | Can a copy of the geotechnical report for B-51-154 please be provided? | The Geotech Report can be found at the following location: https://wisdot.box.com/s/pvro9zrf5f3c0hb335d3red6ndfrf491 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 4 | 2022-11-03 13:37 | 2022-11-04 07:27
20221108 | 20221108028 | 28 | Sawing Asphalt | It appears there will by asphalt sawing cutting required and there is no item for it. Can you provide a revised schedule of items with asphalt saw cutting included? |  |  | 2 | 2022-11-03 16:48
20221108 | 20221108028 | 28 | Removing Asphaltic Surface Butt Joints | It appears there isn't a detail for removing asphaltic surface butt joints. Can you provide a detail? |  |  | 3 | 2022-11-03 16:52
20221108 | 20221108028 | 28 | Preparation of Foundation | After the road has been milled the roadway will need to be prepared prior to paving. Will you provide a Preparation of Foundation Item for that purpose? |  |  | 4 | 2022-11-03 17:03
20221108 | 20221108029 | 29 | Sawing Asphalt | Sawing Asphalt - It appears there will by asphalt sawing cutting required and there is no item for it. Can you add an item to the schedule of items for it? |  |  | 2 | 2022-11-03 17:10
20221108 | 20221108029 | 29 | Removing Asphaltic Surface Butt Joints | It appears there isn't a detail for removing asphaltic surface butt joints. Can you provide one? |  |  | 3 | 2022-11-03 17:12
20221108 | 20221108029 | 29 | Preparation of Foundation | After the road has been milled the roadway will need to be prepared prior to paving. Can you add a Preparation of Foundation item to the schedule of items? |  |  | 5 | 2022-11-03 17:14
20221108 | 20221108032 | 32 | Proposal #32 | Item #0098 646.5105 Marking Word Paint says 1 EA- the plans show 2 "Only" words total Item #0096 646.5005 Marking Arrow Paint says 5 EA- the plans show 6 Arrows total |  |  | 1 | 2022-11-04 11:26
20221108 | 20221108033 | 33 | B-51-154 Rock Core Information | Based on the geotechnical report provided it appears that rock cores were taken, but no information about the rock cores was provided. Can this information please be provided? |  |  | 5 | 2022-11-04 12:23
20221108 | 20221108023 | 23 | 3-INCH HMA PAVEMENT | The plan clearly indicates that the majority of mainline (including shoulder) shall be milled and repaved with 3-inch asphaltic pavement (4 MT 58-28 S). However, installing a one-lift 3-inch 4 MT 58-28 S is nonconforming with the allowable maximum surface thickness (460.3.2). Conversely, installing the aforementioned 3-inch pavement in two lifts does not meet the allowable minimum thickness (460.3.2). Please advise on how the lift/s thicknesses should be bid. |  |  | 2 | 2022-11-04 13:27
20221108 | 20221108022 | 22 | Bid Item14 | The units for the Tack Coat item is listed at tons, quantity appears to be gallons? | An emergency addendum will be issued to change the bid item to gallons. | Mike Coleman | 7 | 2022-11-04 14:53 | 2022-11-07 09:50
20221108 | 20221108020 | 20 | Soils Report | Would you please provide the Soils Report for the project? | The Soils Report can be found at the following location: https://wisdot.box.com/s/orjcil9nn9w04fbd5556wf8dll3qul8x It may also be accessed from the November Bid Letting webpage by clicking the link "Supplemental QA Documents" under the Supplemental Information header. | Jill Fehrman | 1 | 2022-11-04 15:53 | 2022-11-04 15:58
20221108 | 20221108027 | 27 | Base Patching in Intersections | Usually there is a bid item for SHES BASE PATCHING for intersections in order to achieve rapid set times. Is there no base patching in the intersections? If there is base Patching in the intersections, should a SHES BASE PATCHING item be added? If SHES BASE PATCHING isn't added, and there is base patching in the intersections, how should this work be bid? |  |  | 1 | 2022-11-06 10:50