## qandasearchletting_results
Date: | 2022-12-12
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20221213 | 20221213002 | 2 | Earthwork Data | The earthwork data sheets in the plan are blank. Can you provide the missing plan sheets? | The earthwork data sheets will be replaced in an upcoming addendum. | Mike Coleman | 1 | 2022-11-16 07:34 | 2022-11-21 08:10
20221213 | 20221213013 | 13 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - Per City of Madison specifications, the proposed storm sewer would fall under the Type II storm sewer specifications, which includes AASHTO M330 pipe. (Polypropylene) According to the City of Madison, â€œAcceptable applications for usage of Type II storm sewer shall be in areas under pavement in the street where installation allows for a minimum of two (2) foot of cover from the top of the pipe to the top of the basecourse. The maximum allowable size is 36 inch.â€ SSPRC Class III min/max cover heights are identical to SSP Class IIIB within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIB in lieu of the sole specified SSPRC Class III and IV? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 1 | 2022-11-17 11:21 | 2022-11-21 08:01
20221213 | 20221213015 | 15 | Cabinet Controller | In reviewing the special provisions and plans we were unable to locate information on what type of controller is being used for the intersection on this project. Can you please confirm the cabinet signal controller being used for this intersection? (ie. EPAC, ECONOLITE, etc.) | An Econolite controller will be used. | Mike Coleman | 1 | 2022-11-11 08:14 | 2022-11-15 08:22
20221213 | 20221213016 | 16 | Mandatory Pre-bid | Can the mandatory pre-bid attendance requirement be waived to allow for more bidders? Or can there be a second meeting for those who were unable to attend the first one? Can meeting minutes, Q/A, and attendance be shared or provided? | The department held a mandatory pre bid meeting for WisDOT Proposal #20221213016 at 9:00 AM Tuesday, November 15th. An Addendum was processed and posted on 11/10 clarifying the 9:00 am, virtual meeting with call in #, and link. The department will not be holding another pre bid meeting. Question and answers, and the power point presentation can be found at the following location: https://wisdot.box.com/s/v28anz4u02q4bwqyz7z4ou7inejzuyy8 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-11-16 07:35 | 2022-11-28 07:23
20221213 | 20221213016 | 16 | Geotechnical Report | I am with Ram Jack Wisconsin, a helical pile contractor. I was hoping to obtain a copy of the geotech report for this project in order to provide the most accurate bid for the helical pile portion of the project. It was noted in the project documents that a copy of the geotech report could be made available by request. Thank you. | The Geotech Reports can be found at the following location: https://wisdot.box.com/s/v28anz4u02q4bwqyz7z4ou7inejzuyy8 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-11-16 11:52 | 2022-11-18 07:43
20221213 | 20221213016 | 16 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This is a non-highway project on railroad right of way. The requirement for SSPRC Class III will remain as shown in the plans. | Mike Coleman | 3 | 2022-11-17 11:59 | 2022-12-06 06:15
20221213 | 20221213016 | 16 | Mandatory Pre-Bid Meeting Presentation | Can the pre-bid meeting presentation be posted? | The Mandatory Pre-bid Meeting presentation and attendance list can be found at the following location: https://wisdot.box.com/s/v28anz4u02q4bwqyz7z4ou7inejzuyy8 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 4 | 2022-11-18 07:46 | 2022-11-18 08:08
20221213 | 20221213019 | 19 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 1 | 2022-11-17 12:57 | 2022-11-21 08:05
20221213 | 20221213020 | 20 | Project 1146-75-76(77) Schedule | Can Department provide the schedule developed for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/7b1adxa53uiha7x8neu5ym5uav5pcqyp or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-11-14 15:51 | 2022-11-16 06:35
20221213 | 20221213020 | 20 | Embankment Quantity | The preliminary plans show the same embankment quantity as the current bid quantity but there has been fill being placed from Project 1146-75-72 on this project recently. Will the Department be updating the embankment quantity to reflect the fill being placed from project number Project 1146-75-72? | An addendum is currently being prepared that will incorporate final field measurements of the fill placed from ID 1146-75-72 and will include appropriate adjustments in the embankment quantity. | Mike Coleman | 2 | 2022-11-16 13:34 | 2022-11-17 06:56
20221213 | 20221213020 | 20 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | An addendum will be issued to correct this. | Mike Coleman | 3 | 2022-11-17 13:00 | 2022-11-22 09:02
20221213 | 20221213021 | 21 | Department Design Construction Schedule | Could the department provide the design construction schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/nreqxnteo5d2pj8k5qkisambl3q61hbp or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-11-14 14:35 | 2022-11-15 10:18
20221213 | 20221213022 | 22 | Schedule | Contractor is requesting a copy of the DOT's preliminary schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/nreqxnteo5d2pj8k5qkisambl3q61hbp or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-11-17 12:04 | 2022-11-23 09:58
20221213 | 20221213027 | 27 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class II min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class II? | The design team has reviewed Question #1 and will be issuing an addenda to make the following changes: â€¢ The 12â€ and 18â€ SSRCP will be changed from Class II to SSRCP Class III for their respective sizes. â€¢ The 18â€ SS Class III-A will be changed to 18â€ SSRCP Class III. | Mike Coleman | 1 | 2022-11-17 13:15 | 2022-11-23 10:00
20221213 | 20221213029 | 29 | schedule | Can we get the designers schedule please | The design schedule can be found at the following location: https://wisdot.box.com/s/vmutfwqyzdg0s9hbnft90lcw2p7flxqm or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-11-17 14:37 | 2022-11-18 07:39
20221213 | 20221213030 | 30 | Earthwork Data & Soli Borings | Can the Department please provide the soil borings for this project and the earthwork tables in excel format? | Soil borings were only performed at the hill cut (which is related to the ID 6170-00-74 work) and at the proposed box culverts. â€¢ The boring results at the box culverts are shown in the plan. â€¢ Attached are the boring logs for the borings done at the hill cut. Five borings were done on STH 21, and one was done on CTH B. The mileage listed in the station field on the boring logs is the approximate distance from the beginning of the project in Coloma. The borings and earthwork data (excel) can be found at the following location: https://wisdot.box.com/s/eqfunfdif2vgvgpg18narq6yu0avl6f5 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-11-10 14:10 | 2022-11-15 08:28
20221213 | 20221213032 | 32 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2022-11-17 13:29 | 2022-12-06 10:31
20221213 | 20221213037 | 37 | Existing Fence | Is the removal and replacement of the fence incidental to another item? | The remove and replace fence note is being removed from the plans via an upcoming addendum. | Mike Coleman | 1 | 2022-11-15 16:51 | 2022-11-17 06:54
20221213 | 20221213037 | 37 | Fencing, cattle pass, utility conflicts, excavation | Hi, I saw the first question- the bridge has private fencing attached to it and the area under the bridge is used as an active cattle pass. Is the fencing related item being removed from the contract because it is covered under a separate agreement? Can a copy of the agreement be provided? There are no provisions made in the riprap for the cattle pass. Has this been addressed with the landowner? When constructing the east abutment, the power lines overhead power lines will be in conflict with the crane, as there will be no place to lay down or pick up a pile driver. They should be moved to the east. Can this please be addressed? Lastly, the excavation for structure for the west abutment, when dug to plan, will begin to impede the traffic lane on Rumple Lane. We believe barrier wall should be added to the traffic plan for safety reasons. Our site measurements indicated 60-75 LF would be appropriate. Does that agreement address the cattle pass? | The fencing encroachment will be removed by the Town prior to construction. If the landowner desires to move cattle under the creek in the future, they will utilize the existing stream channel similar to existing conditions. No special provisions are needed. Riverland Energy does not believe there will be a conflict, however, Riverland Energy has previously noted they would be willing to provide coverup on this line during construction if it would aid the contractors means and methods. The contractor will need to coordinate with the Utility. Rumpel lane can be reduced to a single lane of traffic during construction. It was anticipated this would be delineated with drums during construction. See response to question 1. | Mike Coleman | 2 | 2022-11-17 11:05 | 2022-11-17 14:35
20221213 | 20221213029 | 29 | Traffic on HWY 45 | Will the department consider closing hwy 45 during the complete reconstruction of B-43-64? Once the concrete barrier is placed, work on concrete masonry endwalls would need to be done under flagging operations. There isn't sufficient room to safely get equipment between the temporary barrier and the temporary barrier to perform the work. Cofferdam installation would also have to utilize one lane of traffic. Cost savings would be significant if the road were to be closed. The need for concrete barrier, crash cushions, flagging, and possibly some of the temp. shoring could be eliminated. Is it the intent of the department to have most of this work done under flagging? | The intent is to close USH 45 as shown in the plan and special provisions. Flagging operations will be needed for work operations that need closures outside of the timeframes of the full closures of USH 45. | Mike Coleman | 2 | 2022-11-18 10:14 | 2022-11-22 09:01
20221213 | 20221213016 | 16 | Structural Steel Fabricators | The structural steel specifications show that the steel fabricator must be on the APL for steel bridge primary members, however the majority of the construction for this project is building steel, stairs/rails and the canopy. There are potential fabricators who are AISC shop carrying the Standard Building Certification, but do not have a Bridge Cert, although large trusses, canopies, and very complex fabrications are normal work. Will there be any exceptions to the C.2 note in the Steel Specification. It will be difficult to find steel fabricators for this project from the APL as the majority of the fabricators listed are primarily bridge steel focused. | Fabrication by fabricators on the Approved Products List (APL) will only be required for the bridge truss structural steel. This specification will be revised in an upcoming addendum. | Mike Coleman | 5 | 2022-11-18 14:29 | 2022-12-06 06:18
20221213 | 20221213024 | 24 | Line item 96 Concrete Masonry Endwalls | Not seeing any details on line item 96, Concrete masonry endwalls 16 cy. Or Bar steel reinforcement for that item. | A plan detail showing the culvert pipes and concrete masonry endwalls at Station 123+71 is missing from the plan. Concrete Masonry Endwalls layout and bars steel reinforcement will be following Standard Detail Drawing â€œConcrete Masonry Endwalls for Culvert Pipe and Pipe Archâ€. The standard detail drawing is located on page 72 of the plans. An addendum will be forthcoming with the plan detail. | Mike Coleman | 1 | 2022-11-22 09:42 | 2022-11-28 08:54
20221213 | 20221213018 | 18 | 0254 - Urban Tree Planting System | Will the City of West Allis allow an equal alternative such as Stratavault to the sole specified root cell system? If more information is desired, who can this be sent to? Thank you, | The City of West Allis prefers to use the Arborsystem ï¿½ - Urban Tree Planting System, Item SPV.0025.01 as specified in the contract documents. Contractors should bid it as such. | Mike Coleman | 1 | 2022-11-23 09:40 | 2022-11-28 08:55
20221213 | 20221213024 | 24 | Plan Details- Culverts | There does not appear to be a plan detail sheet culverts for the work located at station 123+71 Can this be provided? | A plan detail showing the culvert pipes and concrete masonry endwalls at Station 123+71 is missing from the plan. An addendum will be forthcoming with the plan detail. | Mike Coleman | 2 | 2022-11-23 10:35 | 2022-11-28 08:54
20221213 | 20221213017 | 17 | Design schedule and other | Can a design schedule, Electronic CAD files, and any geotechnical or soil borings available be provide? | The design schedule and geotechnical reports can be found at the following location: https://wisdot.box.com/s/t1pa0o2pv79nxq7g60eycjhzubp2mk6v or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One is Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. For each month going forward, available Contractor Data Packages will be on the letting pages at the time of advertisement. | Mike Coleman | 1 | 2022-11-23 12:32 | 2022-11-28 07:56
20221213 | 20221213017 | 17 | Award of contract | Does the department believe there is enough time after award to fully execute the contract, get all accompanying documentation submitted and approved, hold meetings, layout, close road, set BMPâ€™s, etc. in order to meet the March 1st bridge demo date? If the department takes a 4-5 weeks to award the job plus the 5 â€“ 6 weeks to execute the contract there will be very little time to accomplish this. The department has been slower to award projects than previously. | We process these as quickly as possible. Time sensitive projects will be made a priority. | Mike Coleman | 2 | 2022-11-23 13:32 | 2022-11-30 06:44
20221213 | 20221213017 | 17 | Bedrock | What is the rock excavation item specifically intended for? Its currently identified under excavation as undistributed. If bedrock is encountered during storm sewer installation, electrical base/conduit installation, or any excavation outside the proposed cross sections will that be paid separately? Is it anticipated that bedrock will be encountered during the excavation for bridge structure? | Soil borings near the project identified bedrock depths varying between 8â€™ and 41â€™ in the project corridor. The highly variable depth of the bedrock identified a potential need for rock excavation, but specific locations have not been identified. Rock excavation on the project will be paid for as: â€¢ 206.1000 Excavation for Structures Bridges B-51-0157 â€“ Rock encountered during excavation for the bridge over the Root River per Standard Specification 206.3.1 (1) â€¢ 205.0200 Excavation Rock â€“ Undistributed quantity for elements in the cross sections including ditching for the project. â€¢ 608.0005 Storm Sewer Rock Excavation â€“ Undistributed quantity will be added in an upcoming addendum to address question of how rock excavation for storm sewer is paid for. | Mike Coleman | 3 | 2022-11-23 13:45 | 2022-11-30 06:40
20221213 | 20221213017 | 17 | WE Energies Gas | The WE Energies work listed in the specials is very extensive and will fall into the critical path of construction. Did the department take the 25 working days or 10 working days into account when assembling the design schedule that dictates the completion dates of the project. Additionally, are these guaranteed to be consecutive working days? | The construction schedule posted today shows 25 working days for We Energies gas between the pouring of the deck and the construction of the approach slabs to the structure. Based on the coordination with We Energies gas the 25 working days is a conservative estimate for the installation of the main across the structure and are consecutive working days. | Mike Coleman | 4 | 2022-11-23 14:14 | 2022-11-28 08:06
20221213 | 20221213039 | 39 | Landmark Reference and Landmark Reference Monuments | There are 9 section corners on this project. Should the item be added to the bid to preserve these section corners? | No, because the County Surveyor will re-establish section corners. | Mike Coleman | 1 | 2022-11-28 09:19 | 2022-11-29 06:49
20221213 | 20221213020 | 20 | Asphaltic Surface Driveways and Field Entrances- Bid Item 0062 | For project #77, the estimate of quantities show 366 tons while the miscellaneous quantities do not list any. Additionally, the plan set does not show any paved driveways or field entrances. Will there be any asphaltic driveways on project #77? | The Asphaltic surface driveways and field entrances bid item will be removed from the estimate of quantities in Addendum #2. | Mike Coleman | 4 | 2022-11-28 11:53 | 2022-11-28 13:13
20221213 | 20221213025 | 25 | Clearing and Grubbing and Staking | 1. How are clearing and grubbing to be paid? 2. How will staking be performed and paid? | 1. Clearing and grubbing are incidental to the fencing items. 2. Staking is covered under SS 105.6.1. Alignment information is also included in the planset. | Mike Coleman | 1 | 2022-11-28 12:19 | 2022-11-28 12:20
20221213 | 20221213020 | 20 | Sign Structure S-44-114 | It appears that only drawings for S-44-113 were included in the plan. Please provide the General Layout sheet for S-44-114. | General layout sheet for S-44-114 will be included in addendum #2. | Mike Coleman | 5 | 2022-11-28 14:08 | 2022-11-29 08:07
20221213 | 20221213021 | 21 | Item #18 Removing Concrete Pavement Butt Joint | Plan 1210-11-71 shows 100â€™ concrete milling transition with a 2â€™ pay limit? The miscellaneous quantities appear to only figure the 2â€™. The other 98â€™ does not appear to be accounted in any other item? Plan 1210-09-71 shows 50â€™ concrete milling transition with a 2â€™ pay limit on CTH GV. The miscellaneous quantities appear to figure the full 50â€™? What is the correct pay limit? Will the full butt joint length be paid under this item? | The concrete butt joints will be paid for the full length of the transition. The plans will be updated through a future addendum. | Mike Coleman | 2 | 2022-11-28 14:34 | 2022-12-05 06:34
20221213 | 20221213021 | 21 | #52 Removing Asphalt Surface Milling Special | The structure plans show inside and outside wing walls being replaced at on STH 172 EB at CTH XX (B-05-178) but there is no staging or milling quantity figured to remove outside rumbles for the inside wing wall work? Will this be added/ required? | Yes, removing the outside rumbles will be required at this location. The plans and quantities will be updated through a future addendum. | Mike Coleman | 3 | 2022-11-28 14:37 | 2022-12-02 09:30
20221213 | 20221213021 | 21 | Item #128 4 MT 58-28 S | The typical's on all ramps show the lower wedge layer to be 4 HT other than the IH - 41 Ramps where this 4 MT quantity is figured. Would the department consider eliminating this item and change it to 4 HT? | The 4 HT 58-28 S mix will be allowed on the IH 41 ramps. The plans and quantities will be update through a future addendum. | Mike Coleman | 4 | 2022-11-28 14:41 | 2022-12-02 09:31
20221213 | 20221213021 | 21 | Item #136 Asphaltic Surface | In the miscellaneous quantities where is the asphaltic surface quantity expected to be used that is figured on the mainline portion of STH 172 in both plans 1210-09-71 and 1210-11-71? It appears to correlate with the asphaltic milling special items for the rumble strip removal and shoulder repair but based on those square yards and locations that actual mix calculated is approximately 15% of what is figured in the quantities? Are there other areas this was figured for? | There was an error in the formula quantifying the asphaltic surface quantity. The asphaltic surface quantity should be for the rumble strip areas. An updated quantity will be issued through a future addendum. | Mike Coleman | 5 | 2022-11-28 14:42 | 2022-12-02 09:28
20221213 | 20221213021 | 21 | Mainline Inside Shoulder Paving | In locations where the inside shoulder is 5â€™-7.25â€™ on STH 172 EB/WB and IH 43 & I-41 Ramps, would the department consider changing this mix type from 4 LT to match the inside lane (4 HT/4 SMA) to allow the shoulder to be paved in conjunction with the inside lane (as done on I-43 and I-41), eliminating a cold joint and additional operation? | The shoulders will be allowed to be paved integral with the mainline as long as there is a break in slope. A future addendum will address the change in mix type for the inside shoulders where they are less than 8â€™ to match the mainline mix type. | Mike Coleman | 6 | 2022-11-28 14:43 | 2022-12-02 09:20
20221213 | 20221213021 | 21 | Pilgram/Vanderperren/Riverside/Webster/CTH GV Ramps | Would the department consider changing the surface mix type on these ramps from SMA/4 LT to entirely 4HT? In past projects (I-43, I-41) the ramps have not been paved with SMA but with a 4 HT. This would allow the ramps to be paved in echelon eliminating all cold joints. | The service interchange ramps (Pilgrim/Vanderperren/Riverside/Webster/CTH GV) will be allowed to change to all 4 HT 58-28 S mix design. The system interchange ramps at I-41 and I-43 will remain a SMA over 4 HT mix. A future addendum will address the change in mix type. | Mike Coleman | 7 | 2022-11-28 14:43 | 2022-12-02 09:39
20221213 | 20221213021 | 21 | Riverside/Webster/ CTH GV/ South Point/ Babcock/ Packerland HMA Mix | The plans call for 4 SMA on the surface of Riverside, Webster, and CTH GV. Due to the nature of the SMA mix design, raking and hand work of the material is extremely difficult, and a material transfer machine is required by spec to minimize segregation. With the geometry of these areas and the short lengths, paving with SMA is not constructible and will likely result in an undesired finished product. Would the department consider changing this mix to 4 HT? On 1210-11-71 there is not a mix specifically called out for the intersections of South Point, Babcock, and Packerland. The Contractor requests that these locations as well as the inside turn lanes and intersections, be switched to a 4 HT or 4 MT mix for same reason as above. | The sideroads and intersections on both project IDâ€™s will be allowed to change to all 4 HT 58-28 S mix design. This mix type will be allowed at the Packerland and Babcock slotted left turn lanes as well. A future addendum will address the change in mix type. | Mike Coleman | 8 | 2022-11-28 14:46 | 2022-12-02 09:35
20221213 | 20221213030 | 30 | Pulverize Questions | With the unknown varied sections of pavement thicknesses that will be required to pulverize, will split lifting be required for compaction? In past projects, pulverized material that was hauled offsite was paid for under â€˜excess pulverized materialâ€™ item. Could this item be added to this project? | Region reviewed and discussed with BPD construction. We are comfortable with the spec as written which leaves flexibility with the contractor. They could waste some material in shoulder, if they choose, which would benefit the region or choose to haul. | Mike Coleman | 2 | 2022-11-28 17:00 | 2022-12-01 14:42
20221213 | 20221213017 | 17 | B-51-157 Pre-boring Quantity | Sheet (1) of the B-51-157 plans calls out a 15' estimated pile length. There are (34) piles in each abutment. Assuming pre-boring length is to be the same as estimated pile length 34x15= 510 LF. The plan quantity for pre-boring at each abutment is 160 LF. Please advise if this is an error in plan quantity? | BOS has reviewed the B-51-157 pre-boring quantity. The estimated pre-boring length per abutment pile is 10 LF (computed from bottom of abutment to the pile tip elevation), so 340 LF per abutment and 680 LF total. The quantity will be revised in an upcoming addendum. | Mike Coleman | 5 | 2022-11-29 07:40 | 2022-12-01 06:35
20221213 | 20221213005 | 5 | Permanent Pavement Markings | Good morning, this project butts right up against #006 (5215-00-67) from March letting. Being #006 (5218-00-67) from March has wet reflective edge lines, would it make sense to change the edge lines on this project to match the project (5215-00-67) it butts up against? Will an addendum be issued to change the edge lines to wet reflective? Thank you. | An addendum will not be issued to change the edge lines to wet reflective. Due to the roadway ADT being below 1,500 vehicles per day for Proposal 20221213005, the Departmentâ€™s pavement marking policy is to install the edge lines as standard epoxy. | Mike Coleman | 1 | 2022-11-29 10:24 | 2022-11-30 14:21
20221213 | 20221213008 | 8 | Crossover Details | Can you provide a typical section, locations on the plan and profile sheets, and cross sections for the crossovers? | Additional crossover detail will be added via addendum. | Mike Coleman | 1 | 2022-11-29 12:04 | 2022-12-01 14:39
20221213 | 20221213020 | 20 | No ASP-5 | This project should have ASP-5 Fuel Cost Adjustment due to embankment quantity. Please add. | An addendum will be issued to add ASP-5 | Mike Coleman | 6 | 2022-11-29 16:04 | 2022-11-30 08:44
20221213 | 20221213021 | 21 | Deck Patching Material | Plans are calling for standard item Concrete Masonry Deck Repair to fix any deteriorated concrete in the decks on the structures. Standard bid item calls for these patches to be Grade C or Grade E concrete, but the roadway will have to be open to traffic the following morning. Is the intent to use SHES deck patching materials for these repairs? | The intent is to use a rapid set concrete for the deck repairs. The updated bid item will be included in the future addendum. | Mike Coleman | 9 | 2022-11-30 08:34 | 2022-12-02 09:36
20221213 | 20221213021 | 21 | Item #556 - Cleaning Box Culvert, B-05-184 | Consider changing the unit of measure for this item to CY or clearly define limits of excavation upstream and downstream to protect all parties. | The bid item for Cleaning Box Culvert B-05-184 will remain an EACH item. The limits of cleaning will be limited to within the box cells and endwalls. No excavation outside of the endwalls will be required. Additional clarification will be added to a future addendum. | Mike Coleman | 10 | 2022-11-30 08:58 | 2022-12-02 09:36
20221213 | 20221213016 | 16 | Helical Pile Shaft Size and Coatings | The plans call for a minimum 3.5" helical pile shaft but the loads given in the plans allow for our Ram Jack 2 7/8in helical pile shafts to meet the load requirements with a 3:1 safety factor as outlined in the Geotech report. Is it okay to substitute our 2 7/8in diameter piles for the 3.5in diameter piles spec'd in the plans. The specifications say that the helical piles should be galvanized. Could our piles, coated with a polyethylene copolymer coating complying with the ICC-ES Acceptance Criteria for Corrosion Protection of Steel Foundation Systems Using Polymer (EAA) Coatings (AC228), and having a minimum thickness of 18 mils (0.46mm) as described in the approved quality documentation be utilized in lieu of galvanized steel? | The minimum helical pile shaft size requirement will be removed from the plan sheets via an upcoming addendum. The specification for galvanized helical piles will remain and should be bid in accordance with the contract documents. | Mike Coleman | 6 | 2022-11-30 14:07 | 2022-12-06 06:19
20221213 | 20221213022 | 22 | Existing Box Culverts Asbuilts | Could asbuilts be provided for existing box culverts that are scheduled to be removed? | The as-builts can be found at the following location: https://wisdot.box.com/s/dg6kns4dsk1xvs0uql8c276uujqiztgy or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-11-30 14:25 | 2022-12-07 08:45
20221213 | 20221213021 | 21 | Concrete Pavement 9-Inch Quantities | Please check & verify the plan quantity for 415.0090 Concrete Pavement 9-Inch on the IWS Ramp. Sheet 86 of the plan set. | The concrete quantity for the IWS ramp is high in the plans. The updated concrete total (2,420 SY) will be included in a future addendum. | Mike Coleman | 11 | 2022-11-30 15:49 | 2022-12-02 09:37
20221213 | 20221213021 | 21 | IWS Ramp | Can the waste dirt for the IWS Ramp be placed in a gore area in the same location? | Any waste site proposed needs to follow the approval procedures for disposal sites in standard specification 107. The DOT cannot approve any proposal until the environmental impacts are known and agency coordination is completed. | Mike Coleman | 12 | 2022-11-30 21:12 | 2022-12-05 06:27
20221213 | 20221213013 | 13 | Lane Closures & Staging | Page 9 of the Special Provisions under "General Traffic Operations During All Stages" says to maintain a minimum of one single lane of eastbound traffic at all times on Atwood Avenue between Fair Oaks and Walter during Stages 3 & 4. Page 15 of the Special Provisions under Stage 3A - Segment 1 says we are closing Atwood for that Segment, this also appears to align with what is shown on the plans. Which is correct? | Page 9 of the Special Provision should read â€œ Maintain a minimum of one single lane of eastbound traffic at all times on Atwood Avenue between Fair Oaks Avenue and Ludington Avenue during Stage 3 for bus access onlyâ€ Page 15 of the Special Provisions for 3A-Segment 1 and the plans for Stage 3 are correct. | Mike Coleman | 2 | 2022-12-01 08:32 | 2022-12-05 06:47
20221213 | 20221213022 | 22 | Culvert Pipes | Some of the pipes on Miscellaneous Quantities Table and Plan sheets show different pipe material. Could it be clarified what is desired? | The Miscellaneous Quantities table shows Reinforced Concrete pipe for some locations where concrete pipe is necessary. The rest of the culvert pipes are only classified as non-metal, the choice of the pipe material is up to contractor. | Mike Coleman | 3 | 2022-12-01 09:47 | 2022-12-07 08:32
20221213 | 20221213018 | 18 | Concrete Paver at Roadway Terrace Limits | Shown in the plan set on Sheet 53 Sta. 13+86 to 14+40 LT Approximately, The area is hatched in Grey, with the Note Circle 13 Concrete Paver Layout at Roadway Corner. This area is also shown on plan sheet 22 with 5" Concrete walk jointing and slope grades. It is also shown on plan sheet 18 called out as SW 5 the delineation for 5" Concrete sidewalk. Requesting clarification on this area, if it is to be Concrete Pavers with base or 5" Concrete sidewalk? | The area in question is to be constructed with concrete pavers with base as depicted on the Streetscaping Layout and Materials Plan (page 53). There is a small area that is shown on sheet 53 at the corner that is unshaded that contains Detectable Warning Fields. This small unshaded area is Concrete Sidewalk 5-Inch to allow easier placement of the DWFâ€™s. The small shaded triangular area between the curb ramps at this corner is to be constructed with concrete pavers and base. | Mike Coleman | 3 | 2022-12-01 10:24 | 2022-12-02 09:42
20221213 | 20221213031 | 31 | Pulverized Material | On the finished typical section for STA 4+54 - 44+43 there is a note stating to pulverize existing asphalt and remove 3" of the pulverized material. Can 3" be milled off the road prior to pulverizing? | No the 3â€ of material that needs to be removed can not be milled off prior to pulverizing. This would change the ratio of asphaltic material to BAD in the pulverized material reducing the structural strength of the pulverized material in the pavement structure. | Mike Coleman | 1 | 2022-12-01 10:26 | 2022-12-05 13:11
20221213 | 20221213018 | 18 | Earthwork Table | In The earthwork table under the salvaged/unusable pavement column, did the design engineer include the asphalt overlay quantity in the salvaged / unusable pavement qty? Or is the Asphalt overlay material quantity still included in the Cut quantity? | The Salvaged Unusable Pavement Material column includes the volume of concrete items (pavement, curb & gutter and sidewalk). The Cut column includes all excavated material (including the existing asphalt overlay). | Mike Coleman | 4 | 2022-12-01 10:27 | 2022-12-02 09:44
20221213 | 20221213009 | 9 | Culvert Pipe Backfill | The detail on sheet 16 calls for backfill granular grade 2 for backfill of culvert pipes. Will the contractor be allowed to use dense graded base course for backfill as allowed in standard spec 520.2.5.2.2? | Since the contractor is being paid separately for backfilling the triangular portions of the cross-drain excavation, the contractor will be allowed to substitute backfill material with a gradation conforming to the ï¿½-Inch Base Aggregate Dense or 1-1/4-Inch Base Aggregate Dense gradation requirements as laid out in Standard Spec 305.2.2.1 at the discretion of the engineer. Dense graded base course would be allowable in both the foundation backfill (rectangular) and trench backfill (triangular) portions of the cross-drain installation excavation area as long as the material substitution doesnâ€™t become cost-prohibitive for the project. | Mike Coleman | 1 | 2022-12-01 11:45 | 2022-12-07 13:59
20221213 | 20221213016 | 16 | Station Elevators | The rated speed of travel specified, 350 FPM, appears unobtainable for the distance traveled, 24â€™-10 3/8â€ by engineering. For the application provided, we would recommend and ask for approval of a rated speed of 200 FPM. | The station elevator rated speed of 200 FPM will be allowed. This requirement will be revised in an upcoming addendum. | Mike Coleman | 7 | 2022-12-01 13:04 | 2022-12-06 06:19
20221213 | 20221213026 | 26 | Uneven Lanes | Per page 2 of the special provisions, 'provide an even cross-sectional profile of each lane prior to reopening to traffic. Uneven lanes are not allowed except within a flagging operation.' If the contractor uses a tapered longitudinal joint at centerline, which negates the greater than 2" drop off, would uneven lanes then be allowed? | The language is referring to each travel lane. It Is not referring to the centerline joint. An uneven profile within each lane is not allowed except within a flagging operation. The centerline joint shall meet drop-off requirements listed in the standard specifications. | Mike Coleman | 1 | 2022-12-01 14:21 | 2022-12-05 06:31
20221213 | 20221213029 | 29 | Asphaltic Curb | The asphaltic curb shown in the construction details, with a cross section to match that of concrete curb & gutter 4-inch sloped 36-inch type D is not constructible as shown. Equipment is not available to machine-place this curb with asphalt to match the detail of concrete curb and gutter. And, due to the location at the bottom of a slope behind beam guard, with limited access, the only option will be to hand-form this asphalt, which is unlikely to achieve the cross-sectional shape desired. Would the department please consider replacing this asphalt curb with a concrete surface drain, or asphaltic flume, or allow hand-shaping of the asphalt curb to achieve the desired flow? | Hand shaping to achieve approximately the desired cross section and achieve the desired result would be acceptable. The intent is to make the asphaltic curb mountable and channelize surface water to the existing flume in this area. | Mike Coleman | 3 | 2022-12-01 14:24 | 2022-12-05 11:33
20221213 | 20221213029 | 29 | Item for Butt Joints is Missing | Will the Department be adding an item for Removing Asphaltic Surface Butt Joints where the milled surface will be matching into the existing pavement at STA 427+00 and 448+13.5? | Agree, item will be added by addendum. | Mike Coleman | 4 | 2022-12-01 14:29 | 2022-12-05 11:35
20221213 | 20221213029 | 29 | Shaping Shoulders | The areas where the HMA pavement on USH 8 will be milled and widened to the new final width of 34-ft or greater, a note in the typical sections calls out "Shaping Shoulders Typ" (See Sheet 6). Will the standard bid item for Shaping Shoulders be added to the job? | The standard bid item for Shaping Shoulders will not be added to the contract. The removal of the extra material to widen the roadway is accounted for in the item of Common Excavation. An addendum will be issued to update this Typical Section to remove this note. | Mike Coleman | 5 | 2022-12-01 14:33 | 2022-12-05 11:42
20221213 | 20221213029 | 29 | Match point between Reconstruct Section and Milling Section | The typical sections show the reconstruct section extending from STA 429+50 to 443+00, with milling occurring outside of that range. The staging, as written out in Article 3, and as drawn in the Traffic Control plan sheets, show constructing pavement to 443+50 to accommodate the staging and positioning of traffic; this would be 50-ft beyond the end of the reconstruct limits, according to the typical sections. Is it the designerâ€™s intent for the contractor to perform milling from STA 443+00 to 443+50 in each of the respective stages to build the typical section shown, or will the match point between the reconstruct section to the milling section be moved to STA 443+50? | The reconstruction limits should be STA 443+00. An addendum will be issued to correct the Special Provisions and Plan accordingly. | Mike Coleman | 6 | 2022-12-01 14:35 | 2022-12-05 11:49
20221213 | 20221213029 | 29 | Staging for Curb & Gutter Construction | The project staging does not identify a stage for the construction of the curb and gutter and related items from STA 427+40 to 428+91. The construction staking summary in the Miscellaneous Quantities identifies this work as Stage 7, but the Traffic Control plan sheets for Stage 5 show this work as previously completed. Is the Departmentâ€™s intent to allow overlap of staging to complete this work? And without a work-zone defined in the staging plan sheets, is it the Departmentâ€™s intent for this work to be constructed under flagging operations outside of allowable traffic staging? | The timeframe for constructing curb and gutter in this area can happen in either Stage 5, 6, or 7. The curb and gutter will need to be constructed under flagging operations outside of the traffic staging area. | Mike Coleman | 7 | 2022-12-01 14:37 | 2022-12-05 11:50
20221213 | 20221213026 | 26 | Asphaltic Surface Patching | What will the Asphaltic Surface Patching item be used for? Can you provide a detail and locations where the item is intended? How will the removals be paid for? | The intent of the Asphaltic Surface Patching item is patching for base repairs prior to the surface lift and filling potholes or pop outs that occur under traffic handling. Locations will be identified in the field by the engineer after asphaltic surface milling operations. If additional asphalt beyond the 2â€ milling is required to be removed, it will be paid for under item 204.0120 â€œRemoving Asphaltic Surface Milling.â€ | Mike Coleman | 2 | 2022-12-01 14:40 | 2022-12-05 06:32
20221213 | 20221213028 | 28 | Earthwork Table | The available material for Division 3 at Sta 604+58 - 609+26 and Sta 1010+25 - 1014+95 is listed as 0 cy. Please review and confirm that this correct. | This is in error and was not linked correctly in the spreadsheet. The material is available for use and thus the borrow should be reduced 416 CY. An addendum will be issued to correct this. | Mike Coleman | 1 | 2022-12-01 14:57 | 2022-12-02 09:40
20221213 | 20221213036 | 36 | Temporary Paint | Good Day, Would the Department permit the use of temporary paint in lieu of temporary tape in the traffic control in stage one? We have had challenges in the past keeping the tape in place in narrow construction lanes, requiring nearly daily tape maintenance, and multiple return trips for traffic control. This would be likely for stage one when temperatures are cooler and tape has adhesion has proven to be difficult. If permitted, would it be paid under 643.3150 Temporary Marking Line Removable Tape 4-Inch, or 643.3105 Temporary Marking Line Paint 4-Inch? | The plan details were developed to minimize damage to existing pavement that will remain due to removal of temporary pavement markings. If the type of temporary pavement markings are modified during construction, provisions may need to be made to repair damaged pavement. | Mike Coleman | 1 | 2022-12-01 15:28 | 2022-12-08 06:12
20221213 | 20221213027 | 27 | 6" Under Drain Removal | The existing 6" Pipe Under Drain shown in the Existing Typical Section shows being removed in the new Typical Section, will this be incidental to the Common Excavation bid item to remove the 6" Pipe Under Drain? | The removal of the 6â€ Under Drain is incidental to the common excavation bid item. | Mike Coleman | 2 | 2022-12-01 15:51 | 2022-12-05 11:51
20221213 | 20221213031 | 31 | Intersection Pavement Type Clarification | The Typical Sections indicate intersections upper layer to be 4MT with 58-34V oil. But, Miscellaneous Quantities show the intersections to be 4MT with 58-34H oil on the upper layer. Could the department verify the intersection upper layer is to be 4MT 58-34H? | The HMA pavement mix needed for the sideroad upper layers is 4MT with 58-34V oil. The Miscellaneous Quantities are not correct and will be updated with an addendum. | Mike Coleman | 2 | 2022-12-02 08:27 | 2022-12-05 13:11
20221213 | 20221213020 | 20 | Rock Excavation | Where exactly is the 120 CY of rock excavation? I do not believe it is shown in any of the cross sections for old sth 15 west from station 50+00 to 69+50. If rock is found on any of the stream realignments how will it be paid? | The Rock Excavation shown in the plans is for the stream realignments. None of the Rock Excavation shown in the plans is for structure excavation per Section 206.3.1 206.3.1 General (1) Under the Excavation for Structures bid items, excavate material of whatever nature encountered. The department will not classify this excavation as common, rock, or marsh excavation under 205 or as dry or wet excavation. Further clarification on the Rock Excavation will be provided in an upcoming addendum. | Mike Coleman | 7 | 2022-12-02 11:31 | 2022-12-06 06:17
20221213 | 20221213022 | 22 | schedule | Could the proper schedule be posted in box as the schedule linked is for the 172 project #21? | The design schedule can be found at the following location: https://wisdot.box.com/s/dg6kns4dsk1xvs0uql8c276uujqiztgy or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2022-12-02 11:55 | 2022-12-05 06:59
20221213 | 20221213020 | 20 | Existing & Proposed Culvert Cross Sections at Proposed Reference Line | Please provide an updated cross section view & elevation view of C-44-124, C-44-126 and C-44-21-59 showing both the existing ground line and proposed finish ground line. The plan & profile, cross sections nor structure plans show an accurate depiction of the existing vs proposed ground lines. | Requested cross sections will be provided in an upcoming addendum. | Mike Coleman | 8 | 2022-12-02 15:07 | 2022-12-06 06:16
20221213 | 20221213021 | 21 | Item #94 Base Patching Asphaltic for HMA Layer Interlayer | The plan sheets for 1210-11-71 state that â€œRepair locations shown for information only. Final locations to be determined by the engineer.â€ Milling and HMA patching of the cracks and joints of this 2.7 mile stretch, including the I-41 to STH 172 ramps, are all included in the lump sum item, Base Patching Asphaltic for HMA Interlayer, to be determined by the engineer. Contractor has no way to estimate this. Can the department give a quantity for this item and changed the item to a unit price of lineal foot (LF)? | The Base Patching Asphaltic for HMA Interlayer will be changed to a LF item and an updated quantity total will be provided. New guidance for these bid items will be provided in a future addendum. | Mike Coleman | 13 | 2022-12-04 11:23 | 2022-12-06 06:14
20221213 | 20221213024 | 24 | Schedule | Can the Department provide a Design Schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/onddso51ee4riv72tdnqjdzb3ohzj6t0 or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2022-12-05 08:20 | 2022-12-06 06:11
20221213 | 20221213021 | 21 | Item #562 - Concrete joint and Crack Cleaning and Repair | This is an SPV item. I cannot find the description. Could this item be addressed? | Special provision and construction detail for Concrete Joint and Crack Cleaning and Repair will be added to a future addendum. | Mike Coleman | 14 | 2022-12-05 12:32 | 2022-12-06 06:13
20221213 | 20221213009 | 9 | Cleaning and Culvert Pipe Liners | Can you confirm which culverts are getting lined? The stations for the pipe requiring the liners do not match with any of the stations for the required cleaning for liner verification. Thanks | The pipe liner and pipe cleaning items will be clarified in an upcoming addendum. | Mike Coleman | 2 | 2022-12-05 13:27 | 2022-12-07 13:59
20221213 | 20221213020 | 20 | Removing Concrete Pavement Item | Based on the existing typical section for STH 15, there is concrete pavement under the asphalt. There is no bid item for Removing Concrete Pavement. Also, the Available Material in the earthwork summary table calls out that it is the Cut - Salv/Unusuable Material, yet there is no difference in quantity from the Cut quantity. Could you provide clarification? | These questions will be addressed in an upcoming addendum. | Mike Coleman | 9 | 2022-12-05 14:06 | 2022-12-06 10:35
20221213 | 20221213018 | 18 | Borings | Were borings in the existing pavement performed and if so are the results available? | There were 3 borings. The geotechnical reports can be found at the following location: https://wisdot.box.com/s/w6gttaclfd5uktg07oo455pua3avrzd4 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 5 | 2022-12-05 14:52 | 2022-12-06 10:38
20221213 | 20221213001 | 1 | Interim Completion | Would the Department allow the Curb, sidewalk, and curb ramp construction to be done prior to the 15 day detour. Curb ramp areas are required to be built half at a time, with the staging and the cure time we do not feel the milling and paving will also fit in the time allowed. Thanks | Curb and gutter, sidewalk, and curb ramp work may be started prior to the Stage 1 closure. All curb and gutter work shall be completed prior to paving STH 80. The total working days in the contract will remain unchanged. An addendum will be issued to revise the special provisions. | Mike Coleman | 1 | 2022-12-05 15:28 | 2022-12-07 14:03
20221213 | 20221213013 | 13 | 656.0201 Electrical Service Meter Breaker | Th current lead time for this item is 80 weeks. There is no alternate made by any other manufacturers. How should we bid this and how should we expect the late delivery of this item to be handled at project completion? | This question will be addressed via an emergency addendum to include Remove, Salvage, and Reinstall existing Electrical Service Meter Breaker Pedestal as a bid item. | Mike Coleman | 3 | 2022-12-05 16:27 | 2022-12-09 04:47
20221213 | 20221213036 | 36 | Prosecution and Progress | Would the Department permit a start date early enough in the season for the contractor to complete Stage 1 in-stream activities prior to March 15th, and allow stage 2 work in "flowing or standing water" to be started after May 15th but end prior to June 23rd? This would allow the contractor to avoid conflicts with the Cricket Frog BITP, eliminate 50% of the need for bird deterrence, and allow for clearing to be performed in concurrence with the Northern Bat guidelines for a timeframe. | The proposed timing appears to fit within the timing constraints listed in the Special Provisions. The timing of the project will ultimately be approved by WisDOT and WDNR after a contract is awarded and more details are provided about the work activities. A few items to note regarding an early project schedule are as follows: â€¢ Based on the Standard Specs, Working Days would not be charged for the early work. The contract would likely end up with extra leftover working days. â€¢ There may be concerns with Traffic Control and single lane signalized bridges during winter months. â€¢ The application of temporary markings for stage 1 traffic would need to be reviewed and approved by the engineer â€¢ BIPT restrictions for the BCF will still apply for the Native Seeding requirements. | Mike Coleman | 2 | 2022-12-05 16:30 | 2022-12-07 07:12
20221213 | 20221213031 | 31 | AC Type | Will the department consider making both the turn lanes and intersections the same oil type as they would typically be paved at the same time. This will eliminate the need to either A) bid it that way or B) pave them in 2 operations. | The mainline, turn lanes and sideroads will use the same mix types for the top layer. Use 4MT 58-34 H from 4+55 to 44+45 for mainline, turn lanes and sideroads. Use 4MT 58 34 V from 44+45 to 173+00 for mainline, turn lanes and sideroads. An addendum will be submitted correcting the Miscellaneous Quantities for the HMA pavements. | Mike Coleman | 3 | 2022-12-05 17:42 | 2022-12-06 10:34
20221213 | 20221213020 | 20 | ASP 5 | Embankment is not listed as an item for payment, Can that be listed as an item for payment with ASP 5? | ASP-5 was added to the proposal via addendum #02. ASP-5 does not list SPV items on the document itself, however, roadway embankment is part of the grading items and is included in ASP-5 computations. A list of items can be found in FDM 19-15-90. https://wisconsindot.gov/rdwy/fdm/fd-19-15.pdf#fd19-15-90 Special provision article 29 specifies that ASP-5 will be applied to Roadway Embankment, Item SPV.0035.01 with a Fuel Usage Factor is 0.23. | Mike Coleman | 10 | 2022-12-06 10:07 | 2022-12-06 11:08
20221213 | 20221213030 | 30 | Plan Profile | The plan and profile shows that the new proposed surface height will be approximately equal to the thickness of the new HMA (up 0.48'). Based on the typical section, the detail shows pulverized material in the shoulder matching the height of the first lift of HMA. If the excess pulverized material is insufficient in quantity to cover the proposed typical section (i.e. placing pulverized material in the shoulders after first lift of HMA) will the height of the road be lowered? | The region would not change the profile of the roadway. We estimated there would be adequate materials for this, but if not, then 1.25â€ base aggregate dense would be used to meet the proposed profile. Material would be paid for at bid cost if needed. | Fred Schunke | 3 | 2022-12-06 12:41 | 2022-12-08 15:08
20221213 | 20221213029 | 29 | Traffic on USH 45 for B-43-64 | Is it possible to perform the work on B-43-64 associated with concrete masonry endwalls, backfill structure Type B, riprap, etc. with temporary signals and temporary barrier shifted to a one-lane road configuration? This would reduce the amount of time needed to perform the work; which would therefore reduce the impact on the traveling public. If this is allowed; will these items be added to the contract. | The intent is to stage USH 45 as shown in the plan and special provisions. Flagging operations will be needed for closures outside the timeframes of the full closures of USH 45. USH 45 will be open to two-way, two-lane traffic outside of the detours and single lane closures. Temporary signals were investigated in design but were not pursued further do to queuing concerns on USH 8 due to the close proximity of that intersection. | Mike Coleman | 8 | 2022-12-06 13:33 | 2022-12-07 08:31
20221213 | 20221213008 | 8 | Earthwork Verification | Is the pavement, curb, and sidewalk removal being paid as unclassified excavation along with being paid by their own unit price items? In addition to salvage unusable pavement cut where is the remaining cut material of 3,652 CY being generated from? In the earthwork data tables there are no notes shown and the salvage unusable columns show zeros. Can you please update the tables to include salvaged unusable and usable cut material per station? Median grading station 14+50-20+00 LT cross sections and the asphalt shoulder cross sections do not match the typical sections. Cross sections show what appears to be a cut and the typicals only show HMA replacement. Is there grading in these areas? Please clarify. | 1. Yes, the removal of concrete pavement, C&G and sidewalk gets paid under common excavation and removing concrete pavement. 2. The additional cut is from the new concrete being 1.5â€ deeper, space behind curb, the areas of the asphalt and shoulders, new base under shoulders, side streets, driveways, etc. Additional information will not be provided. 3. This is shown as a total value using area of the concrete, C&G and asphalt pavement by division. This information is typically not provided station by station and was not for this specific project due to varying pavement types and widths throughout the project. This should not impact the bid for overall quantity. A revised detailed earthwork table will be included in Addendum 2 with the Salvaged/Unusable columns removed for clarity. 4. The base below the center turn lane from STA 14+50 â€“ 20+00 LT and asphalt shoulders will be replaced per the cross sections. The typical sections and base aggregate dense 1 ï¿½-inch quantities will be revised in Addendum 2 to include the base aggregate material. The earthwork includes this base material. | Mike Coleman | 2 | 2022-12-06 13:43 | 2022-12-08 06:10
20221213 | 20221213021 | 21 | Box Culvert cleaning | could the size of the existing box culvert be provided with the addendum for estimating the CY's? | Page 414 of the 1210-09-71 plans state the size of the cells at 12â€™x250â€™. There are 2 cells that need to be cleaned. The addendum will address that the cleaning should occur between the ends of the apron endwalls. | Mike Coleman | 15 | 2022-12-06 13:58 | 2022-12-07 10:58
20221213 | 20221213036 | 36 | Railroad Flagging | There is no standard special provision included on this project for railroad flagging on structures B-6-201 & B-6-204. The railroad is between 75'-100' from the project site. In the past, projects within this distance of railroad tracks have included standard special provisions for railroad flagging. Will the department be including a provision for railroad flagging on this project, or is railroad flagging not required on this contract? | The special provisions currently include RR STSP 107-026 which doesnâ€™t allow contractor to be reimbursed for 50% of the flagging cost. STSP 107-034 is normally used when there is several weeks of flagging required, which is the case for this project. The special provisions will be updated to replace STSP 107-026 with STSP107-034. With this change, 50% reimbursement will be available for flagging costs. In addition, insurance requirements will increase to $5,000,000/$10,000,000 instead from $2,000,000/$6,000,000. An emergency addendum will be issued to add the correct article. | Mike Coleman | 3 | 2022-12-06 14:21 | 2022-12-09 15:30
20221213 | 20221213001 | 1 | wayside utilization | Would the department allow excess common excavation to be wasted in the wayside site? | No waste material or excess common excavation shall be placed in the wayside site. | Mike Coleman | 2 | 2022-12-06 14:23 | 2022-12-07 14:03
20221213 | 20221213014 | 14 | milling quantity | It appears there may be a typo in the quantity tabulation on sheet 37. STA 490+90 - 493+21 LT & RT Shoulders the S.Y. seem too high for this station range? Please advise. Thanks | DOT project staff has reviewed the miscellaneous quantity table â€œAsphaltic Summary Continuedâ€ on page 37 and found computational errors for Removing Asphaltic Surface Milling on the lines referencing STA 490+90 to STA 493+21 LT and STA 490+90 to STA 493+21 RT, as well as subsequent Subtotal and Item Totals. An addendum will be issued correcting the item quantity and miscellaneous quantity sheet. | Mike Coleman | 1 | 2022-12-07 07:25 | 2022-12-07 11:45
20221213 | 20221213031 | 31 | Stage 4 Traffic Control | The traffic control detail on sheets 249 and 252 thru 257 show a single lane closure in each direction, allowing a 12-ft lane, a 2-ft buffer space, and delineation with traffic control drums positioned in the lane that is to be constructed. This traffic configuration does not allow adequate space to pave the surface layer of asphalt in each 12-ft lane, adjacent to traffic. The paver will need to sit in the space occupied by the TC drums in the closed lane, and equipment will protrude into the open lane in order to construct the pavement to the lane-line. Will traffic be allowed to run bi-directional with tubular marker posts (or tall cones) for delineation on the opposite lane to allow adequate width for construction to construct the pavement? Alternatively, will the contractor be allowed to flag traffic between adjacent intersections to allow for adequate room to construct the work? | The special provision break Stage 4 into two parts Stage 4A and Stage 4B. The full lane closures with traffic control drums is needed during Stage 4A. The work during Stage 4A includes removing temporary asphaltic surface and replacing median noses, curb and gutter, concrete bases and salvaged signal poles. During Stage 4B the special provisions call for using lane closures with flagging operations to pave the surface layer of HMA pavement for the entire project. Once the work for Stage 4A is complete the drums are not required and the paving operation can be completed under flagging operations as stated in the Project Timing and Staging section of the Prosecution and Progress article of the special provisions. Traffic will not be allowed to run bidirectional with tubular markers during Stage 4. | Mike Coleman | 4 | 2022-12-07 07:47 | 2022-12-07 13:56
20221213 | 20221213031 | 31 | Removing Excess Pulverized Material | How will the grade be established to determine that the appropriate depth of material (3-inches) is removed from the project? What criteria will be used to determine that adequate material has been removed, and/or that an adequate base course section thickness remains? Will the department be performing an initial survey, and adding a construction staking item to provide hubs set at a depth of 3-inches below the existing surface? If it is determined in the field that some of the excess 3-inches of material that has been hauled away will need to be brought back to the project, how will this be compensated? | The grade can be established by using the profile provided on the plan and profile sheets. You can tell if the appropriate amount of material has been used by using the profiles on the plan and profile sheet or by following the â€œMainline Pulverize Transition Detailâ€ for tie in locations at the tie in locations at the beginning of the project, the bridge and at station 44+43. An initial survey was completed during design and the profile is shown in the plans. The â€œConstruction Staking Resurfacing Referenceâ€ item should be bid to allow reestablishment of the alignment and grade. See spec below. If the profile in the plan is followed, excess material should not need to be returned to the project. Some material will need to be salvaged at the tie in locations. Salvaging of pulverized material at tie ins is incidental to the Pulverize and Relay bid item. | Mike Coleman | 5 | 2022-12-07 07:58 | 2022-12-09 15:27
20221213 | 20221213031 | 31 | Staging Limits | During Stage 2 & 3, the special provisions instruct the contractor to construct the lanes of STH 17 from Sta 42+00 to Sta 173+00. These staging limits extend 243 Lineal Feet into the section designated for pulverize and relay, south of the end of the reconstruct section at STA 44+43. Is it the departmentâ€™s intent for the contractor to pulverize, relay, and pave a portion of the roadway in each of Stage 2 & 3, with the remainder, from STA 42+00 to the southern limits to be constructed in Stage 4? Will the limits for the full reconstruct section be moved to STA 42+00 to accommodate the staging? | The work for Stages 2 and 3 is from Station 44+43 to 173+00. The contractor will not be required to pulverize, relay and pave a portion of the roadway in Stages 2 and 3. All pulverize and relay work is anticipated to occur during Stage 4. | Mike Coleman | 6 | 2022-12-07 07:59 | 2022-12-07 13:56
20221213 | 20221213016 | 16 | Sprayed Fireproofing | Details 2/A514 and 2/A522 show Sprayed Fireproofing. Is the entire pedestrian bridge level (including both towers) to receive fireproofing? What is the hourly rating and UL Design? Please advise. | The underside of bridge floor deck and all steel beams on the underside of bridge to be 2 hours fire rated with spray-on fire-rating material UL design number #D902 or approved equal. This will be clarified in an upcoming addendum. | Fred Schunke | 8 | 2022-12-07 08:21 | 2022-12-08 15:10
20221213 | 20221213018 | 18 | Bicycle Rack - Custom Branding plates | In requesting quotes for materials. The stated supplier in the special provisions for the bicycle racks no longer supplies or fabricates Custom branding plates for their supplied bicycle racks. Is this something that will still be required for this item, if the specified supplier no longer provides? | The City of West Allis would still like to match our existing custom â€œWest Allisâ€ cut-out lettering and bike logo bicycle racks (see photo in Box Link). There are many different manufacturers of similar bike racks. Please use Madrax as the bike rack manufacturer (Level 1 Customization for a Custom U-Rack with City of West Allis Lean Bar, in-ground mount, powder coated black) or approved equal. Quotes available at https://info.madrax.com/custom-bike-racks or by calling (800) 448-7931. https://wisdot.box.com/s/w6gttaclfd5uktg07oo455pua3avrzd4 | Fred Schunke | 6 | 2022-12-07 08:33 | 2022-12-08 15:01
20221213 | 20221213009 | 9 | Sawing Asphalt Item | There is no sawing asphalt item on this project. Will there be an item added for sawing at the culvert pipes and also the 10+ driveways for removal on the project? | The Sawing Asphalt item will not be added. Tie-ins at appropriate driveway locations were accounted for in the Removing Asphaltic Surface Butt Joints quantities. Since the culvert pipe removals will be happening early in the construction sequence under closed-road conditions and prior to anticipated full depth milling operations, a sawed edge at the pipe replacement limits will not be necessary as long as a suitable driving surface as prescribed in the special provisions and appropriate transitions between the pipe replacement limits and the existing pavement are maintained. | Mike Coleman | 3 | 2022-12-07 08:39 | 2022-12-07 14:00
20221213 | 20221213009 | 9 | Shaping Shoulders | On the south end of the project from the Crawford County Line to station 1489+75 a good majority of the existing asphalt is 24' wide. The proposed finished width of new asphalt in this section is 26'wide. Would either a shaping shoulders or Prep Foundation for Asphaltic shoulders item be considered? | Prepare Foundation for Asphaltic Shoulders will be added to the station range in question as part of an upcoming addendum. Other final grading work on the shoulders will be covered by the Base Aggregate Dense ï¿½-Inch quantities already included in the plans. | Mike Coleman | 4 | 2022-12-07 08:46 | 2022-12-07 14:00
20221213 | 20221213027 | 27 | 6" Under Drain Removal - Asbuilt Detail | Can an asbuilt detail of the existing 6" Under Drainage be provided? Need to know where the Fabric is: around the trench, under the entire roadway or around the pipe only (wrapped). | The as-built detail can be found on the last page of the PDF at the following location: https://wisdot.box.com/s/m24hjfpan3oo9bco7gs598sx86rz4xuy or can be accessed on the HCCI December bid letting page under Supplemental Information. The as-built is not for bidding purposes. | Fred Schunke | 3 | 2022-12-07 10:07 | 2022-12-08 12:28
20221213 | 20221213021 | 21 | Culvert Replacement at Station 227+52 | Culvert Replacement at Station 227+52 - Would you pay for temp. asphalt surface the same as the culvert replacement on Riverside Drive? Would it be possible to do the culvert replacement under a full nighttime closure? The eastbound lanes at that location do not allow enough room to flop traffic. | Asphaltic Surface Temporary will be added to the contract to be placed for staging purposes. A future addendum will address the changes. At this time, DOT is not entertaining a full closure of EB STH 172 due to potential disruptions to traffic. We feel the culvert can be replaced within the footprint of the existing roadway and shoulders. | Mike Coleman | 16 | 2022-12-07 11:31 | 2022-12-08 06:08
20221213 | 20221213018 | 18 | Pedestrian Traffic | With the concrete paving grading limits approximately two feet behind the back of curb it appears that there isn't going to be the required 5'-0 pedestrian sidewalk walkway in areas. What will be required in those areas to maintain pedestrian traffic? | Pedestrian through traffic will be allowed to be detoured around the project construction limits via Six Points Crossing and W. Greenfield Ave. on the north side of the road; and S. 65th St., W. Lapham Street and S. 62nd St., on the south side of the road. Residential properties in the project limits have existing access from the back of their lots. The contractor will be required to maintain pedestrian access to businesses along W. National Avenue on temporary pedestrian surfaces or existing concrete sidewalk from the nearest cross street. | Fred Schunke | 7 | 2022-12-07 12:47 | 2022-12-08 12:31
20221213 | 20221213001 | 1 | Traffic | Traffic section in proposal Stage 2 paragraph last sentence "Only one flagging operation at a time can be performed within the project limits without prior approval of the engineer" Will this be an issue? to complete this project in 65 days there will be more than one flagging operation on the project limits at the same time. | More than one flagging operation will be approved if there is a minimum distance of 1 mile between flagging operations. Per SDD Traffic Control for Lane Closure with Flagging Operation, if the distance between flaggers exceeds 2 miles, a pilot car will be required. | Fred Schunke | 3 | 2022-12-07 13:06 | 2022-12-08 13:46
20221213 | 20221213024 | 24 | Pavement Markings | Good afternoon, it appears there are enough temporary epoxy quantities for 2 applications when the plan set calls out for a single application on the surface after pass #2. Please confirm the department's intentions for this item. Will an addendum be issued to correct the quantities? Thank you. | The temporary epoxy quantity is incorrect in the miscellaneous quantities and one application is necessary. An addendum will be sent today to correct the temporary epoxy quantity. | Fred Schunke | 4 | 2022-12-07 13:13 | 2022-12-08 14:02
20221213 | 20221213021 | 21 | Box culvert cleaning | There will have to be some clearing done to be able to remove the dirt from the box culvert. Will this be a bid item or is it incidental to the item? | The operations used for the cleaning of the box cells is considered a mean and methods for the contractor. If clearing is required, it should be incidental to the bid item Cleaning Concrete Box Culvert B-05-184. Any trees deemed necessary to be cleared would need to be included as part of the ECIP. It should be noted that there are NLEB restrictions listed in article 3E and that clearing would need to follow those restrictions and approval process. Clearing of trees 3-Inches or greater would have to be done prior to April 1st. | Fred Schunke | 17 | 2022-12-07 13:39 | 2022-12-08 15:17
20221213 | 20221213032 | 32 | Tribal Entry Permits | Will the Department be reimbursing contractors for the the fees due for Tribal entry permits? If not will a bid item be added for these costs? |  |  | 2 | 2022-12-07 15:45
20221213 | 20221213016 | 16 | Elevator Manufacturers | Please advise if Schindler would be an acceptable elevator manufacturer. They are not listed in the spec currently. Would like to propose using the Schindler 5500 model which is comparable to what is specified. | No, Schindler is not acceptable since this is proprietary equipment. The elevator equipment shall be third party, non-proprietary in nature, per the contract documents. | Fred Schunke | 9 | 2022-12-07 16:38 | 2022-12-08 15:11
20221213 | 20221213018 | 18 | Design Schedule - Electronic CAD files | Can a design schedule and any Electronic CAD files available be provided? |  |  | 8 | 2022-12-07 16:48
20221213 | 20221213021 | 21 | Special Provisions 5. Traffic I Temp Work Clear Zone | Will construction activities be allowed immediately adjacent to traffic during single and double lane closures? In the EB and WB 6-Lane sections will removals, patching, paving, etc. be allowed in the single lane closure prior to the double lane closure times? | The contractor is allowed to work directly behind lane closures. The 15â€™ clear zone referenced in article 5 I references when lane closures are not in place. The contractor is allowed to work directly behind the single lane closures in the 6-lane section as long as the work is not encroaching within the adjacent travel lane. | Fred Schunke | 18 | 2022-12-08 08:07 | 2022-12-08 15:18
20221213 | 20221213004 | 4 | Rock Excavation | If rock is encountered within the sanitary or water trench excavation will a rock excavation item be added through a change order? | Design assumes that rock excavation will not be required, but if encountered, the department will pay for the required excavation as specified for extra work in 109.4. | Fred Schunke | 1 | 2022-12-08 08:37 | 2022-12-08 15:14
20221213 | 20221213004 | 4 | Sanitary Sewer and Water Main Trench Backfill | Is native soil expected to be used as trench backfill for the sanitary sewer and water main as part of the base bid unit rate? If unsuitable native soils are encountered, will a change order granular backfill item be established to remove the unsuitable materials and import replacement granular trench backfill? | Native material will not be permitted as backfill unless it meets the requirements of 209.2.2 Gradation, Grade 1, as spelled out in construction details on sheet 4 and 5 of the plan. Backfill shall be per typical finished section on sheet 4 and 5 for all project trench areas within the roadway and considered incidental to the bid items per the special provisions. | Fred Schunke | 2 | 2022-12-08 08:41 | 2022-12-08 15:15
20221213 | 20221213012 | 12 | Salvage Interior Superstructure Beams | Is the intent to salvage all interior beams, or the two newer ones in each span? We have concern having a salvageable product once the wearing course is removed from the beams. | All of the interior beams are to be salvaged. The village desires to salvage as much usable timber as possible. | Mike Coleman | 1 | 2022-12-08 08:49 | 2022-12-09 15:25
20221213 | 20221213016 | 16 | Exterior Aluminum Fence | Sheets 26 and 114 show fence at the east tower enclosing the generator and transformer pads. Is this the same fence as shown on page 197? What line item is this fence paid under? | The fence shown on sheet 197 is the fence type to be used enclosing the generator and transformer pads shown on sheets 26 and 114. This fence is paid under item SPV.0165 Special 06. Louvers. | Mike Coleman | 10 | 2022-12-08 09:13 | 2022-12-09 04:45
20221213 | 20221213032 | 32 | Removing Longitudinal Notched Wedge Joint Milling | Will you add the item 204.0126S Removing Longitudinal Notched Wedge Joint Milling to the contract? Normally on this type of job we would see that item. |  |  | 3 | 2022-12-08 09:28
20221213 | 20221213004 | 4 | Geotechnical Report | Is there a Geotechnical Report available for project 5180-00-71? | No geotechnical report is available. | Fred Schunke | 3 | 2022-12-08 09:59 | 2022-12-08 15:13
20221213 | 20221213013 | 13 | 512.1000 Piling Sheet Steel Temporary | I do not see the piling sheet steel temporary on the plan set. What is the retained grade? The plans also do not indicate the required section modulus. | Piling Sheet Steel Temporary is shown on Page 102 in the plan set within the erosion control. The temporary sheet piling is included to provide a cofferdam option to manage lake water intake during outfall and storm sewer construction and to minimize possible sediment that could get it lake in addition to the turbidity barrier. This item will be updated via an addendum to Temporary Shoring. | Mike Coleman | 4 | 2022-12-08 10:06 | 2022-12-09 15:32
20221213 | 20221213028 | 28 | Construction Schedule | Can you please provide the designed construction schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/4w4pukcm9dfbguiz2p8kqva0epeza4zx or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Fred Schunke | 2 | 2022-12-08 10:20 | 2022-12-08 15:27
20221213 | 20221213024 | 24 | Existing Structure STA 123+57 | Can as-builts for existing structure C-38-813 be provided? | The as-built for existing structure C-38-813 can be found at the following location: https://wisdot.box.com/s/onddso51ee4riv72tdnqjdzb3ohzj6t0 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 5 | 2022-12-08 11:14 | 2022-12-09 04:43
20221213 | 20221213031 | 31 | HMA surface | Would the HMA surface for stages 2 & 3 be able to be paved at the end of their respected stages and the island noses get sawed and poured in stage 4. This would help with not having a water bath for the bi-directional traffic and give traffic another 18" of room. would also help with the earlier proposed question of not having enough room to work for surface in stage 4. | Bid the traffic control per plan. | Mike Coleman | 7 | 2022-12-08 11:30 | 2022-12-09 15:28
20221213 | 20221213015 | 15 | Special 02. 10" Water Main Constructed Using Directional Drilling, Ductile Iron - PIPE TYPE | Special 02. 10" Water Main Constructed Using Directional Drilling, Ductile Iron TR FLEX AVAILABILITY IS UNKNOWN OR MAY HAVE A LEAD TIME OF 12 MONTHS, CAN ANOTHER PIPE TYPE BE USED? |  |  | 2 | 2022-12-08 16:39
20221213 | 20221213029 | 29 | Charter Line at station 1411 | The plans indicate a Charter utility line on the west side at station 1411 that will be in conflict with the cofferdam installation. the special provisions do not address the movement of this line which will be required to install the cofferdam and provide for dewatering. Does the DOT have a plan for relocating this line? | The Charter/Spectrum utility line is mislabeled in the plans at this location for the area of the cofferdam installation. The line that is being questioned in is the Frontier Communications of WI LLC line that will be relocated approximately 30 feet to the west of the existing facility and the existing facility will be discontinued in place as described in the Special Provisions. | Mike Coleman | 9 | 2022-12-09 09:31 | 2022-12-12 07:03
20221213 | 20221213021 | 21 | A.8 Hazard Protection | Could you please clarify what this statement is saying from page 4 specifications: A.8 Hazard Protection Follow spec 104.6.1.2.4(2), except as follows: â€¢ At Structures B-05-108, B-05-121, B-05-147, B-05-148, B-05-149, B-05-151, B-05-157, B-05-171, B-05-173, B-05-176, B-05-178, B-05-180, B-05-190, B-05-182, B-05-332, B-05-333, and B-05-386, eliminate the need for delineation within 7 calendar days after removing permanent roadside safety devices. Is this trying to say that you are giving only 7 days to complete each wing wall repair? If so that would be a tall order. | A.8 Hazard Protection is referring to the removal and replacement of guardrail. The contractor has 7 days from removal of the existing guardrail to install the new devices. Delineation is referring to temporary traffic control devices delineating the temporary hazard. | Mike Coleman | 19 | 2022-12-09 14:12 | 2022-12-12 06:41
20221213 | 20221213017 | 17 | Design Schedule | It appears the link for the design schedule has expired. Can it please be reset? | The design schedule can be found at the following location: https://wisdot.box.com/s/t1pa0o2pv79nxq7g60eycjhzubp2mk6v or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2022-12-10 11:39 | 2022-12-12 06:54
20221213 | 20221213027 | 27 | Design Schedule | Can the design schedule be provided? |  |  | 4 | 2022-12-11 13:20
20221213 | 20221213027 | 27 | Concrete Centerline Repair | Concrete Centerline Repair is shown in the plans, but there is no bid item. Will a bid item be added to the bid or an item established after the bid? |  |  | 5 | 2022-12-12 10:57