## qandasearchletting_results
Date: | 2023-03-13
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20230314 | 20230314003 | 3 | Watermain | Does the watermain going through the casing need to be restraint joint or regular TJ pipe? | The watermain that runs through the casing pipe will require restraint joints. | Mike Coleman | 1 | 2023-03-09 07:28 | 2023-03-13 12:14
20230314 | 20230314005 | 5 | Restoration Quantities | The proposal has a total bid quantity of topsoil and seed represent approximately 6,000 SY of ground. However there is 1,285 SY of mulch and over 26,000 SY of erosion mat called out. Are the topsoil and seed vastly underestimated or is the mulch or erosion mat severely inflated? | For 5030-01-73 the erosion mat was accounted for twice. It was accounted for under the actual bid item 628.2008 Erosion Mat Urban Class 1 Type B and included for informational purposes under the item 614.0010 Barrier System Grading Shaping Finishing. An addendum will be prepared to remove item 628.2008 Erosion Mat Urban Class 1 Type B from 5030-01-73. In addition to removing item 628.2008 from 5030-01-73, some of finishing items quantities listed â€œfor informational purposes onlyâ€ under item 614.0010 Barrier System Grading Shaping Finishing will be revised in the addendum because they appear to be underestimated. | Mike Coleman | 1 | 2023-02-09 12:34 | 2023-02-22 11:50
20230314 | 20230314005 | 5 | Conflicting Milling and Paving Special Provisions | In the special provisions the first line for milling and paving operation states the lower layer of HMA pavement the same day milling occurs which would mean this job needs to be done as a same day mill and fill. Then 2 lines down it states that project 5030-00-72 & 5030-00-73 pave the lower layer HMA pavement within 72 hours that milling occurs. Which special provision is DOT wanting to follow for project 5030-00-72 & 5030-00-73? | Pave the lower layer within 72 hours of milling. An addendum will be prepared to revise the special provisions. | Mike Coleman | 2 | 2023-03-03 15:15 | 2023-03-07 08:25
20230314 | 20230314005 | 5 | Conflicting Milling and Paving Special Provisions | In the special provisions the first line for milling and paving operation states the lower layer of HMA pavement the same day milling occurs which would mean this job needs to be done as a same day mill and fill. Then 2 lines down it states that project 5030-00-72 & 5030-00-73 pave the lower layer HMA pavement within 72 hours that milling occurs. Which special provision is DOT wanting to follow for project 5030-00-72 & 5030-00-73? |  |  | 3 | 2023-03-03 15:15
20230314 | 20230314005 | 5 | Beam Guard Removal & Reinstallation Requirements | In the special provisions and in the plan it states and shows that in the beam guard replacement locations the beam guard will be removed so that the grading can be done. What's the plan for the structure beam guard because structures can't be left unprotected longer that 3 working days. Is the intent to keep the beam guard down until the final lift of asphalt? If beam guard is installed ahead of the 2 lifts of asphalt after the grading operations the overall height of the beam guard could be an issue and would cause need for adjustments of new beam guard. | Language will be added to the special provisions by addenda to state that guardrail installation shall occur within 7 calendar days from when the existing guardrail is initially removed. | Mike Coleman | 4 | 2023-03-03 15:30 | 2023-03-08 06:20
20230314 | 20230314005 | 5 | Design Schedule | Would DOT be able to supply a Design Schedule for the project. |  |  | 5 | 2023-03-08 08:46
20230314 | 20230314005 | 5 | Mixture Usage Table & Density & Volumetric Test Strips | There is a total of 6 density test strips (3) for 5030-01-72, (2) for 5030-01-73, and (1) for 5030-01-74. There is also (3) volumetric test strips 1 for each project. We don't think there is a need to have this many test strips for the entire job because 5030-01-72/73/74 are the same pavement thickness, so you would only need 1 volumetric and 2 density tests strips for 5030-01-72/73/74. The only thing that would warrant the need for more than a total of 3 test strips would be a change in thickness in the project. There are two sections that are different thickness from STA 163+44 - 168+65 & 378+05 - 386+06 on project ID 5030-01-72, These two sections are too short to do a a test strip a rolling pattern couldn't be establish in those sections. So, if the intent to keep those two sections at 2" HMA they should be eliminated from the PWL platform and be considered as QMP. DOT could also adjust the thickness at STA 163+44 - 168+65 to 3.5" and leave STA 378+05 - 386+05 at 2" pavement | An addendum will be prepared to revise quantities for 2 Test Strip Density and 1 Test Strip Volumetrics. | Mike Coleman | 6 | 2023-03-08 13:56 | 2023-03-09 13:09
20230314 | 20230314005 | 5 | Beam Guard Section Milling & Paving to meet the 7 calendar requirement | With the DOT going through with the beam guard being removed and installed within 7 calendars, is the intent to complete all the milling and paving operations including both binder and surface in those 7 calendar days? If that is the case in those sections (31 sections) that mix should be eliminated from the PWL test requirement because those sections are too short to establish any rolling pattern. |  |  | 7 | 2023-03-09 16:59
20230314 | 20230314006 | 6 | Soil Borings | Are soil borings available for this project? | The soils report can be found at the following location: https://wisdot.box.com/s/0kbminm4gwhfu3upnbx8y99q3j9wie7t or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-03-03 15:01 | 2023-03-07 08:28
20230314 | 20230314008 | 8 | Design Files | Can the Department provide the meta-data for this project? | This is a local program project. On local program projects, there is no requirement for contractor data packets. | Mike Coleman | 1 | 2023-02-27 09:48 | 2023-02-27 10:22
20230314 | 20230314011 | 11 | Base Patch Shes | sheet 32 shows base patch concrete SHES. What item will that be paid under on the contract? | The base patching concrete SHES, item 390.0403 and quantities will be provided in Addendum #1. | Mike Coleman | 1 | 2023-03-03 09:02 | 2023-03-07 08:29
20230314 | 20230314012 | 12 | Design Schedule | Can the DOT design schedule be provided for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/derfnmf8dj6c6r93hzj4sizuovhub1p0 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-02-15 16:17 | 2023-02-22 11:30
20230314 | 20230314012 | 12 | Contractor Data Packet and Schedule | Can the contractor data packet and design schedule be made available? | The Contractor Data Packet can be found at the following location: https://wisdot.box.com/s/9xo46loybvgx9vh17o6otj18ykrl9u2g can be accessed on the HCCI February bid letting page under Supplemental Information. The design schedule can be found at the following location: https://wisdot.box.com/s/derfnmf8dj6c6r93hzj4sizuovhub1p0 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-02-16 10:03 | 2023-02-27 08:57
20230314 | 20230314012 | 12 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/derfnmf8dj6c6r93hzj4sizuovhub1p0 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2023-02-16 16:52 | 2023-02-22 11:39
20230314 | 20230314012 | 12 | Can the drainage tables be provided in excel format? | Can the drainage tables found on sheets 707 to 724 be provided in excel format? | The drainage tables can be found at the following location: https://wisdot.box.com/s/derfnmf8dj6c6r93hzj4sizuovhub1p0 can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 4 | 2023-02-20 21:34 | 2023-02-22 11:04
20230314 | 20230314012 | 12 | General Notes - #15 - Finishing Roadway | Plan Page #2 - General Notes - #15 FINISHING ROADWAY SHALL INCLUDE CLEANOUT OF EXISTING DRAINAGE STRUCTURES AS DIRECTED BY THE ENGINEER. Please include a number and location of these structures, so the bidder can determine a price to include in the bid. Please consider adding a new bid item to handle this item. | The design team will remove note #15 from the general notes and will add the following SPV bid item, â€œCleaning Drainage Structuresâ€ with an undistributed quantity of 40 Each. This will be addressed with the upcoming Addendum 1. | Mike Coleman | 5 | 2023-02-22 11:28 | 2023-02-23 08:35
20230314 | 20230314012 | 12 | soil borings | Can the soil borings be provided for this project? | Soil borings were not obtained for the project. However, a Level 1 Subsurface report can be found at the following location: https://wisdot.box.com/s/derfnmf8dj6c6r93hzj4sizuovhub1p0 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 6 | 2023-02-22 12:23 | 2023-02-23 08:37
20230314 | 20230314012 | 12 | SPV0060.0152 & SPV0060.0153 | Please provide the CUC plan pages & CUC detail page showing conduit installation, expansion fittings & hanger information for the Underdeck Utilities Structures B-40-206 & B-40-207 | The CUC plan pages and detail page can be found on sheets 372 - 380. | Mike Coleman | 7 | 2023-02-22 14:02 | 2023-02-27 09:00
20230314 | 20230314012 | 12 | 1-1/4" Base Quantity | It appears the 1-1/4" Base quantity total is missing Stage 5. The overall quantity should be 95,428 ton, please confirm. | The design team agrees that the overall base aggregate dense 1 ï¿½-inch quantity should be 95,428 ton. This revision will be addressed as part of Addendum 1. | Mike Coleman | 8 | 2023-02-22 15:42 | 2023-02-23 10:27
20230314 | 20230314012 | 12 | Milling and Paving Operations | The plan calls for final surface to be placed prior to opening to traffic. Is it really your intention to mill the existing pavement and place both lower and surface pavements within a single nighttime closure? | In sections of the corridor where the roadway is superelevated and sloped towards the drive lanes and there is the potential of storm water ponding, it is recommended to mill and overlay to final surface to eliminate ponding within the drive lanes. In areas where the roadway slopes towards the shoulder/away from the drive lanes, the surface can be milled with just the lower layer required to be placed before opening to traffic. | Mike Coleman | 9 | 2023-02-27 11:13 | 2023-02-27 14:32
20230314 | 20230314012 | 12 | Monotubes | Project has Type 9 and Type 10 Special monotube poles but isn't calling out any Special Monotube arms. Is that correct? | The monotube arm bid items will be updated as part of Addendum 1. | Mike Coleman | 10 | 2023-02-27 19:07 | 2023-03-01 05:40
20230314 | 20230314012 | 12 | Core Pilot Project | A failing core test would require additional coring forwards and backwards to find the limits of the area in penalty. How are we to handle this considering that traffic will be running on the surface long before a failing core test result would come in? | Overnight lane closures will be required to perform the additional coring operations. Traffic should be okay to drive on the pavement temporarily until fixed. The project has bid item, â€œMobilizations Emergency Pavement Repairâ€ as well, if needed. | Mike Coleman | 11 | 2023-02-28 10:51 | 2023-03-01 05:41
20230314 | 20230314012 | 12 | Earthwork Tables | Could the Department release the earthwork tables in excel format? | The earthwork tables can be found at the following location: https://wisdot.box.com/s/derfnmf8dj6c6r93hzj4sizuovhub1p0 or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 12 | 2023-03-03 09:54 | 2023-03-07 08:11
20230314 | 20230314012 | 12 | Can the structure tables on sheets 716-724 be provided in excel format | Previously in question 4 drainage tables were requested in excel format from sheets 707 to 724, upon reviewing the data it appears only the pipe tables were provided, can the structure table found on sheets 716 to 724 be provided in excel format? | The drainage excel files for both the pipes and drainage structures can be found at the following location: https://wisdot.box.com/s/derfnmf8dj6c6r93hzj4sizuovhub1p0 or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 13 | 2023-03-06 17:04 | 2023-03-07 16:13
20230314 | 20230314012 | 12 | QMP Subgrade? | This project doesn't seem like a QMP Subgrade project, Median & Shoulder reconstruction with a typical finished section of 45" of Asphalt, Base and Select Crushed. Not sure how that vertical cut along the existing pavements is going to hold up as the subgrade get disked and dried to meet the moisture requirement and with that thick of a finished typical section does the subgrade need to be tested? Also with no soil borings preformed on this project how is the contractor supposed to know how much subgrade improvements will be required? Please consider removing the QMP subgrade on this project. | After further review, we will remove the QMP Subgrade article from the project. This will be addressed as part of an addendum (Addendum 2). | Mike Coleman | 14 | 2023-03-07 14:46 | 2023-03-08 11:36
20230314 | 20230314012 | 12 | SHES Batch Patching | Can overnight base patching be performed on the inside or center lane (the area that would be under the temp barrier wall in stage 2) prior to the placement of temp barrier wall required for stage 2 median work? This work would occur after stage 1, but before stage 2. Lane configuration would be the same as Stage 2, but drums would be used in lieu of the temporary barrier while the concrete is curing. This question also applies to base patching work prior Stage 4. | The department is supportive of the contractor advancing work shown from a later stage to an earlier stage for schedule and cost efficiencies provided daytime/peak hour operations and intermediate completion dates shown are not impacted beyond what is shown in the plans. Base patches should not encroach into the travel lanes. Specific work operations would require further coordination with the department during construction. | Mike Coleman | 15 | 2023-03-08 11:53 | 2023-03-08 11:54
20230314 | 20230314012 | 12 | Draintile/Open Grade/DF Schedule A Fabric | Can a little more clarification be provided on how the following items are to be paid? The draintile detail on sheet 209 indicates that both the open graded material and the geotextile fabric type DF schedule A are incidental to the item pipe underdrain 6-inch special. If you multiply the draintile footage 12,749 LF by the 5' of fabric per LF you get 7,083 SY of fabric matching line number 644, is the fabric incidental as stated on sheet 209? Additionally, if you review sheets 675-676 open grade material is shown in large quantities throughout the job, the typical sections from sheets 16-32 only show 4" of open grade on sheet 16, and no other open grade in the remaining typical sections. There is less than 1000 tons needed of open grade for draintile if its incidental and the pay quantity is 15,639 tons, where is this material supposed to go and is the underdrain quantity included? |  |  | 16 | 2023-03-11 22:58
20230314 | 20230314012 | 12 | Stage IV | For Stages IV A and IV B the Traffic Control Sheets appear to show there are long term ramp closures. However, Special Provision 5. IH 43, Stage IV Re-Open Ramps provides 14-day ramp closures that appears conflicts with the plan sheets. Can WisDOT clarify? Are the 14-day ramp closures for electrical work or some other work other than the major items of work? | Stages IV-A and IV-B in the plan set show all the work that is to be completed as part of that stage and is not intended to be completed simultaneously. It is intended that only ramps that are being worked on should be closed at a time and closed up to 14-days per ramp. Some ramps are closed long-term during the entire duration of Stage II. The contractor may choose to take advantage of these earlier closures to complete some ramp work earlier. Specific work operations would require further coordination with the department during construction. | Mike Coleman | 17 | 2023-03-13 09:36 | 2023-03-13 13:09
20230314 | 20230314013 | 13 | Shotcrete | Would shotcrete be considered an acceptable alternative lining method instead of the CIPP for this project? Thank you! | The response to the use of shotcrete question is no. From the City Engineer: Shotcrete is not waterproof, so the answer is no. Since we're lining under the train tracks and it's sanitary, shotcrete will not be accepted. | Mike Coleman | 1 | 2023-02-20 08:42 | 2023-02-21 09:12
20230314 | 20230314013 | 13 | Earth work quantities and boring request | In the Earth work summary for the project, is the Asphalt pavement taken in to account with the Salvaged / Unusable Pavement Material Section (4)? Also are there any borings logs associated with the proposal that could be shared? | The asphalt pavement is included in the salvaged unusable quantity in the earthwork summary for the project. The average unusable material depth was generally assumed to be 1â€™ for the width of the existing roadway. The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/1fxwbml1h1nh6lo1e55h9smzrorvzdhi or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-03-07 16:52 | 2023-03-08 11:29
20230314 | 20230314013 | 13 | CIPP LIning 42" and 12" | Are there sewer videos of the 42" and 12" segments we can review prior to bid? | The storm sewer videos can be found at the following location: https://wisdot.box.com/s/1fxwbml1h1nh6lo1e55h9smzrorvzdhi or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 3 | 2023-03-09 16:02 | 2023-03-13 12:08
20230314 | 20230314014 | 14 | Joint Repair | What â€œjoint repairâ€ is required for the transverse joints shown on the removal plans and what bid item does it go with? | The transverse joints noted are to be repaired per SDD 13C9. The bid items that go along with this are as follows: 204.0100 Removing Concrete Pavement 416.1710 Concrete Pavement Repair 416.0610 Drilled Tie Bars 416.0620 Drilled Dowel Bars 690.0250 Sawing Concrete | Mike Coleman | 1 | 2023-02-24 11:30 | 2023-02-27 14:37
20230314 | 20230314014 | 14 | Hampton Ave. Milling | For milling on Hampton, is the intent to remove a uniform 4â€ of asphalt/concrete from curb to curb and maintain the existing slope, no adjustment? Depth of milling over the curb pan will be ~1.75", correct? | Correct, milling is a uniform 4â€. See the notes on the first page of the proposed typical sections. There is the possibility that the existing curb pan has more than the 1.75â€-2â€ of hma present. The intent is for the existing curb head once the pan is paved will have a 4â€ reveal. | Mike Coleman | 2 | 2023-02-24 11:34 | 2023-02-27 14:37
20230314 | 20230314014 | 14 | PWL Density for turn lanes and cross overs | It is odd for the QMP mix to be associated with PWL density for parking lanes as shown on the PWL table on sheet 419. Is this correct? Also, please clarify whether median turn lanes, crossovers, and minor intersection returns will be PWL or QMP for mix and density. | An addendum will be issued to clarify everything. | Mike Coleman | 3 | 2023-03-01 11:44 | 2023-03-07 08:20
20230314 | 20230314014 | 14 | SIGNAL CABINET & ETHERNET SWITCH | Can you please confirm if the traffic signal control cabinet needs to be the standard City of Milwaukee cabinet or is this open to any NEMA TS2 Type 1 traffic signal control cabinet? Can you also confirm what model number and type of ethernet switch is required? | SPV.0060.205, B Materials, paragraph 2, specifies the cabinet to conform to the city of Milwaukee cabinet design DWG. For the Ethernet switch, the City of Milwaukee has previously accepted Extremeswitching Industrial Ethenet switches, part 16804 (ISW 8GBP, 4-SFP). | Mike Coleman | 4 | 2023-03-08 15:19 | 2023-03-09 13:03
20230314 | 20230314016 | 16 | R-40-724 and R-40-725, MSE Walls | Sheets 143 and 148 state that front face of wall shall receive sack rubbed finish. Is the sack rubbed finish applied at the precast plant or in the field after installation. Is there a set of special provisions for sack rubbed finish? Since panels are poured face down, it is quite difficult to achieve sack rubbed finish at the precast plant. | Sack rubbed finish to be applied following section 502.3.7.5 in the WisDOT standard specification. | Mike Coleman | 1 | 2023-02-18 04:35 | 2023-02-21 13:48
20230314 | 20230314016 | 16 | Protection & Closure of HAST | In the Special Provisions page 2 or 35 3. "Prosecution & Progress" states "Construct and maintain a 12â€™-0â€ x 12â€™-0â€ trail zone above Hank Aaron State Trail during construction. Provide debris protection within this area. Limited short-term closures may be allowed with approval of engineer." Page 4 of 35 4. Traffic states - The Hank Aaron State Trail (HAST) located under the structure will remain open at all times, except when short term closures are necessary to accommodate the removal of existing bridge P-40-856. Other trail closures may be necessary to safely complete work adjacent to the HAST and are subject to approval by the engineer. The contractor shall not close the HAST until the detour traffic control has been installed as shown in the plans. Do not close the HAST over the weekend (end of work on Friday to start of work on Monday), unless approved by the engineer. Please clarify what is expected of the 12' x 12' Construct and Maintain trail zone "above" HAST. | Construct debris protection a minimum of 12' above the travel surface of the Hank Aaron State Trail (HAST), and a minimum of 6' each direction from the centerline of the HAST (12' total). The intent of the trail zone is to protect HAST users at all times during construction. | Mike Coleman | 2 | 2023-03-01 09:19 | 2023-03-08 11:35
20230314 | 20230314016 | 16 | Existing Bird Deterrent System | Per Article 3, Migratory Birds, it states that City of Milwaukee has installed a bird deterrent system. From site visits, there is currently no deterrent system in place. With an April 15th start date for nesting season, will something be installed by owner prior to that date OR item added to the contract for this work? It is assumed that contract would not be executed in time for a contractor to install deterrent system prior to April 15th. |  |  | 3 | 2023-03-10 08:50
20230314 | 20230314016 | 16 | Northern Long-Eared Bat | Per Article 3, Northern Long-eared Bat, there is limitations on clearing operations. With USFWS limiting clearing operations from April 1 - October 31, it is not anticipated that contract will be executed prior to that date to complete clearing operations. The contract has quantity for clearing and grubbing needed for proposed construction limits but this would not be allowed once project starts. Additionally, the article seems to indicate trees larger than 3-inch diameter would be limited and from site visits, it appears that there will be trees that meet that requirement within the grading limits. How will clearing be addressed so as not to impact the northern long-eared bats? |  |  | 4 | 2023-03-10 08:58
20230314 | 20230314016 | 16 | B-40-1008 Structural Backfill | The quantity for structural backfill totals 5,976 ton across the structural approaches and abutments. It is unclear where this quantity goes beyond the standard structural backfill zone as indicated on sheet 7 of 25. Could you provide clarification on the intent and location of all structural backfill for the current plan quantity. |  |  | 5 | 2023-03-10 13:05
20230314 | 20230314017 | 17 | Earthwork | On the earthwork table there is more waste than cut on the job. I believe you have a wrong number copied into the cell. Just wanted to make sure nothing else was off in the table. | The waste volume for Calhoun Road was displayed incorrectly on the Common Excavation table (it was displayed as 4,028 CY, a copy of the cell above, the correct value is 862 CY. This changes to total waste from 8,055 to 4,890 CY. An addendum will be issued to correct this. | Mike Coleman | 1 | 2023-02-20 09:47 | 2023-02-21 11:44
20230314 | 20230314021 | 21 | B-8-9 Diaphragm Pour Height | Reference â€˜Part Longitudinal Sectionâ€™ detail on B-8-9 structure plan sheet 5. The detail shows the diaphragm pour to the surface of the proposed concrete overlay. Low slump overlay machines do not finish along the skew. Provided the 52 degree skew and the crown adjustment, it is not constructible to match the proposed overlay into the previously poured diaphragm pour as detailed. The diaphragm pour will need to be poured low and the overlay placed over the top, as is typical with a joint repair. Will this be allowed? | The Department does not have concerns with this approach. The Contractor will need ensure correct dimensions on the parapets remain as shown in the plans. | Mike Coleman | 1 | 2023-02-16 15:08 | 2023-02-21 13:44
20230314 | 20230314021 | 21 | B-8-9 Steel Shim Height | Reference B-8-9 structure plan sheet 4. What is the required height of the 8â€ x 2â€™-2â€ steel shims. | The height requirement is dimensioned and further described as a note in the abutment elevation detail. | Mike Coleman | 2 | 2023-02-16 15:09 | 2023-02-21 13:46
20230314 | 20230314021 | 21 | Design Schedule | Could the Department provide the construction schedule that was developed during the design phase? | The design schedule can be found at the following location: https://wisdot.box.com/s/sr6i2flall9u1sp3j9feg48w4g6tx1be or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2023-02-28 10:33 | 2023-03-01 05:40
20230314 | 20230314021 | 21 | Base Patching Traffic Control | There is no traffic control information or items for the base patching. Is this assumed to be done in two phases and drums will be paid for under the appropriate bid items? The schedule shows all of the base patching then cure time. Please clarify. | Our intention is to do base patching in 2-phases (halves). We will issue an addendum to cover traffic control items for base patching and special provision language detailing phasing requirements. | Mike Coleman | 4 | 2023-03-08 18:49 | 2023-03-13 07:39
20230314 | 20230314022 | 22 | Asphaltic Surface Mix Design | The specials provisions require a 4 MT 58-28 S mix design for the Asphaltic Surface item. Would the department also allow a 3 MT 58-28 S. | Yes. The department will allow a 3 MT 58-28 S mix for the Asphaltic Surface item. An addendum will soon be posted to allow alternative mix designs for Asphaltic Surface. | Mike Coleman | 1 | 2023-03-03 10:21 | 2023-03-09 13:10
20230314 | 20230314022 | 22 | Milled Surface 72 HR | Under the traffic section of the special provisions it states â€œDo not allow the milled surface to remain exposed to traffic for a period greater than 72 hours.â€ With the project requiring a PWL test strip and widening prior to the beginning of mainline paving would the department change this to 96 hours to allow the milling operation to get ahead of the paving. This would also allow more room for the separate flagging operations to safely operate and reduce potential traffic delays. | : Yes. The department will increase the period from 72 hours to 96 hours. An addendum will soon be posted to address this change in the provisions. The contractor should be aware that there are several locations along the project that will have a relatively thin remaining pavement thickness after milling takes place. The contractor and the department should monitor the condition of the milled pavement for distress after it is exposed to traffic to determine if changes to the contract or work are necessary. | Mike Coleman | 2 | 2023-03-07 11:33 | 2023-03-09 07:51
20230314 | 20230314022 | 22 | Prepare Foundation for Asphaltic Shoulders | Can the department clarify what is expected under the Prepare Foundation for Asphaltic Shoulders item. It is difficult to determine at this point with the snow but if 2' of existing shoulder is bladed out to widen the paved shoulder there may not be room on the shoulder for all the material. On the majority of the project the typical sections only show a 1' finished aggregate shoulder. Will removal of the excess shoulder material be paid for separately? Can the material be pushed out wider than 1'? If not, does the contractor have the option to excavate and remove the existing 2' of aggregate shoulder prior to paving. If this is allowed would the department expect it to be brought back to the project or would new 3/4" base aggregate be placed after paving? | The Prepare Foundation for Asphaltic Shoulders item includes excavating and shaping the existing base aggregate shoulder for asphaltic shoulder construction/widening, incorporating excavated material to shape remaining aggregate shoulders or to widen the roadbed, disposing of surplus or unsuitable material, and other requirements in section 211 of the standard spec. Removal of surplus shoulder material from the project will not be paid separately as it is already covered under item 211.0400 per standard spec 211.3.6. The width and slopes of the finished base aggregate shoulder should not exceed what is shown on the finished typical sections without the approval of the engineer. The contractor may temporarily push some of the material onto the gravel inslopes during construction provided positive drainage and the requirements of standard spec 104.6 are maintained. If the contractor chooses to haul existing shoulder material to a stockpile location, care should be taken to minimize contamination. Suitable existing base aggregate material is expected to be incorporated into the finished aggregate shoulder under item 211.0400, so no additional compensation will be provided for hauling the material away/back, placing/shaping the material, or providing new 3/4â€ base aggregate in locations that had enough material present. Although not currently anticipated, the engineer may direct excess material to be trucked and placed in other areas of shortages which would be paid as extra work under Hauling Excess Shoulder Material, Item 305.0504.S. | Mike Coleman | 3 | 2023-03-07 11:45 | 2023-03-09 08:02
20230314 | 20230314025 | 25 | Design Schedule | Can the Department please provide the preliminary design schedule used for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/h4il4wfmy1mo0z6lxs7rpz16dmr0otyz or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Jill Fehrman | 1 | 2023-03-01 15:48 | 2023-03-06 12:06
20230314 | 20230314025 | 25 | Asphaltic Surface Driveways and Field Entrances | With the miscellaneous quantities calling out a quantity for item 465.0120 Asphaltic Surface Driveways & Field Entrances, and the plan sheets calling out locations for Asphaltic P.E.â€™s, it is unclear how far into the Driveways and Field Entrances the contractor is to remove the surface and repave. Can the department provide clarification on the limits of private entrances? | The item 465.0120 Asphaltic Surface Driveways and Field Entrances is being removed. | Mike Coleman | 2 | 2023-03-02 08:58 | 2023-03-07 08:15
20230314 | 20230314026 | 26 | Culvert Replacements | Are any of the culverts part of the Mecan River or it's tributaries? Or could the culvert replacements be constructed prior to June 15th? | : The special provision language defines where the instream restriction applies. Culverts are subject to the restriction and have to be installed after June 15th. | Mike Coleman | 1 | 2023-02-22 14:56 | 2023-02-23 13:30
20230314 | 20230314029 | 29 | Missing all traffic control items | There is a posted detour but no traffic control items, will there be any added? | The County is responsible for installing and maintaining traffic control for the project (including the detour route); therefore traffic control items will not be added. See paragraph two of article 4 (Traffic) and General Notes on detour plan. | Mike Coleman | 1 | 2023-03-09 11:39 | 2023-03-09 14:19
20230314 | 20230314033 | 33 | Apron Endwalls | The notes in the plan for the AEW replacement at STA 645+90 RT state REMOVE EXISTING RIPRAP. Please clarify how removing the existing riprap is paid and does it need to be replaced. Also, is there restoration (salvaged topsoil/seeding items) that will be required and paid for at the AEW replacements? | The item for removing existing riprap and restoration items at the AEW will be added per addendum. The AEW is being replaced at STA 645+90 RT. | Mike Coleman | 1 | 2023-03-02 10:40 | 2023-03-07 16:14
20230314 | 20230314033 | 33 | Traffic Control / Workzone | Sheet 6 of the plans has a **Note related to traffic control drum offset from centerline. The note allows for 0' Typical and up to 3' for centerline repair. Section 415.3.6.1 requires slipforming on concrete pavement more than 300' in length. All of the concrete pavement removal / concrete pavement 9-inch areas fall within the guidelines of this section. A finisher is required on the drum side of the paving surface to provide the tooling required in section 415.3.6.2 of the Standard Specifications. Will a minimum 4' offset be allowed/provided for trackline and worker safety in concrete paving areas? | A 4-feet offset will be allowed in concrete pavement 9-inch areas. Addendum 1 includes shoulder pavement widening and traffic control lane width restriction signing at these locations. | Mike Coleman | 2 | 2023-03-07 15:01 | 2023-03-09 13:02
20230314 | 20230314033 | 33 | Asphaltic Surface Patching | There is an â€˜Asphaltic Surface Patchingâ€™ item and all of the plan tonnage is undistributed. What is the intended purpose/locations for the tonnage specified? | Asphaltic Surface Patching is intended to be used at ramps and shoulders once the surface is milled to provide the contractor with a means to make minor repairs (i.e. filling potholes, traffic pop-outs and for ramping at the butt joint saw cuts). These locations are unknown and will be identified after milling operations. | Mike Coleman | 3 | 2023-03-08 07:45 | 2023-03-09 13:06
20230314 | 20230314033 | 33 | Removing Asphaltic Surface Butt Joints | There is no detail for the â€˜Removing Asphaltic Surface Butt Jointsâ€™ item and all of the plan tonnage is undistributed. Aside from the Wallace St intersection where it is called out, where is the intended locations for the remaining plan quantity. | The intended locations for Removing Asphaltic Surface Butt Joints are at the intersections/side roads of BUS 53 South LT, STA 665+00 LT, Wallace St. LT, Wallace St. RT, BUS 53 North LT, and BUS 53 North RT. The quantity estimated in the plan are for 25-ft transverse joints at these locations. | Mike Coleman | 4 | 2023-03-08 07:46 | 2023-03-09 13:08
20230314 | 20230314033 | 33 | North Business 53 Ramp | On the North Business 53 Ramp the plan shows to mill and overlay the driving lane and shoulders all the way out to NB USH 53. The existing ramp switches from asphalt to concrete around STA 725+50. What is the intention for the ramp from the switch to concrete to NB USH 53? Is the intention to mill and overlay only the shoulders with asphalt? Or is the intention to mill the concrete and shoulders and overlay with asphalt (this would require a concrete milling item)? | The asphalt/concrete joint at the ramp was missed in the plans. The intention is to mill and overlay the asphalt portion of the ramp only, including the asphalt shoulders. The concrete portion of the ramp, including the concrete curb and gutter, will remain intact. The MSQ sheet shows the mill and overlay station ending at approximately STA 725+28. | Mike Coleman | 5 | 2023-03-08 07:47 | 2023-03-09 13:05
20230314 | 20230314034 | 34 | Article 17. Archaeological Site - Site 47WB147 (Sugar Camp) Site | This article description starts at the CTH H intersection and extends to the CTH A intersection. It also states "do not complete any ground disturbing activities beyond the existing right-of-way limits within the 47WB147 Sugar Camp site". Please provide a map of this site. As there is an existing aggregate operation beyond the existing right-of-way limits within the described location of this site at the USH 63 interchange we don't feel it is the intent of this special provision to preclude this aggregate site from providing materials for the project. | A map of the archaeological area can be found at the following location: https://wisdot.box.com/s/e8myuoscoy772watxdumifkmnjqdq9wl or can be accessed on the HCCI March bid letting page under Supplemental Information. The special provision included in the contract only covers the proposed disturbance within the WisDOT right-of-way to accomplish the project work. If the aggregate pit has a WDNR permit, you can use the pit without further coordination with WisDOT cultural resources. If the pit does not have a WDNR permit, completion of a DT1919 | Mike Coleman | 1 | 2023-03-07 22:28 | 2023-03-09 13:01
20230314 | 20230314034 | 34 | Plan Sheet 23 - Pipe Transition Detail | Please provide a specification for the material to be used as Trench or Foundation Backfill in this detail. Also, this detail requires additional excavation and backfill than would typically be required for a culvert pipe installation. The additional excavation is paid for as Common Excavation, shouldn't the additional backfill material also be paid for as a bid item? | The detail provides for the trench configuration since storm sewer runs are similar to cross drain culverts for this project. Backfill as shown on the detail will be incidental to the pipe per standard spec. 608.5.2. | Mike Coleman | 2 | 2023-03-07 22:34 | 2023-03-09 13:09
20230314 | 20230314034 | 34 | Plan Sheet 207 - Miscellaneous Quantities Earthwork Summary | Note 3 on this plan sheet states "EBS excavation to be backfilled with Backfill Granular Grade 1 material" There is not currently a bid item for Backfill Granular Grade 1. Please provide a bid item for this EBS backfill material. | This note is in error. No Grade 1 Granular backfill is required. If a future addendum is issued, this error will be corrected. As shown on sheet 207 of the plan in the Earthwork Summary, the EBS is paid as Excavation Common and any necessary backfill is paid as Borrow per standard spec 208. | Mike Coleman | 3 | 2023-03-07 22:39 | 2023-03-09 13:07
20230314 | 20230314034 | 34 | Article 17. Archaeological Site - Site 47WB61 (Mitchell) Site | Please provide a plan sheet showing the limits of this identified site similar to what was provided for the Sugar Camp Site. | The archeological Site 47WB61 can be found at the following location: https://wisdot.box.com/s/e8myuoscoy772watxdumifkmnjqdq9wl or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 4 | 2023-03-09 18:53 | 2023-03-13 12:12
20230314 | 20230314036 | 36 | Temp Barrier Anchoring | Please confirm that the barrier wall on this project will need to be anchored. Past projects have not required anchoring of block on a bridge joint repair project. | Anchoring was included as dropoffs/setbacks on this project meet the requirements outlined in SDD 14B7 for anchoring. | Mike Coleman | 1 | 2023-03-06 12:53 | 2023-03-13 07:48
20230314 | 20230314037 | 37 | Riprap | Specials state that all rip rap installed above the ordinary high-water mark will be backfilled with 3/4" Base. Will the 3/4" base be paid for under the contract item or is it incidental to the riprap item? |  |  | 1 | 2023-03-02 08:06
20230314 | 20230314037 | 37 | Grading | Finished typical section shows select borrow fill and salvaged topsoil on the slope widening throughout the approaches which I would assume would be paid for under the applicable bid items of Select Borrow and Salvaged Topsoil. There is also a bid item for Barrier System Grading Shaping Finishing that seems to fall within the same stationing. Can you please clarify how the slope fills, salvaged topsoil, and restoration will be paid for on the project? | The grading shaping and finishing bid item is called out for the beam guard terminal EATâ€™s and beyond. Any transition grading or slope correction that MAY be necessary between the EATs and the bridge abutments , not including what is covered under the Structure Backfill item, shall be paid separately under the individual items of Select Borrow, Salvaged Topsoil, and gardening items as shown in the miscellaneous quantities. | Jill Fehrman | 2 | 2023-03-02 08:24 | 2023-03-06 12:09
20230314 | 20230314037 | 37 | Grading | The finished typical section appears to show the existing shoulder being cut down at approximately 15' and then placing 6" of 1 1/4" base. There doesn't appear to be a Common Excavation item in the contract and the Barrier System Grading Shaping Finishing item shows 0 CY of Common Excavation in the "INFORMATION ONLY" earthwork summary in the cross sections. Can you please clarify how these shoulder cuts will be paid? | The â€œINFORMATION ONLYâ€ quantity for Common Excavation should have shown 10 CY per beam guard EAT to prepare the shoulder for the additional asphalt that gets paved out to the face of the terminal. This common excavation can be used for fill immediately below/outside the cut. The total â€œinformational onlyâ€ common excavation for the project should have been 40 CY. | Jill Fehrman | 3 | 2023-03-02 08:35 | 2023-03-06 12:12
20230314 | 20230314038 | 38 | Item 502.3210 Pigmented Surface Sealer | Estimate of Quantities in Structure Plans call for Item 502.3210 Pigmented Surface Sealer, however, the Item listing for the Project does not include this item. Will the Dept be issuing an addenda correcting this? | An addendum will be issued to add item 502.3210 Pigmented Surface Sealer to the item listing. | Mike Coleman | 1 | 2023-02-20 11:20 | 2023-02-21 09:10